## Read Me
MASTER WEBSITE — 2-DAY BUILD PLAN ¦ FULL VISUAL WEBSITE BUILDER ¦ GOOGLE AI STUDIO
Item | Decision / Instruction
Purpose | Build the complete requested internal company master website in 2 days starting 20-Sep-2026 for approximately 20 company users, including the genuinely flexible visual website builder and all Projects, Finance, HR, reimbursement, salary, investment, MOM and custom-page requirements.
Critical implementation strategy | Use Google AI Studio with the user's existing Google AI Pro subscription as the primary AI-assisted implementation environment. Use mature/open-source components and Google services already available to the user wherever practical. The architecture must target ₹0 additional software/service spend.
What 'full builder' means in this plan | Drag/drop elements anywhere; resize; arbitrary columns/containers; nested layouts; responsive breakpoints; typography/spacing/borders/backgrounds; animations/interactions; custom CSS; custom JavaScript; reusable components; pages; templates/themes; plugin/extension architecture; asset management; preview; undo/redo; save/load; publish.
2-day rule | Zero-additional-cost rule: do NOT make Firebase Storage, Cloud Functions, paid email providers, paid visual-editor plugins, Clerk, PostgreSQL, Prisma, Liveblocks or Trigger.dev mandatory. Prefer Google Drive for files, Gmail API for MOM email, Firestore/Auth for application state, open-source libraries, and Google AI Studio/full-stack hosting options.
Cost target | ₹0 additional cost beyond the user's existing Google AI Pro subscription. Free/open-source components and existing Google services are preferred. This is an internal ~20-person system, so architecture should be sized for low traffic and low operational volume.
2-day rule | The full builder requirement is NOT reduced. Fit the deadline through mature editor integration, reuse of existing libraries, Google-managed services, and strict feature-unit execution.
Business application | Master website with Projects, Finance and HR, plus user/admin permissions and custom pages created through the full visual builder.
Authoritative source | AI-Ready App Building Playbook uploaded by user. It emphasizes architecture first, six context files + agents.md, feature specs, one-unit execution, verification, review, progress tracking and production verification.
Dates | Day 1: 20-Sep-2026. Day 2: 21-Sep-2026. Target production handover: 21-Sep-2026 21:00.
Important financial rule | The ₹5,000 allowance wording is preserved as a configurable policy. The implementation must support the requested calculation, but the exact accounting interpretation should be confirmed before production.
Definition of done | All P0 features work in production, full builder capabilities are usable, admin-only boundaries are server-enforced, file uploads persist, MOM email sends, salary/reimbursement calculations pass tests, and critical flows pass production smoke testing.

## 2-Day Checklist
2-DAY MASTER SEQUENCE CHECKLIST
ID | Date | Start | End | Phase | Feature / Unit | Exact Task | Dependency | P0/P1 | Google AI Studio Action | Verification / Done Condition | Owner | Status
D1-01 | 20-Sep-2026 | 08:00 | 08:30 | Architecture | Requirement freeze | Freeze full product scope: Projects, Finance, HR, permissions, file uploads, MOM email, salary/reimbursement, investments, AND full unrestricted visual website builder. | None | P0 | Create project-overview.md from the approved requirements; do not omit builder capabilities. | All requirements are represented as explicit features and acceptance criteria. | User/AI | Not Started
D1-02 | 20-Sep-2026 | 08:30 | 09:00 | Architecture | Builder architecture | Choose mature page-builder engine; recommended GrapesJS/equivalent. Define editor iframe/canvas, component tree, style manager, asset manager, pages, storage, commands, devices, plugins. | D1-01 | P0 | Create architecture-context.md and record the engine as a core dependency instead of generating a custom editor. | Architecture diagram and responsibility boundaries documented. | AI | Not Started
D1-03 | 20-Sep-2026 | 09:00 | 09:30 | Architecture | Backend architecture | Define zero-additional-cost architecture: Google AI Studio full-stack app; Firestore for structured data; Firebase Auth for identity; Google Drive for uploaded Excel/PDF/image files; Gmail API for MOM email; open-source XLSX/PDF libraries; free/open-source visual editor; free hosting/deployment option. | D1-01 | P0 | Document client/server boundaries, data ownership and environment variables. | Every data type has one authoritative owner; no mandatory component requires paid billing. | AI | Not Started
D1-04 | 20-Sep-2026 | 09:30 | 10:00 | Architecture | Roles & permissions | Define Admin and Standard User permissions; enforce at server/API mutation boundaries. | D1-03 | P0 | Write permission matrix and authorization invariants. | Unauthorized API calls fail even if UI is manually manipulated. | AI | Not Started
D1-05 | 20-Sep-2026 | 10:00 | 10:30 | Context | AI context system | Create agents.md plus project-overview.md, architecture-context.md, code-standards.md, ai-workflow-rules.md, ui-context.md, progress-tracker.md and feature-specs folder. | D1-01:D1-04 | P0 | Have Google AI Studio create/read these files before feature implementation. | Agent can resume project from files without relying on chat history. | AI | Not Started
D1-06 | 20-Sep-2026 | 10:30 | 11:00 | Foundation | Repository/app | Create clean React/Next.js TypeScript application, Git repo, environment structure, lint/type/build checks. | D1-05 | P0 | Prompt AI Studio to initialize only the foundation; no feature creep. | App starts, builds and commits cleanly. | AI | Not Started
D1-07 | 20-Sep-2026 | 11:00 | 11:30 | Foundation | UI system | Install/configure Tailwind/shadcn or equivalent, icons, tokens, reusable layout primitives, navigation and dialogs. | D1-06 | P0 | Implement UI foundation from ui-context.md. | No scattered styling; shell renders correctly. | AI | Not Started
D1-08 | 20-Sep-2026 | 11:30 | 12:00 | Auth | Authentication | Implement sign-in/sign-up/session handling and protected application routes. | D1-06,D1-04 | P0 | Use provider documentation/current SDK patterns; do not guess version-sensitive APIs. | Authenticated and unauthenticated flows pass. | AI | Not Started
D1-09 | 20-Sep-2026 | 12:00 | 12:30 | Database | Core schema | Create Users, Roles, Projects, ProjectMembers, Pages, PageVersions, Assets, Expenses, ExpenseAllocations, OOPClaims, Salaries, SalaryPayments, Investments, MOMs, Notes, AuditLogs. | D1-03,D1-08 | P0 | Generate schema/migrations and seed data from architecture context. | Relations, indexes and migrations succeed. | AI | Not Started
D1-10 | 20-Sep-2026 | 12:30 | 13:00 | Master Site | Application shell | Build master dashboard with Projects, Finance, HR and Custom Pages navigation; admin indicators; user profile. | D1-07:D1-09 | P0 | Implement only shell/navigation. | Navigation works and permissions affect visible routes. | AI | Not Started
D1-11 | 20-Sep-2026 | 13:00 | 13:45 | Projects | Project CRUD | Create/edit/delete projects, project access members, title, description, event date, links and status. | D1-09,D1-10 | P0 | Feature spec → plan → implement → verify. | CRUD works; membership enforced. | AI | Not Started
D1-12 | 20-Sep-2026 | 13:45 | 14:15 | Projects | Countdown | Display event date/time as live countdown on project page. | D1-11 | P0 | Implement isolated countdown component. | Countdown is accurate and handles expired events. | AI | Not Started
D1-13 | 20-Sep-2026 | 14:15 | 15:00 | Projects | Checklist Excel | Upload ready Excel, title it, store file, show downloadable/previewable representation on project page. | D1-09,D1-11 | P0 | Use storage service; keep file metadata in DB. | Upload, persistence, download/preview and authorization verified. | AI | Not Started
D1-14 | 20-Sep-2026 | 15:00 | 15:45 | Projects | Expense Excel | Upload ready Excel, title it, display it on project page, link it to structured expense/budget records. | D1-13 | P0 | Treat uploaded Excel as an artifact and structured records as calculation source. | File persists; project association correct. | AI | Not Started
D1-15 | 20-Sep-2026 | 15:45 | 16:30 | Finance | Budget & spending | Implement budget given-to-person records and employee spending records: amount, recipient/employee, purpose, date, project, attachment, status. | D1-09,D1-14 | P0 | Create server APIs with ownership checks. | Totals and records reconcile with uploaded/project data. | AI | Not Started
D1-16 | 20-Sep-2026 | 16:30 | 17:15 | HR | Employee records | Create employee directory: name, email, role, salary basis, active status, reimbursement settings. | D1-09,D1-08 | P0 | Admin mutation endpoints; limited user visibility. | Admin can manage; users see only permitted data. | AI | Not Started
D1-17 | 20-Sep-2026 | 17:15 | 18:00 | Finance | Salary foundation | Admin-only salary setup by employee/month; due amount; paid amount; pending carry-forward ledger. | D1-16 | P0 | Implement salary ledger rather than overwriting balances. | Admin-only mutation; carry-forward is auditable. | AI | Not Started
D1-18 | 20-Sep-2026 | 18:00 | 18:45 | Finance | Out-of-pocket claims | Employees create monthly OOP claims with date, purpose, amount, project, proof; claim status and approval flow. | D1-16,D1-17 | P0 | Separate claim lifecycle from salary calculation. | Employee can submit; admin can approve/reject. | AI | Not Started
D1-19 | 20-Sep-2026 | 18:45 | 19:30 | Visual Builder | Editor engine integration | Integrate mature visual editor: canvas iframe, drag/drop, component tree, selection, move, resize, delete, duplicate, undo/redo, HTML/CSS rendering. | D1-07,D1-06 | P0 | Install/configure engine; do not hand-code editor primitives. | Can drag, select, move, resize, duplicate and undo in browser. | AI | Not Started
D1-20 | 20-Sep-2026 | 19:30 | 20:00 | QA | Day 1 gate | Run build/lint/type checks; test auth, project CRUD, uploads, expense records, salary foundation, OOP and base editor. | D1-01:D1-19 | P0 | Use exact failures for focused corrective prompts. | All P0 Day-1 units pass or have documented blockers. | AI | Not Started
D2-01 | 21-Sep-2026 | 08:00 | 08:20 | Resume | Context restore | Read all context/spec/progress files and verify current branch/build before continuing. | D1-20 | P0 | No coding until context is restored. | AI Studio can state current phase, next unit and open questions. | AI | Not Started
D2-02 | 21-Sep-2026 | 08:20 | 09:00 | Finance | ₹5,000 allowance engine | Implement configurable monthly OOP allowance policy. Requested rule: if eligible expenses cross ₹5,000, excess is reimbursed with salary and ₹5,000 extra is included per stated requirement. | D1-18 | P0 | Make formula explicit/configurable; do not silently reinterpret wording. | Automated unit tests cover below/equal/above ₹5,000. | AI | Not Started
D2-03 | 21-Sep-2026 | 09:00 | 09:45 | Finance | Salary + reimbursement payout | Approved OOP reimbursement flows into salary portal and total payout; salary due + reimbursement + applicable allowance/extra line items. | D2-02,D1-17 | P0 | Build calculation service separately from UI. | Salary statement matches ledger totals. | AI | Not Started
D2-04 | 21-Sep-2026 | 09:45 | 10:30 | Finance | Carry-forward | Monthly unpaid salary automatically carries to next due balance without losing original month. | D2-03 | P0 | Use immutable payment/ledger records. | Test unpaid and partially paid months. | AI | Not Started
D2-05 | 21-Sep-2026 | 10:30 | 11:00 | Finance | Salary report | Generate downloadable salary/reimbursement report with employee/month/paid/pending/claim details. | D2-03,D2-04 | P0 | Generate report from authoritative ledger. | Report totals equal portal totals. | AI | Not Started
D2-06 | 21-Sep-2026 | 11:00 | 11:30 | Finance | Investment details | Admin-only investment ledger: source/person, amount, taken date, expected return date, actual return date, status, notes. | D1-09,D1-04 | P0 | Server-enforce admin access. | Standard user cannot read/write investment data. | AI | Not Started
D2-07 | 21-Sep-2026 | 11:30 | 12:00 | Projects | MOM editor | Create/update MOM for project, participants/registered email IDs, version/history and published status. | D1-11,D1-09 | P0 | Persist MOM content and recipient list. | MOM saves and version/status is visible. | AI | Not Started
D2-08 | 21-Sep-2026 | 12:00 | 12:30 | Projects | MOM email | On MOM publish/update, send email to registered IDs. Use background/async job or managed email service; record send status. | D2-07 | P0 | Keep email side effect behind explicit server boundary. | Email send success/failure is logged and retryable. | AI | Not Started
D2-09 | 21-Sep-2026 | 12:30 | 12:50 | Projects | Notes | General project notes with edit/history and permission control. | D1-11 | P0 | Implement simple persistent notes. | Notes survive refresh and respect access. | AI | Not Started
D2-10 | 21-Sep-2026 | 12:50 | 14:20 | Visual Builder | Full layout editor | Enable arbitrary nested containers, columns, rows, free placement where engine supports it, alignment, sizing, margins/padding, gaps, layers/tree and component nesting. | D1-19 | P0 | Configure editor capabilities; do not rebuild engine internals. | Create complex multi-column page and reload successfully. | AI | Not Started
D2-11 | 21-Sep-2026 | 14:20 | 15:00 | Visual Builder | Responsive design | Add device/breakpoint controls, desktop/tablet/mobile styles, visibility per breakpoint, responsive preview. | D2-10 | P0 | Configure device manager and style rules. | Same page renders correctly at all configured breakpoints. | AI | Not Started
D2-12 | 21-Sep-2026 | 15:00 | 15:40 | Visual Builder | Styling system | Typography, colors, backgrounds, borders, shadows, spacing, dimensions, positioning, flex/grid controls, reusable style classes. | D2-10 | P0 | Configure style manager and tokens. | Style changes persist and do not corrupt unrelated components. | AI | Not Started
D2-13 | 21-Sep-2026 | 15:40 | 16:10 | Visual Builder | Animations/interactions | Add transition/animation controls and event/action hooks; support reusable interactions where engine/plugin permits. | D2-12 | P0 | Use engine-native commands/plugins; isolate custom scripts. | Animation works in preview/published page. | AI | Not Started
D2-14 | 21-Sep-2026 | 16:10 | 16:40 | Visual Builder | Custom CSS | Provide page-level and component/class-level custom CSS editor with preview and persistence. | D2-12 | P0 | Store CSS separately from structured page JSON/HTML. | Custom CSS applies only to intended page/scope. | AI | Not Started
D2-15 | 21-Sep-2026 | 16:40 | 17:10 | Visual Builder | Custom JavaScript | Provide custom JS editor for advanced page behavior, with explicit admin permission and sandbox/isolated execution boundary. | D2-13,D2-14 | P0 | Do not execute arbitrary admin/user JS in the main application origin. Use iframe sandbox/isolated published runtime and explicit warnings. | Script works in preview/published sandbox; app shell remains protected. | AI | Not Started
D2-16 | 21-Sep-2026 | 17:10 | 17:40 | Visual Builder | Themes/templates | Create reusable themes/templates, global styles, duplicate page, save as template, apply template to page. | D2-12 | P0 | Build on editor's component/style storage. | Template creates independent editable page. | AI | Not Started
D2-17 | 21-Sep-2026 | 17:40 | 18:00 | Visual Builder | Plugins/extensions | Create plugin/extension registration boundary and load at least one test extension. Document extension API and versioning approach. | D2-10:D2-16 | P0 | Use editor's plugin API rather than a custom plugin runtime. | Plugin can add a component/control without changing core editor. | AI | Not Started
D2-18 | 21-Sep-2026 | 18:00 | 18:20 | Visual Builder | Pages/assets/publish | Multiple pages per site/project, asset upload/manager, page settings, preview, save/load, publish/unpublish, version snapshot. | D2-16,D2-17 | P0 | Persist editor JSON/HTML/CSS/JS/assets with version metadata. | Create 2 pages, reload, publish, preview and unpublish. | AI | Not Started
D2-19 | 21-Sep-2026 | 18:20 | 18:50 | CMS | Flexible access | Anyone with project/site access can edit permitted pages; admins control protected pages, finance, salary and investments; custom page creation/edit rights configurable. | D1-04,D2-18 | P0 | Enforce permissions server-side and in editor load/save/publish APIs. | Test each role by direct API request and UI. | AI | Not Started
D2-20 | 21-Sep-2026 | 18:50 | 19:20 | Security | Security audit | Audit authentication, authorization, file access, custom JS isolation, XSS, CSRF, injection, storage rules, admin endpoints, secrets and published-page boundaries. | D2-15,D2-19 | P0 | Use focused corrective prompts for every finding. | No critical auth/storage/script-isolation issue remains. | AI | Not Started
D2-21 | 21-Sep-2026 | 19:20 | 19:50 | QA | End-to-end QA | Test: login → project → countdown → Excel upload → expense → OOP → salary → report → MOM email → custom page → publish → responsive preview. | D2-20 | P0 | Use an explicit acceptance checklist; capture exact failures. | All critical user journeys pass. | AI | Not Started
D2-22 | 21-Sep-2026 | 19:50 | 20:15 | QA | Financial test suite | Test allowance threshold, excess reimbursement, carry-forward, partial payment, duplicate claim prevention and report reconciliation. | D2-21 | P0 | Run automated and manual tests. | All expected totals reconcile. | AI | Not Started
D2-23 | 21-Sep-2026 | 20:15 | 20:35 | Review | Code review | Review AI-generated code, dependency changes, editor integration, authorization and business calculations; fix findings only. | D2-21,D2-22 | P0 | Review against feature specs and context; no unrelated refactor. | Review findings resolved/documented. | AI | Not Started
D2-24 | 21-Sep-2026 | 20:35 | 20:50 | Production | Deploy | Configure production environment, secrets, auth, DB, storage, email, published-site runtime and hosting; deploy. | D2-23 | P0 | Follow current provider docs; inspect build/deploy logs. | Production build succeeds and logs are clean for critical paths. | AI | Not Started
D2-25 | 21-Sep-2026 | 20:50 | 21:00 | Closeout | Production smoke + handover | Run final production smoke test, update progress tracker, document URLs/credentials setup, known issues and next improvements. | D2-24 | P0 | Mark only verified features complete. | Production critical flows pass; tracker and documentation match implementation. | User/AI | Not Started
D2-20 | 21-Sep-2026 | 20:45 | 21:00 | Closeout | Zero-cost verification | Verify that the production configuration does not require Firebase Blaze, paid storage, paid email, paid editor plugins, or any other new subscription/billing commitment. Verify all selected Google services remain within the intended no-cost or existing-subscription usage model. | D2-19 | P0 | Ask Google AI Studio to inspect environment/configuration and list any service that would require billing. | No unexpected paid dependency; cost architecture documented. | User/AI | Not Started

## Requirements Mapping
FULL REQUIREMENTS → IMPLEMENTATION MAPPING
ID | User Requirement | Implementation | Data/Service | Access | Acceptance Test | Priority | Checklist IDs
R01 | Master website: Projects / Finance / HR | Master shell + protected modules | Firestore + Firebase Auth | All | Each module opens and respects role | P0 | D1-10
R02 | Create/edit projects | Project CRUD + members | DB | Configurable | Admin/user with access can create/edit as configured | P0 | D1-11
R03 | Event date countdown | Live countdown component | Project DB | Project access | Correct time remaining + expired state | P0 | D1-12
R04 | Upload ready checklist Excel and reflect on site | File upload + metadata + preview/download | Google Drive + Firestore | Project access | Upload persists and appears in project | P0 | D1-13
R05 | Upload ready expense Excel and reflect on site | File upload + structured expense ledger | Google Drive + Firestore | Project access | File visible + records calculate | P0 | D1-14,D1-15
R06 | Budget given to whom + employee spending purpose/date | Allocation and expense records | DB | Project access; approvals configurable | Budget vs spent totals reconcile | P0 | D1-15
R07 | MOM automatically emailed after update | MOM editor + async email job | DB + email service | Project access | Registered IDs receive update; send logged | P0 | D2-07,D2-08
R08 | OOP monthly reimbursement | Claim workflow + approval | DB | Employee own; admin approval | Claim flows into salary payout | P0 | D1-18,D2-03
R09 | General notes | Persistent notes | DB | Page/project access | Edit and reload | P0 | D2-09
R10 | Admin-only salary sheet | Salary ledger | DB | Admin only | Direct unauthorized API blocked | P0 | D1-17
R11 | Monthly due salary + carry-forward | Salary payment ledger | DB | Admin | Pending carries without data loss | P0 | D2-04
R12 | Generate salary report | Report generator | Server/report library | Admin | Report totals match ledger | P0 | D2-05
R13 | ₹5,000 OOP rule | Configurable calculation engine | DB/service | Admin config + employee claims | Below/equal/above threshold tests pass | P0 | D2-02,D2-03
R14 | Admin-only investment details | Investment ledger | DB | Admin only | Standard user cannot read/write | P0 | D2-06
R15 | Anyone with access can edit | Permission-aware editor | Auth + page ACL | Per page/site | Allowed user can edit and save | P0 | D2-19
R16 | Admin-controlled pages | Protected pages + server rules | Auth + ACL | Admin | Non-admin blocked | P0 | D2-19,D2-20
R17 | Create new website sheet/page | Full multi-page builder | Editor engine + DB | Configurable | Create/delete/duplicate/publish pages | P0 | D2-18
R18 | Drag anything anywhere | Visual editor canvas | Editor engine | Editor access | Drag/drop/reposition elements | P0 | D1-19,D2-10
R19 | Resize elements | Canvas/style manager | Editor engine | Editor access | Resize selected components | P0 | D1-19,D2-10
R20 | Arbitrary columns/layouts | Nested containers + flex/grid | Editor engine | Editor access | Create complex multi-column layout | P0 | D2-10
R21 | Animations | Animation/interaction controls | Editor engine/plugin | Editor access | Preview animation | P0 | D2-13
R22 | Custom CSS | Scoped page/component CSS | DB + editor | Configurable; admin for sensitive pages | CSS persists and renders | P0 | D2-14
R23 | Custom JavaScript | Isolated page script runtime | Sandboxed iframe/published runtime | Admin or explicit role | JS runs without compromising app shell | P0 | D2-15
R24 | Themes | Global styles + templates | Editor + DB | Admin/configurable | Apply theme to new page | P0 | D2-16
R25 | Plugins | Plugin registration boundary | Editor plugin API | Admin | Test plugin loads | P0 | D2-17
R26 | Responsive breakpoint editor | Device manager | Editor engine | Editor access | Desktop/tablet/mobile settings persist | P0 | D2-11
R27 | Fully customizable pages | Pages/assets/components/styles/scripts/publish | Editor + storage | ACL | Build a nontrivial custom page end-to-end | P0 | D2-10:D2-18

## Required Tools
REQUIRED TOOLS — GOOGLE AI STUDIO IMPLEMENTATION
Tool / Service | Role in this app | Required? | Recommended choice | Cost model for this project | Why / Boundary | Fallback | Configured
Google AI Studio | Primary AI-assisted app builder/coding environment | Yes | Google AI Studio + existing Google AI Pro | Existing subscription / target ₹0 additional | Primary implementation environment. Use persistent repo context, specs and verification. | Other AI coding agent
Google AI Pro | Existing user subscription | Already available | User's existing plan | Already paid by user; no new purchase | Provides expanded Google AI access/storage benefits relevant to the workflow. | N/A
Git + GitHub | Version control and recovery | Yes | Git + GitHub Free | ₹0 | Keep development history, branches and rollback points. | GitLab/Bitbucket free tier
React + TypeScript | Application UI/runtime | Yes | React + TypeScript | ₹0 / open source | Application and editor integration layer. | Equivalent frontend
GrapesJS or equivalent | Full visual website builder | Yes | GrapesJS open-source core | ₹0 / open source | Provides the editor foundation; do not hand-build the editor engine from zero. | Other open-source page-builder engine
Tailwind CSS | Styling | Recommended | Tailwind CSS | ₹0 / open source | Fast application UI styling. | Plain CSS
shadcn/ui | Reusable application UI components | Recommended | shadcn/ui | ₹0 / open source | Dashboard/forms/dialogs/tables. | Equivalent open-source UI library
Firebase Authentication | User identity and login | Yes | Firebase Auth | ₹0 target for ~20 users | Internal company user authentication; avoid unnecessary paid authentication methods. | Google OAuth directly
Firestore | Structured application database | Yes | Firestore | ₹0 target for ~20 users / low volume | Projects, employees, expenses, salary, permissions, pages and metadata. | Other free Google-backed database option
Google Drive | Uploaded Excel/PDF/image/file storage | Yes | Google Drive API | Use existing Google storage; no new storage subscription | Avoid Firebase Storage so the app does not require Blaze just for file storage. | Local/deployment storage only for temporary artifacts
Gmail API | MOM email delivery | Yes | Gmail API | ₹0 target for low internal volume | Send updated MOM to registered project recipients; no Resend/SendGrid required initially. | Manual email fallback
XLSX / ExcelJS | Excel read/write/reporting | Yes | Open-source npm library | ₹0 / open source | Read existing Excel files and generate/update reports where needed. | CSV parser
PDF library | PDF report generation | If required | pdf-lib / jsPDF or equivalent | ₹0 / open source | Generate downloadable reports without paid reporting SaaS. | HTML print/PDF
Hosting / deployment | Serve the application | Yes | Google AI Studio supported deployment / Firebase Hosting free option | ₹0 target; stay within no-cost limits | Select a deployment route that does not require paid billing for this internal app. | Other free hosting
Paid visual-editor plugins | Optional editor extensions | No | Open-source/custom extensions only | ₹0 | Do not introduce paid plugins into the mandatory architecture. | Build required extension with open source APIs
Firebase Storage | Binary file storage | No | Do not use as mandatory storage | Avoid billing dependency | Use Google Drive instead so Firebase Storage/Blaze is not required. | Google Drive
Cloud Functions | Serverless backend functions | No | Do not make mandatory | Avoid billing dependency | Use the application's supported server-side runtime/backend instead. | Google AI Studio full-stack server runtime
Resend / SendGrid / Mailgun | Third-party transactional email | No | Do not use initially | ₹0 | Gmail API is sufficient for the low-volume internal MOM workflow. | Gmail API
Clerk | Third-party authentication | No | Do not use | ₹0 | Firebase Auth is sufficient for ~20 internal users. | Firebase Auth
PostgreSQL + Prisma | Alternative relational DB stack | No | Do not use unless a concrete need appears | ₹0 by avoiding it | Firestore is simpler for the 2-day internal application. | Firestore
Liveblocks | Real-time collaboration | No | Do not use for MVP | ₹0 | The requirement is multi-user access/editing, not simultaneous cursor-level collaborative editing. | Firestore updates
Trigger.dev | Background jobs | No | Do not use for MVP | ₹0 | MOM/report tasks can remain within the chosen backend/runtime for this low-volume system. | Server-side async operations

## Permissions Matrix
PERMISSIONS & SECURITY MATRIX
Capability | Admin | Standard User with Access | Employee Self | Server Enforcement | Sensitive Data | Test
Dashboard | Read/write | Read/write permitted modules | Read own | Yes | No | Try direct API
Create project | Yes | Configurable | No | Yes | No | Role/API test
Edit project | Yes | Yes if member/editor | No | Yes | No | Member test
Delete project | Yes | Configurable | No | Yes | No | Unauthorized delete
Event date | Yes | Yes if editor | No | Yes | No | Edit/reload
Checklist Excel | Yes | Yes if editor | No | Yes | Potential | Storage rules
Expense Excel | Yes | Yes if editor | No | Yes | Potential | Storage rules
Budget allocations | Yes | Yes if permitted | No | Yes | Financial | Role test
Own OOP claim | Yes | Yes | Yes | Yes | Financial | Employee sees own
Other employee OOP | Yes | Configurable/no by default | No | Yes | Financial | Cross-user access
Salary | Yes | No | No | Yes | Highly sensitive | Direct API denial
Salary report | Yes | No | No | Yes | Highly sensitive | Direct API denial
Investments | Yes | No | No | Yes | Sensitive | Direct API denial
MOM | Yes | Yes if editor | No | Yes | Business | Email recipient test
Custom page create | Yes | Configurable | No | Yes | No | ACL test
Custom page edit | Yes | Yes if page ACL | No | Yes | No | ACL test
Custom CSS | Yes | Configurable | No | Yes | Potential | Scope test
Custom JS | Yes | Admin/default restricted | No | Yes | Critical | Sandbox escape test
Themes/templates | Yes | Configurable | No | Yes | No | Apply/rollback
Plugins | Yes | Admin | No | Yes | Critical | Plugin isolation
Publish | Yes | Configurable | No | Yes | Critical | Draft vs published
Uploaded files / Drive assets | Yes | Yes if permitted | Own/assigned files only | Yes | Potentially sensitive | Verify direct Drive/app access

## Open Questions
OPEN QUESTIONS / DECISIONS TO CONFIRM BEFORE PRODUCTION
ID | Question | Default for 2-Day Build | Why It Matters | Decision Needed By | Impact | Status
Q01 | Which visual editor engine will be used? | GrapesJS or equivalent mature editor | This is the key mechanism that makes the full builder achievable in 2 days. | 20-Sep 09:00 | High | Open
Q02 | Should standard users be able to create projects? | Configurable permission; admin can enable | Requirement says anyone with access can edit, but project creation is not explicitly restricted. | 20-Sep 09:00 | Medium | Open
Q03 | Who receives MOM emails? | Registered project participant emails | Need authoritative recipient source. | 21-Sep 11:30 | Medium | Open
Q04 | Should uploaded Excel be parsed into editable web tables? | File is displayed/downloaded; structured expense records are separately editable | Avoid corrupting authoritative Excel while still enabling calculations. | 20-Sep 15:00 | High | Open
Q05 | Exact ₹5,000 interpretation? | Configurable: threshold + requested extra ₹5,000 line item | Wording can produce different accounting outcomes. | 21-Sep 08:20 | High | Open
Q06 | Who can run custom JavaScript? | Admin only by default | Arbitrary JS is a major security boundary. | 21-Sep 15:00 | Critical | Open
Q07 | Should plugins be arbitrary third-party code? | Plugin registration API, admin-controlled; no untrusted third-party runtime | Security and production stability. | 21-Sep 17:10 | Critical | Open
Q08 | Published custom pages run on same domain or separate route/subdomain? | Same app domain with isolated page runtime | Determines routing and script isolation design. | 21-Sep 18:00 | High | Open
Q07 | Must the app remain at ₹0 additional cost beyond the existing Google AI Pro subscription? | Yes — hard constraint for this build | Determines storage, email, hosting and backend choices. | 20-Sep 10:00 | High | Resolved

## Feature Specs
FEATURE-UNIT MAP — SPEC-DRIVEN EXECUTION
Feature ID | Feature | Goal | Dependencies | Implementation Boundary | Explicit Out of Scope for Unit | Verification | Checklist
F01 | Context + Architecture | Create durable product/architecture context | None | Context files, architecture, permissions, storage, editor decision | No feature implementation | All context files exist and agree | D1-01:D1-05
F02 | Foundation | Create clean app and UI shell | F01 | React/TS, UI system, auth-ready shell, env | Business features | Build/lint/type pass | D1-06:D1-08
F03 | Core Data | Persist core entities | F01,F02 | Schema/migrations/API boundaries | UI polish | CRUD + relation tests | D1-09
F04 | Master Dashboard | Navigate Projects/Finance/HR/Custom Pages | F02,F03 | Shell and navigation | Deep module logic | Routes work and roles apply | D1-10
F05 | Projects | Manage projects/members/event data | F03,F04 | Project APIs + UI | Finance/MOM | CRUD + membership tests | D1-11:D1-12
F06 | Project Files | Checklist/expense Excel uploads | F03,F05 | Storage + metadata + project links | Full spreadsheet editor | Upload/reload/access test | D1-13:D1-14
F07 | Expense Ledger | Budget allocations + employee spending | F03,F06 | Structured records/calculations | Salary payout | Reconciliation tests | D1-15
F08 | HR | Employee directory | F03,F04 | Employee APIs/UI | Performance/payroll automation | Access tests | D1-16
F09 | Salary | Admin salary ledger | F07,F08 | Monthly ledger + carry-forward | Bank transfer integration | Ledger tests | D1-17,D2-04
F10 | OOP | Employee reimbursement workflow | F07,F08 | Claims/approval/status | Automatic bank payment | Approval and payout tests | D1-18,D2-02:D2-03
F11 | Reports | Generate salary reports | F09,F10 | Server report generation | BI dashboard | Totals reconcile | D2-05
F12 | Investments | Admin investment ledger | F03 | CRUD + audit | Investment recommendations | Direct API denial for users | D2-06
F13 | MOM | MOM editor + notification | F05,F03 | Content + recipients + async send | Full email campaign system | Email/send-log test | D2-07:D2-08
F14 | Notes | Project notes | F05 | Persistent text records | Rich collaborative editor | Reload/access test | D2-09
F15 | Visual Editor Core | Integrate mature full page builder | F02,F03 | Canvas, components, selection, drag, resize, history | No custom editor internals | Build nontrivial page | D1-19
F16 | Visual Layout | Nested containers/columns/responsive | F15 | Layout + devices | 3D/WebGL editor | Desktop/tablet/mobile tests | D2-10:D2-11
F17 | Visual Styling | Style manager + custom CSS | F15,F16 | Style rules/tokens/CSS | Server-side CSS compilation | CSS persistence/render test | D2-12,D2-14
F18 | Visual Behavior | Animations + custom JS | F15,F17 | Interaction controls + isolated runtime | Untrusted script execution in app origin | Sandbox test | D2-13:D2-15
F19 | Themes/Plugins | Templates, themes, plugin API | F15:F18 | Reusable config + extension boundary | Unreviewed arbitrary third-party plugins | Load/apply test | D2-16:D2-17
F20 | Pages/Publishing | Multi-page storage, assets, preview, publish | F15:F19 | Page versions + assets + publish | Full CDN/page analytics | Publish/reload/rollback test | D2-18
F21 | Access-aware CMS | Editor permissions by page/project | F04,F15,F20 | ACL on load/save/publish | Enterprise SSO provisioning | Direct API security tests | D2-19
F22 | Security | Full application security audit | All | Auth/storage/XSS/script/ACL audit | Pen test beyond 2-day scope | No critical findings | D2-20
F23 | Production | Deploy and verify | All | Production services/env/logs/smoke test | Long-term operations | Critical journeys pass | D2-24:D2-25

## Timeline Summary
2-DAY TIMELINE SUMMARY
Time | Day 1 — 20 Sep | Time | Day 2 — 21 Sep | Critical Gate | Dependency Strategy | Status
08:00–10:30 | Architecture + context + full-builder engine decision | 08:00–09:45 | Resume + allowance + salary integration | Scope/context + backend boundaries | No implementation before context
10:30–13:00 | Foundation + auth + DB + master shell | 09:45–11:30 | Carry-forward + reports + investments | Core business data | Use managed services
13:00–16:30 | Projects + Excel uploads + expense ledger | 11:30–12:50 | MOM + email + notes | Project workflows | Feature-unit execution
16:30–19:30 | HR + salary + OOP + visual editor core | 12:50–15:00 | Full layout + responsive + styling | Full builder becomes usable | Mature editor integration
19:30–20:00 | Day 1 QA gate | 15:00–18:20 | Animations + CSS + JS + themes + plugins + publishing | Builder feature completeness | Configure engine/plugin APIs
— | — | 18:20–19:50 | ACL + security + E2E + financial QA | Production readiness | Focused corrections only
— | — | 19:50–21:00 | Review + deploy + production smoke + handover | Definition of done | No unverified completion
COST GATE | ₹0 additional-cost target: Google AI Pro already available; Drive for files; Gmail API for MOM; Firestore/Auth for app data; open-source editor/libraries; no mandatory Blaze/paid SaaS. | Final gate | 21-Sep-2026 20:45–21:00 | No unexpected billing dependency

## Full Builder Matrix
FULL WEBSITE BUILDER — CAPABILITY CHECKLIST
Capability | Required | Engine Responsibility | Our Integration | Security / Persistence | Acceptance Test | Day/Task | Status
Drag & drop components | Yes | Editor canvas/component system | Configure component palette | Persist component tree | Drag text/image/button/container and save | D1-19 | Not Started
Move/reposition | Yes | Canvas selection/commands | Configure commands | Persist positions | Move component and reload | D1-19 | Not Started
Resize | Yes | Canvas/style manager | Configure dimensions/handles | Persist width/height | Resize desktop/mobile independently | D1-19,D2-10 | Not Started
Arbitrary columns | Yes | Nested containers/layout system | Configure flex/grid/containers | Persist hierarchy | Build 3-column + nested layout | D2-10 | Not Started
Free-form placement where supported | Yes | Editor positioning | Enable absolute/relative positioning modes | Validate page scope | Place element independently without breaking others | D2-10 | Not Started
Layers/component tree | Yes | Editor layer manager | Expose tree panel | Persist hierarchy | Select nested element from tree | D2-10 | Not Started
Undo/redo | Yes | Editor command/history system | Configure history | Version snapshot | Undo/redo multiple changes | D1-19 | Not Started
Typography | Yes | Style manager | Expose font/size/weight/line height | Persist style rules | Style heading/text | D2-12 | Not Started
Colors/backgrounds | Yes | Style manager | Expose controls | Persist | Change background/color | D2-12 | Not Started
Spacing | Yes | Style manager | Margin/padding/gap controls | Persist | Change spacing | D2-12 | Not Started
Flex/grid | Yes | Style manager | Expose layout properties | Persist | Responsive flex/grid test | D2-10,D2-12 | Not Started
Responsive breakpoints | Yes | Device manager | Desktop/tablet/mobile + custom breakpoints | Persist per device | Different mobile layout | D2-11 | Not Started
Animations | Yes | Commands/plugins/CSS | Configure animation controls | Persist animation definition | Preview animation | D2-13 | Not Started
Interactions/events | Yes | Commands/components | Configure click/hover actions | Persist event config | Button interaction test | D2-13 | Not Started
Custom CSS | Yes | CSS/style system | Page + component CSS editor | Scoped/persisted | Custom CSS changes page | D2-14 | Not Started
Custom JavaScript | Yes | Script/component/plugin boundary | Admin-controlled script editor + sandbox | Isolated runtime | Script executes in preview/published page | D2-15 | Not Started
Themes | Yes | Global style/template system | Theme selector + tokens | Persist theme version | Apply theme to page | D2-16 | Not Started
Templates | Yes | Page/component storage | Save as template/duplicate | Versioned | Create page from template | D2-16 | Not Started
Plugins/extensions | Yes | Editor plugin API | Registration + admin controls | Version/allowlist | Load test extension | D2-17 | Not Started
Pages | Yes | Page manager | Create/rename/delete/duplicate | DB persistence | Create 2 pages | D2-18 | Not Started
Assets | Yes | Asset manager | Upload images/files | Object storage + ACL | Upload and reuse asset | D2-18 | Not Started
Preview | Yes | Editor runtime | Preview route | No edit controls | Preview matches published | D2-18 | Not Started
Publish/unpublish | Yes | Page storage/runtime | Draft/published state | Versioned | Publish then unpublish | D2-18 | Not Started
Version snapshots | Yes | Storage/version layer | Save page versions | Immutable snapshot | Restore prior version | D2-18 | Not Started
Permissions | Yes | App API/auth layer | Page/site ACL | Server enforced | Direct API denial | D2-19 | Not Started
BUILDER COST RULE | Use the open-source editor core and open-source/custom extensions. No paid visual-editor plugin is mandatory. The builder must remain fully customizable: drag/drop, arbitrary layouts, resize, responsive breakpoints, animations, custom CSS/JS, themes, templates, plugins/extensions, pages and publishing.

## AI Studio Prompt Sequence
GOOGLE AI STUDIO — EXECUTION PROMPT SEQUENCE
Prompt # | When to use | Prompt objective | Required input/context | Expected AI Studio behavior | Done condition
P01 | Start of project | Create architecture and context before coding | User requirements + playbook | Produce project-overview, architecture-context, code-standards, ai-workflow-rules, ui-context, progress-tracker, agents.md | Files created and internally consistent
P02 | Before foundation | Initialize clean application | P01 files | Create app, env, lint/type/build, Git; no feature implementation | Clean build
P03 | Before each feature | Implement one feature unit | Relevant context + feature spec | Plan first, implement exact scope, verify, update tracker | Feature verification passes
P04 | When builder starts | Integrate mature visual editor | F01/F02 + builder matrix | Install/configure editor engine; do not recreate editor internals | Core drag/select/move/resize works
P05 | When a defect appears | Focused correction | Exact error + affected feature spec | Inspect boundary/docs, make smallest root fix, rerun tests | Defect fixed, no unrelated changes
P06 | Security pass | Audit custom JS and authorization | Permissions + builder runtime design | Test direct API calls, storage access, script isolation and XSS boundaries | No critical security issue
P07 | Production | Deploy and verify | Production env config | Build, deploy, inspect logs, smoke test | Production critical flows pass
P06 | Before backend/storage setup | Enforce zero-additional-cost architecture | Read Required Tools + architecture context + 20-user scale | Use Firestore/Auth, Google Drive, Gmail API, open-source libraries and a no-billing deployment route where supported. Do not introduce Firebase Storage, Cloud Functions, paid email, paid editor plugins or other paid SaaS without explicit approval. | Dependency scan and configuration show no mandatory paid service.

## Playbook Alignment
ALIGNMENT WITH UPLOADED APP-BUILDING PLAYBOOK
Playbook Principle | How this workbook applies it | Where | Why it matters for 2-day build | Status
Architecture before coding | Architecture, builder-engine choice, data ownership, security boundaries are first tasks. | D1-01:D1-04 | Prevents Google AI Studio from improvising the system. | Applied
Six-file context + agents.md | Created before implementation and restored on Day 2. | D1-05,D2-01 | Lets AI Studio resume without rediscovering requirements. | Applied
Feature specs | Business modules and builder capabilities are decomposed into units. | Feature Specs | Controls AI scope and reduces debugging loops. | Applied
One unit at a time | Each checklist item has dependency, exact action and verification. | 2-Day Checklist | Allows parallel-looking speed without architectural drift. | Applied
Provider-native capabilities | Full builder uses mature editor engine rather than custom canvas implementation. | D1-19,D2-10:D2-18 | This is the main mechanism for fitting full builder into 2 days. | Applied
Server-side authorization | Permissions are enforced at mutation/API boundaries. | Permissions Matrix,D2-19:D2-20 | UI-only hiding is insufficient. | Applied
Focused corrections | Exact errors become corrective prompts rather than full-project re-prompts. | AI Studio Prompt Sequence | Reduces regression and wasted time. | Applied
Review before completion | AI-generated code is reviewed before merge/deploy. | D2-23 | Catches spec/security mismatches. | Applied
Production verification | Deploy, inspect logs and test critical flows. | D2-24:D2-25 | Prevents assuming a successful build is a successful product. | Applied
Cost-aware architecture | Architecture assigns each responsibility to an existing/free/open-source service appropriate for a ~20-person internal system. | Read Me; Required Tools; architecture tasks | Prevents unnecessary infrastructure and keeps the 2-day build aligned with the user's ₹0 additional-cost constraint. | Applied