## START HERE
Purpose | Final autonomous phase: take the verified Phase 9 application to production, run production smoke tests, verify the ₹0 additional-cost constraint, complete handover, and close the 2-day build.
Authoritative source | Master_Website_2_Day_App_Build_Checklist_ZERO_ADDITIONAL_COST_Google_AI_Studio.xlsx, especially D2-24 Deploy, D2-25 Production smoke + handover, Required Tools, Open Questions, Read Me, Timeline Summary and AI Studio Prompt Sequence.
Phase | Phase 10 — Production deployment, final verification & handover
Target window | Day 2 — 21-Sep-2026 20:35–21:00
Scope | D2-24 + D2-25 + zero-cost verification gate. No new feature development unless required to fix a production-blocking defect discovered during deployment/smoke testing.
Autonomy model | AI reads this workbook and the complete project context → inspects current repository → plans each unit → executes → verifies → stops only at a Human Gate → tells the user exactly what action is required → waits for DONE — RESUME PHASE 10 → re-verifies the gate → resumes from the exact blocked unit.
Hard cost invariant | ₹0 additional cost beyond the user's existing Google AI Pro subscription. Do not silently enable billing, Blaze, paid storage, paid email, paid editor plugins, or any new subscription.
Critical safety rule | Never request or expose passwords, private keys, OAuth client secrets, API keys, service-account keys, tokens or other credentials in chat. Use the platform's secure environment/secret configuration mechanisms and ask the human only to perform the required secure action.
No invention rule | Do not invent a production provider, domain, DNS setup, billing plan, database migration, storage model, email provider, or hosting route if it was not selected by earlier phases. Inspect architecture-context.md, decision register and actual repository first.
Completion | Phase 10 is complete only when production deployment succeeds, production critical flows pass, zero-cost verification passes, handover artifacts are updated, known issues are documented, Git state is recorded, and no required human gate remains unresolved.
Resume command | DONE — RESUME PHASE 10
Final state | There is no Phase 11. After successful closeout, stop and provide the final handover summary.

## Autonomous Control
Control | Instruction | AI behavior | Stop condition
Control | Instruction | AI behavior | Stop condition
Read before act | Read this entire workbook plus all available Phase 1–9 context/spec/progress files and inspect the current repository/branch/build. | Do not begin deployment from assumptions. | Required predecessor context is missing or contradictory.
Restore state | Read progress-tracker.md, decision register, correction log, Git status/log and Phase 9 handoff. | Determine the exact last verified state and remaining production tasks. | State cannot be established safely.
Plan each unit | Before each unit, produce an internal execution plan tied to acceptance criteria. | Implement only the current unit and its dependencies. | A dependency is missing or requires human action.
Production changes | Use the architecture already approved. Make the smallest safe production configuration changes. | Do not redesign the application during deployment. | Production architecture is materially unresolved.
Credentials | Never ask the user to paste secrets into chat. | Use secure env/secret configuration UI or documented secure provider flow. | Credential/OAuth/secret action requires user.
Cost gate | Inspect actual selected services, project billing state, package dependencies and deployment settings. | If any required step would create a new charge, STOP before enabling it. | Billing or paid dependency is required/unclear.
Verification | After each production action, verify logs, build output, route availability, auth and critical data paths. | Do not claim success from a command completing alone. | Verification fails.
Correction loop | Reproduce → identify root cause → smallest safe fix → targeted retest → regression test → update tracker. | No unrelated refactor. | Fix would expand scope or create new risk.
Human gate | Explain exactly what the user must do, where, why, and what confirmation is needed. | Pause execution; preserve state. | Any essential human action is required.
Resume | When user sends DONE — RESUME PHASE 10, re-check the gate and continue from the exact blocked point. | Do not restart completed work. | Gate remains incomplete.
Closeout | Update progress, decisions, context, known issues and handover information. | Stop after final handover; do not start new features. | All completion criteria satisfied.

## Phase 10 Units
ID | Unit | Scope | Acceptance evidence | Owner | Done condition | Human gate | Maps to
P10-01 | Restore Phase 9 state | Read Phase 9 completion/handoff, context files, progress tracker, decision register, correction log; inspect Git status and current branch. | Phase 9 completed; no unresolved P0 security/ACL/QA/code-review blocker. | AI | Phase 9 evidence + repo inspected | Block if predecessor incomplete. | D2-24
P10-02 | Production readiness audit | Compare actual repo/config against production requirements: auth, Firestore, Drive, Gmail, published-page runtime, hosting, env variables, migrations, build command and routes. | Production readiness checklist and exact missing items. | AI | Readiness matrix complete | STOP if architecture/provider is unresolved. | D2-24
P10-03 | Secure production configuration | Configure production environment using secure secret/config mechanisms. Never expose secret values in chat. Configure only approved services. | Environment names/locations documented, values secured, no secrets committed. | Human + AI | Secure configuration verified | STOP for OAuth consent, secret entry, billing, DNS/domain or provider action. | D2-24
P10-04 | Production database/storage/email readiness | Verify Firestore/Auth, Google Drive file access, Gmail API/MOM delivery path and published-page persistence/runtime using the approved architecture. | Connectivity and permission checks pass. | AI | Read/write tests pass without unauthorized access. | STOP for missing OAuth/permission/credential action. | D2-24
P10-05 | Build and production deploy | Run type/lint/test/build, create production artifact, deploy using the already selected no-cost-supported route, inspect deployment logs. | Production deployment succeeds and application is reachable. | AI | Clean deployment evidence. | STOP on billing prompt, failed build/deploy, or provider approval. | D2-24
P10-06 | Zero-cost verification | Verify no mandatory Firebase Blaze billing, paid storage, paid email, paid editor plugins, new SaaS, or other subscription was introduced. Check actual configuration rather than assumptions. | Cost gate evidence recorded. | AI | All mandatory dependencies satisfy ₹0 target. | STOP immediately if charge/billing is required or unclear. | D2-25
P10-07 | Production smoke: identity + dashboard | Test login, role loading, master dashboard, navigation and protected sections. | Expected roles/routes load successfully. | AI | Smoke checks pass. | STOP on auth/ACL failure. | D2-25
P10-08 | Production smoke: Projects | Test project create/edit according to configured policy, countdown, checklist/expense Excel artifact access, structured expense records, budget/spending and notes. | Critical Projects journey passes. | AI | Production data behavior verified. | STOP on data-loss/access/permission defect. | D2-25
P10-09 | Production smoke: Finance/HR | Test employee access, admin-only salary, OOP claim, allowance calculation as configured, approval/payout, carry-forward, report and admin-only investments. | Financial critical journey passes and totals reconcile. | AI | No discrepancy or unauthorized access. | STOP on financial mismatch/security defect. | D2-25
P10-10 | Production smoke: MOM + email | Publish/update MOM and verify send status and recipient behavior according to resolved configuration. Do not spam recipients during testing. | MOM workflow and email path pass. | AI | One controlled production test succeeds. | STOP on OAuth/email configuration or recipient-policy ambiguity. | D2-25
P10-11 | Production smoke: Builder | Open custom page, edit/save/load, responsive preview, CSS/JS isolation, themes/templates, plugin boundary, assets, publish/unpublish and version snapshot. | Builder production journey passes without main-app compromise. | AI | Critical builder capabilities pass. | STOP on script isolation, plugin, asset or publish defect. | D2-25
P10-12 | Production security smoke | Verify direct unauthorized API attempts, protected salary/investment access, file isolation, published-page boundary, custom JS isolation and no secret leakage in client/logs. | No critical production security regression. | AI | Security smoke passes. | STOP on any critical security issue. | D2-25
P10-13 | Rollback/readiness check | Confirm a known-good Git commit/tag/version and practical rollback procedure; document what to roll back if deployment fails. | Rollback point and instructions recorded. | AI | Rollback path documented. | STOP if no safe rollback point exists. | D2-25
P10-14 | Final documentation + handover | Update progress tracker, context files, decision register, known issues, production URL(s), environment variable names only, setup steps, smoke results, rollback notes and future improvements. | Handover package is complete without secrets. | AI | All handover fields populated. | STOP if required production facts are unavailable. | D2-25
P10-15 | Final acceptance gate | Verify every Phase 10 completion criterion and confirm no unresolved human gate, no mandatory paid dependency and no unverified production-critical path. | Mark Phase 10 Complete only after evidence exists. | AI | Final acceptance checklist passes. | Do not mark complete if any P0 item is unresolved. | CLOSE

## Production Readiness
Area | Required verification | Expected result | Evidence to record | Human action if blocked
Area | Required verification | Expected result | Evidence to record | Human action if blocked
Hosting | Selected production hosting route matches approved architecture and remains within cost constraint. | Production route identified and deployable without new paid commitment. | Provider/project/route name; no secret values. | Complete provider setup or approve an alternative only if explicitly requested.
Authentication | Firebase Auth/approved auth is configured for production; redirect/origin settings correct. | Login works and session/role state is correct. | Smoke result + config names. | Complete OAuth/consent/domain configuration securely.
Firestore | Production database/project and security rules are correct. | CRUD and protected data access work. | Test record IDs only if safe; rules verification. | Complete project/database permission setup.
Google Drive | Drive OAuth/scopes and folder/file access are configured. | Permitted users can access permitted files; unauthorized access fails. | Folder IDs/names if non-secret; access test. | Complete OAuth/permission grant.
Gmail API | Approved Gmail sending path and sender identity are configured. | Controlled MOM email test succeeds. | Send status/message metadata without sensitive content. | Complete OAuth/consent/sender setup.
Published runtime | Published pages have isolated/safe runtime and correct route/domain. | Preview and published page behavior match expected version. | Production URL/route and version ID. | Configure route/domain only through approved secure flow.
Environment | All required env variable names exist; secret values are stored securely. | No missing required production configuration. | Variable names only; never values. | Enter secrets through secure UI.
Build | Production build/type/lint/test gates pass. | Clean production artifact. | Build/test summary. | Fix blocking defect before deploy.
Billing | No mandatory billing upgrade is triggered. | ₹0 additional-cost target preserved. | Cost gate checklist/screenshot or provider evidence if available. | STOP; do not enable billing without explicit user decision.

## Human Gates
Gate ID | Trigger | What AI must do before stopping | Exact human action | Resume command | AI resumes by
Gate ID | Trigger | What AI must do before stopping | Exact human action | Resume command | AI resumes by
HG10-01 | OAuth/Google service authorization | Identify exact service/scope and why it is needed; do not request secret paste. | Complete OAuth/authorization in the provider UI. | DONE — RESUME PHASE 10 | Re-check token/permission state and continue exact unit.
HG10-02 | Production secrets/config | List variable names and secure location only; never values. | Enter required secrets through secure environment configuration. | DONE — RESUME PHASE 10 | Verify presence/operation without revealing values.
HG10-03 | Billing/paid service prompt | Stop before enabling billing; identify the dependency causing it. | Keep billing disabled or explicitly decide whether to change the architecture. No silent upgrade. | DONE — RESUME PHASE 10 | Re-run cost gate and proceed only if ₹0 constraint remains satisfied.
HG10-04 | Domain/DNS/provider setup | Explain exact configuration needed and expected effect. | Complete domain/DNS/provider action if required. | DONE — RESUME PHASE 10 | Verify route/certificate/host availability.
HG10-05 | Deployment approval/manual platform action | State exact deployment action and where to perform it. | Perform required platform approval/action. | DONE — RESUME PHASE 10 | Inspect deployment status/logs.
HG10-06 | Production defect requiring human decision | Give evidence, impact and options without silently changing business requirements. | Choose/confirm the required business or architecture decision. | DONE — RESUME PHASE 10 | Record decision, then implement only the approved choice.
HG10-07 | Unresolved predecessor blocker | Identify the Phase 9 blocker and why production cannot safely proceed. | Resolve predecessor issue or explicitly decide how to handle it. | DONE — RESUME PHASE 10 | Re-verify predecessor acceptance criteria.

## Production Smoke Test
ID | Test | Expected result | Priority | Status | Evidence | Defect ID | Retest status | Notes
SM-01 | Login + logout | Authentication works in production; logout invalidates session. | P0 | Not Started
SM-02 | Role/ACL | Admin, standard user and employee-self permissions match Phase 9 matrix. | P0 | Not Started
SM-03 | Dashboard | Master dashboard and Projects/Finance/HR navigation work. | P0 | Not Started
SM-04 | Project | Project access/create/edit behavior matches resolved policy. | P0 | Not Started
SM-05 | Countdown | Event countdown displays correct configured event date/time. | P1 | Not Started
SM-06 | Checklist Excel | Authorized upload/access works and authoritative Excel is preserved. | P0 | Not Started
SM-07 | Expense Excel | Authorized upload/access works and structured records remain separate as specified. | P0 | Not Started
SM-08 | Budget/spending | Budget and spending values are consistent with records. | P0 | Not Started
SM-09 | OOP claim | Employee can create own claim; cannot access another employee's claim. | P0 | Not Started
SM-10 | ₹5,000 policy | Configured policy produces expected below/exact/above-threshold results. | P0 | Not Started
SM-11 | Salary | Admin-only salary ledger works; unauthorized users denied. | P0 | Not Started
SM-12 | Payout/carry-forward | Approved reimbursement + salary + configured allowance/extra lines reconcile; unpaid salary carries forward. | P0 | Not Started
SM-13 | Salary report | Report totals reconcile to ledger and claims. | P0 | Not Started
SM-14 | Investments | Admin-only investment ledger works; unauthorized users denied. | P0 | Not Started
SM-15 | MOM | MOM publish/update works and controlled email send status records correctly. | P0 | Not Started
SM-16 | Notes | Project notes permissions/history work. | P1 | Not Started
SM-17 | Builder edit | Page edit/save/load and core editor operations work. | P0 | Not Started
SM-18 | Responsive | Desktop/tablet/mobile preview behaves as configured. | P0 | Not Started
SM-19 | Custom CSS | Scoped CSS persists and does not leak into app shell. | P0 | Not Started
SM-20 | Custom JS | Admin-only JS executes only inside the isolated/sandboxed page runtime. | P0 | Not Started
SM-21 | Themes/templates | Create/apply/duplicate behavior works without mutating unrelated pages unexpectedly. | P1 | Not Started
SM-22 | Plugins | Allowlisted/test extension boundary works; arbitrary untrusted runtime is blocked. | P0 | Not Started
SM-23 | Assets | Permitted asset upload/use works; unauthorized access fails. | P0 | Not Started
SM-24 | Publish | Publish/unpublish/version snapshot works; published runtime uses intended version. | P0 | Not Started
SM-25 | Security | No critical auth/storage/script-isolation/secret-leak issue observed. | P0 | Not Started
SM-26 | Cost | No mandatory paid dependency or billing upgrade introduced. | P0 | Not Started
SM-27 | Rollback | Known-good rollback point and procedure documented. | P1 | Not Started

## Zero-Cost Verification
Check | Must be true | How AI verifies | Status | If false
Check | Must be true | How AI verifies | Status | If false
Google AI Studio / existing Google AI Pro | No new AI subscription is required. | Inspect project/tool configuration and billing implications. | Not Started | STOP and report.
Firebase Auth | Chosen auth path does not require unexpected paid commitment for intended low volume. | Inspect plan/configuration and actual deployment settings. | Not Started | STOP before upgrade.
Firestore | Within intended no-cost/low-volume model for this internal app. | Inspect usage assumptions/configuration; do not claim future usage guarantees. | Not Started | STOP if paid tier is mandatory.
Google Drive | Existing Google storage is used; no Firebase Storage requirement was introduced. | Inspect file-storage implementation and deployment config. | Not Started | STOP and correct before closeout.
Gmail API | No paid transactional email service introduced. | Inspect dependencies and email configuration. | Not Started | STOP and remove/replace paid dependency.
Visual editor | No paid editor plugin is mandatory. | Inspect package/dependency/license configuration. | Not Started | STOP and replace or ask for decision.
Hosting | Selected production route remains within intended no-cost model. | Inspect actual provider/project/billing configuration. | Not Started | STOP before enabling billing.
Other SaaS | No Clerk/Resend/SendGrid/Mailgun/Liveblocks/Trigger.dev/etc. became mandatory without approval. | Dependency scan + architecture context comparison. | Not Started | STOP and report exact dependency.
Billing account | No billing activation is required to finish the production path. | Check provider UI/configuration where accessible. | Not Started | STOP; never silently activate billing.

## Correction Loop
Step | Required action | Evidence | Rule
Step | Required action | Evidence | Rule
1 Reproduce | Reproduce exact production defect or failure condition. | Exact route/action/log/test ID. | Do not fix without a reproducible failure unless configuration is obviously missing.
2 Classify | Classify as configuration, deployment, auth/ACL, data, email, storage, builder runtime, security, financial, or infrastructure. | Category + severity. | P0 security/financial/data-loss issues block closeout.
3 Root cause | Inspect relevant boundary and determine root cause. | Root-cause note. | Do not guess.
4 Smallest fix | Apply smallest safe change within Phase 10 scope. | Commit/diff summary. | No unrelated refactor.
5 Targeted retest | Repeat failed test. | Pass/fail evidence. | Failed retest loops back to root-cause analysis.
6 Regression | Re-run affected critical journey and relevant Phase 9 tests. | Regression results. | No closeout with regression failure.
7 Record | Update correction log and progress tracker. | Correction ID + status. | Keep handover auditable.

## Handover
Handover item | Required content | Secret rule | Status
Handover item | Required content | Secret rule | Status
Production URL(s) | Actual deployed app URL and published-page route/domain if applicable. | URLs are fine; no credentials. | Not Started
Repository state | Branch/commit/tag used for production. | No tokens/keys in logs. | Not Started
Deployment route | Selected hosting/deployment provider and exact project/app identifier where non-sensitive. | Do not include secrets. | Not Started
Environment variables | Names of required variables and where they are configured. | Never record secret values. | Not Started
Auth setup | Production auth provider/config summary and user/role setup process. | No passwords/tokens. | Not Started
Database | Firestore project/collection/schema summary and security-rule status. | No service-account keys. | Not Started
Drive storage | Folder/storage model and permission model. | No OAuth tokens. | Not Started
Gmail/MOM | Sender/recipient configuration and send-status behavior. | No tokens; avoid unnecessary message content. | Not Started
Builder | Editor engine/version, enabled capabilities, custom JS isolation, plugin boundary. | No secrets. | Not Started
Cost | Zero-cost verification result and any usage assumptions/limits. | Do not claim guaranteed future free usage. | Not Started
Smoke tests | Final production smoke test results and failures resolved. | No sensitive data. | Not Started
Rollback | Known-good commit/version and rollback steps. | No credentials. | Not Started
Known issues | Only remaining non-blocking issues, workarounds and impact. | No secrets. | Not Started
Future improvements | Deferred enhancements only; do not silently implement them. | No credentials. | Not Started
Phase status | Phase 10 completion state and timestamp. | No secrets. | Not Started

## Context Updates
Context artifact | Phase 10 update required | Minimum content | Do not change
Context artifact | Phase 10 update required | Minimum content | Do not change
project-overview.md | Yes | Final production state, URL(s), scope delivered, status. | Core product requirements unless decision recorded.
architecture-context.md | Yes | Actual production topology, selected hosting, auth/DB/Drive/Gmail/runtime boundaries. | Do not rewrite architecture merely to fit deployment.
code-standards.md | If deployment fixes change code | Any new deployment-related conventions. | Existing standards.
ai-workflow-rules.md | Yes | Final autonomous workflow/stop-resume state and production verification rules. | Core stop/resume principles.
ui-context.md | If production fixes alter UI | Final published/admin UI state. | Unrelated UI.
progress-tracker.md | Mandatory | All Phase 10 units, final verification, status, evidence, blockers. | Completed history.
agents.md | If agent behavior changed | Final operating constraints relevant to maintenance. | Unrelated agent behavior.
Decision register | Mandatory | Production provider/route, billing decision, domain decision, any resolved gate. | Prior decisions.
Correction log | If corrections occurred | Production defects, root cause, fix, retest and regression evidence. | Completed corrections.
Git checkpoint | Mandatory | Final commit/tag/hash and clean/known-dirty status. | Do not commit secrets.

## Final Acceptance Gate
Gate | Acceptance criterion | Evidence required | Status
Gate | Acceptance criterion | Evidence required | Status
A1 | Phase 9 predecessor accepted and current production candidate identified. | Phase 9 completion + Git state. | Not Started
A2 | Production environment is configured using approved architecture. | Readiness matrix. | Not Started
A3 | No secrets are exposed in repository, client bundle, logs or handover. | Secret hygiene scan/review. | Not Started
A4 | Deployment succeeds and production URL is reachable. | Deployment logs + URL. | Not Started
A5 | Zero-cost verification passes. | Zero-Cost Verification sheet all mandatory checks Pass. | Not Started
A6 | Authentication/ACL production smoke passes. | SM-01/02/11/14/25 results. | Not Started
A7 | Projects production smoke passes. | SM-03 through SM-08 + relevant builder tests. | Not Started
A8 | Finance/HR/financial reconciliation smoke passes. | SM-09 through SM-14. | Not Started
A9 | MOM/email smoke passes. | SM-15. | Not Started
A10 | Builder/publishing smoke passes including responsive/CSS/JS/plugins/assets. | SM-17 through SM-24. | Not Started
A11 | Rollback point is documented. | Handover rollback item. | Not Started
A12 | Progress/context/decision/correction artifacts are updated. | Context Updates + progress tracker. | Not Started
A13 | Known issues are documented and none are production-blocking. | Handover known issues. | Not Started
A14 | Final handover is complete and no human gate remains. | Handover + Human Gates. | Not Started
A15 | Phase 10 marked COMPLETE; no Phase 11 created. | Final tracker status. | Not Started

## AI Studio Master Prompt
Prompt section | Instruction to Google AI Studio
Prompt section | Instruction to Google AI Studio
ROLE | You are the autonomous production/deployment agent for Phase 10 of the Master Website project. Your job is to finish D2-24 and D2-25 from the approved master workbook, not to redesign the product.
SOURCE OF TRUTH | Read this entire workbook first. Then read the master workbook and all available project context/spec/progress artifacts from Phases 1–9, especially architecture-context.md, project-overview.md, ai-workflow-rules.md, progress-tracker.md, decision register, correction log, Phase 9 handoff, Required Tools, Open Questions, Permissions Matrix, Feature Specs and Full Builder Matrix.
FIRST ACTION | Inspect the actual repository, current branch, Git status/log, build configuration, environment variable names, package/dependency state and the last verified Phase 9 state. Do not assume a provider or deployment route.
EXECUTION LOOP | For each P10 unit: (1) identify acceptance criteria, (2) inspect dependencies, (3) plan, (4) execute only the unit scope, (5) verify, (6) update progress/context, (7) continue if pass.
HUMAN GATES | If any action requires human OAuth authorization, secure secret entry, domain/DNS setup, provider approval, billing decision, unresolved business decision or other essential manual action, STOP. Explain exactly what the human must do. Never request secrets in chat.
RESUME | When the user replies exactly or equivalently 'DONE — RESUME PHASE 10', verify the previously blocked condition, then resume from the exact unit/sub-step. Do not restart completed work.
COST | The hard invariant is ₹0 additional cost beyond the existing Google AI Pro subscription. Never activate billing or a paid tier silently. Verify Firebase Auth/Firestore, Google Drive, Gmail API, open-source editor/libraries and the selected hosting route against the intended no-cost model. If a paid dependency is required or unclear, STOP.
DEPLOYMENT | Deploy only using the already selected architecture/provider. If the project has no resolved production provider, stop and ask the human to select/confirm one rather than inventing it.
SECURITY | Never expose credentials. Verify auth, ACL, file access, published-page boundaries, custom JavaScript isolation, XSS/CSRF/injection protections, storage rules and secret hygiene remain intact in production.
SMOKE TEST | Run the production critical journey: login → project → countdown → Excel upload → expense → OOP → salary → report → MOM email → custom page → publish → responsive preview. Also verify notes, protected admin pages, financial reconciliation, builder JS isolation, plugins/assets and rollback.
CORRECTION LOOP | For every failure: reproduce → classify → root cause → smallest safe fix → targeted retest → regression → record. Do not perform unrelated refactors.
HANDOVER | Update progress tracker, context files, decision register, correction log and handover sheet. Record URLs, selected provider/route, environment variable names only, Git commit/tag, smoke results, cost verification, rollback steps and known issues. Never record secret values.
COMPLETION | Mark Phase 10 complete only when D2-24 deployment and D2-25 production smoke/handover pass, zero-cost verification passes, no critical security/financial issue remains, and all required human gates are resolved.
NO PHASE 11 | After final acceptance, stop. Do not invent or execute a Phase 11. Provide a concise final handover summary with completed units, production URL(s), verification status, known non-blocking issues and the final Git checkpoint.

## Completion & Handover
Item | Phase 10 final requirement | Status
Item | Phase 10 final requirement | Status
D2-24 | Production environment configured and deployed successfully. | Not Started
D2-25 | Final production smoke test completed. | Not Started
Zero-cost gate | No mandatory new billing/subscription/paid service introduced. | Not Started
Security | No critical production security issue remains. | Not Started
Financial | Critical financial calculations/reconciliation pass. | Not Started
Builder | Critical production builder/publishing paths pass. | Not Started
Context | Progress/context/decision/correction records updated. | Not Started
Handover | Production URL(s), configuration names, rollback, known issues and future improvements documented. | Not Started
Git | Final production commit/tag/checkpoint recorded. | Not Started
Human gates | All required human actions completed and re-verified. | Not Started
Final status | Phase 10 COMPLETE; project handed over. | Not Started

## Decision Register
Decision ID | Decision | Default/source | When to stop | Recorded decision | Status
Decision ID | Decision | Default/source | When to stop | Recorded decision | Status
P10-D01 | Production hosting route | Use the provider/route already selected in architecture context; do not invent one. | If none is resolved. |  | Open
P10-D02 | Production domain/route | Use already resolved same-app/published route decision from earlier phase. | If DNS/domain is required and unresolved. |  | Open
P10-D03 | Billing | ₹0 additional cost is hard constraint. | Any mandatory upgrade/charge. |  | Resolved = ₹0
P10-D04 | Secrets | Secure environment/secret manager; never chat. | If secure entry is required. |  | Resolved
P10-D05 | Rollback | Known-good Git checkpoint before/at deployment. | If no safe rollback point exists. |  | Open
P10-D06 | Known issues | Only non-blocking issues may remain at handover. | Any P0/P1 production blocker. |  | Open

## Playbook Alignment
Playbook principle | How Phase 10 implements it | Evidence
Playbook principle | How Phase 10 implements it | Evidence
Architecture before action | Restore and obey approved production architecture before deploying. | Production Readiness + architecture-context.md
Plan before implementation | Each P10 unit has acceptance criteria and execution sequence. | Phase 10 Units
One unit at a time | Deployment, verification and handover are separated into units. | Phase 10 Units
Verification before completion | Production deployment is not accepted without smoke/cost/security checks. | Production Smoke + Final Acceptance
Focused correction loop | Failures use reproduce/root cause/small fix/retest/regression. | Correction Loop
Human intervention gates | AI stops for OAuth, secrets, billing, DNS, approvals and unresolved decisions. | Human Gates
Progress persistence | Progress/context/decision/correction records updated throughout. | Context Updates
Git/recovery | Final production checkpoint and rollback are documented. | Handover + Git checkpoint
Production verification | Final smoke test uses the requested end-to-end journey. | Production Smoke Test
Cost control | No new mandatory paid services; verify actual configuration. | Zero-Cost Verification
Handover | Final URLs, configuration, rollback, issues and future improvements are documented. | Handover

## Workbook Index
Order | Sheet | Purpose
1 | START HERE | Read first; scope, autonomy, cost invariant, resume and completion rules.
2 | Autonomous Control | Global agent behavior and stop/resume rules.
3 | Phase 10 Units | P10-01 through P10-15 execution sequence.
4 | Production Readiness | Pre-deployment readiness matrix.
5 | Human Gates | Exact intervention gates and resume behavior.
6 | Production Smoke Test | Production critical-path verification.
7 | Zero-Cost Verification | Mandatory ₹0 additional-cost verification.
8 | Correction Loop | Focused production defect correction method.
9 | Handover | Required production handover record.
10 | Context Updates | Files/state that must be updated.
11 | Final Acceptance Gate | Definition of done.
12 | AI Studio Master Prompt | Primary autonomous execution instructions.
13 | Completion & Handover | Final status checklist.
14 | Decision Register | Phase 10 decisions and blockers.
15 | Playbook Alignment | Traceability to the build playbook.