## START HERE
PHASE 1 — PRODUCT UNDERSTANDING, REQUIREMENTS FREEZE & ARCHITECTURE ¦ GOOGLE AI STUDIO AUTONOMOUS HANDOFF
Item | Instruction
Purpose | This workbook is the complete execution contract for Phase 1 only. Upload this workbook to Google AI Studio at the start of the project. AI Studio must execute the phase autonomously, stop only when a human action/decision is genuinely required, tell the user exactly what to do, wait, and resume when the user confirms completion.
Phase window | Day 1 — 20-Sep-2026, 08:00–09:00 local time. Do not silently continue into Phase 2 before Phase 1 passes its final gate.
Application | Internal company master website for approximately 20 people initially, designed so the same architecture can support growth to approximately 100 people.
Core requirement | Projects + Finance + HR + project files + expense management + MOM email + out-of-pocket reimbursement + salary + investments + notes + permissions + a genuinely flexible visual website builder.
Builder requirement | Do NOT downgrade the builder to a predefined block-only editor. It must target drag/drop, arbitrary positioning/layouts, resize, nested columns/containers, responsive breakpoints, typography, styling, animations/interactions, custom CSS, custom JavaScript, reusable components, pages, templates/themes, plugin/extension capability, assets, preview, undo/redo, save/load and publish.
Cost requirement | Target ₹0 additional cost beyond the user's existing Google AI Pro subscription. Prefer open-source libraries and Google services already available to the user. Do not introduce paid SaaS dependencies without explicit user approval.
Execution principle | AI is the implementation engine; the workbook is the authoritative Phase 1 contract. Read it fully before acting. Do not guess about requirements that affect architecture.
Source methodology | Follow the attached app-building playbook methodology: understand → pressure-test → architecture → durable context → explicit boundaries → verification. The playbook says architecture and context precede serious implementation and that agents must work in bounded units.
Critical behavior | If human intervention is required (account authorization, OAuth consent, GitHub connection, API key/secret entry, service permission, unresolved product decision), STOP. Do not fake completion. State the exact action, where to perform it, what success looks like, and the exact phrase the user should send to resume.
Resume behavior | When the user says the requested action is complete, re-check the dependency yourself. If it passes, resume automatically from the exact paused task. Do not restart Phase 1 and do not ask the user to repeat already-completed work.
No premature implementation | Phase 1 must produce the product/architecture/context foundation. Do not start business-feature implementation merely because the AI can code it. Phase 2 handles project foundation/environment implementation.
Completion rule | Phase 1 is complete only when every Phase 1 acceptance criterion passes, all required decisions are recorded, all context files exist and agree, human gates are resolved or explicitly documented, and a handoff package for Phase 2 is written.

## Autonomous Control
PHASE 1 AUTONOMOUS EXECUTION CONTROL
Step | Time | Phase Unit | AI must do | Human gate? | STOP condition | Resume command | Verification | Status
P1-01 | 08:00–08:05 | Load and understand workbook | Read every sheet/cell relevant to Phase 1; summarize requirements internally; establish workbook as authoritative. | No | Only if file cannot be read or is corrupted. | Upload/repair workbook and say: RESUME PHASE 1 | Requirements are loaded; no missing Phase 1 input. | Not Started
P1-02 | 08:05–08:12 | Requirement normalization | Create a requirements inventory covering all business modules and every full-builder capability. Identify ambiguity without silently changing scope. | No, unless an ambiguity changes architecture or accounting/security behavior. | A required product decision cannot be safely defaulted. | Tell user the exact decision with 2–3 concrete options and say: RESUME PHASE 1 after decision. | Inventory maps to source requirements; no requirement silently removed. | Not Started
P1-03 | 08:12–08:20 | Scope and success criteria | Freeze Phase 1 scope, Phase 2+ boundaries, 2-day constraint, 20→100-user scalability assumption, and ₹0 additional-cost constraint. | No | A constraint conflicts with another requirement. | Ask the user to resolve the conflict; resume phrase: RESUME PHASE 1. | In/out-of-scope list is explicit. | Not Started
P1-04 | 08:20–08:30 | Architecture options analysis | Evaluate the app architecture needed for this exact internal use case. Prefer mature/open-source builder engine and Google ecosystem services; document responsibility per service. | Only if an external account/connection is actually required to validate a selected service. | AI cannot validate an integration because authorization is required. | Give exact UI/action steps; after user completes it, they say: DONE — RESUME PHASE 1. | Architecture context has one owner per data type and no contradictory services. | Not Started
P1-05 | 08:30–08:37 | Security/permissions architecture | Define Admin vs Standard User and page/project-level editing/access. Define server-side authorization invariants. | No unless policy is genuinely ambiguous. | A permission rule affects sensitive salary/investment data and cannot safely be defaulted. | Ask one precise decision; resume with RESUME PHASE 1. | Permissions matrix is complete and mutation boundaries are defined. | Not Started
P1-06 | 08:37–08:45 | Human integration gates | Attempt required environment/account integrations only if Phase 1 truly needs them. Never ask for credentials in chat; use secure UI/secret mechanisms. If OAuth/GitHub/etc. requires user action, stop. | Yes, if required | OAuth/connection/permission cannot be completed autonomously. | Tell user exactly what to click/connect; then user says DONE — RESUME PHASE 1. | Dependency is re-checked successfully before proceeding. | Not Started
P1-07 | 08:45–08:53 | Generate durable AI context | Create/update agents.md, project-overview.md, architecture-context.md, code-standards.md, ai-workflow-rules.md, ui-context.md, progress-tracker.md and feature-spec index. These are Phase 1 deliverables. | No | Repository/file write access is unavailable. | Ask user to grant/enable the required workspace/repository access; resume phrase: DONE — RESUME PHASE 1. | All files exist, are internally consistent, and point to Phase 2. | Not Started
P1-08 | 08:53–08:57 | Architecture verification | Run consistency checks: requirements ↔ architecture ↔ permissions ↔ storage ↔ builder ↔ cost constraint. Detect contradictions and fix only Phase 1 artifacts. | No | A contradiction cannot be resolved without user choice. | State the exact conflict and ask for one decision; resume with RESUME PHASE 1. | No unresolved architectural contradiction. | Not Started
P1-09 | 08:57–09:00 | Phase 1 handoff gate | Write Phase 2 handoff: exact next unit, dependencies, files to read, decisions, open questions, and verification plan. Mark Phase 1 COMPLETE only after all checks pass. | No | Any P0 acceptance criterion is incomplete. | Continue Phase 1 until complete; do not mark done. | Phase 1 acceptance matrix passes 100%. | Not Started

## Requirements Freeze
PHASE 1 — REQUIREMENTS FREEZE / AUTHORITATIVE PRODUCT CONTRACT
ID | Area | Frozen requirement | Access / ownership | Phase 1 decision | Acceptance definition | Priority | Status
R1 | Master site | Master website with Projects, Finance, HR and provision for custom pages. | Role-controlled | Included | Top-level navigation and module boundaries defined. | P0 | Frozen
R2 | Projects | Create/edit projects, event date/countdown, members/access, project-specific files, expenses, MOM, notes. | Configurable by permission | Included | Project data model and ownership defined. | P0 | Frozen
R3 | Checklist Excel | User can enter title and upload an already-ready Excel; file is reflected in the project site. | Project access/editor | Included | Authoritative file + metadata model defined; display/download behavior defined. | P0 | Frozen
R4 | Expense Excel | User can enter title and upload Excel; budget allocation and employee expense details are represented and reflected. | Project access/editor + finance controls | Included | File + structured expense ledger relationship defined. | P0 | Frozen
R5 | MOM | MOM can be updated and automatically emailed to registered project recipient emails. | Authorized editor; recipient list controlled | Included | Recipient source and send trigger defined. | P0 | Frozen
R6 | Out-of-pocket | Employees record own-pocket expenses monthly; claims flow into salary payout calculation. | Employee own claim; admin approval/configuration | Included | Claim lifecycle and salary integration boundary defined. | P0 | Frozen
R7 | ₹5,000 rule | Each employee has ₹5,000 allowance/threshold; amount above threshold plus requested extra ₹5,000 behavior must be represented as configurable policy until confirmed. | Sensitive finance/admin | Needs explicit policy confirmation if implementation semantics remain ambiguous | Phase 1 must not invent accounting behavior. | P0 | Decision gate
R8 | Salary | Admin-only salary data; monthly due salary; pending carried forward; generate report. | Admin only | Included | Salary ledger and carry-forward model defined. | P0 | Frozen
R9 | Investments | Admin-only investment records: amount, from whom, date, return date. | Admin only | Included | Investment entity and access boundary defined. | P0 | Frozen
R10 | HR | Employee details and user identity/access relationship. | Admin-controlled sensitive fields | Included | Employee/user relationship defined. | P0 | Frozen
R11 | Flexible editing | Users with access can edit permitted pages/projects/text/links; admins control protected pages. | Permission-based | Included | Server-side authorization model defined. | P0 | Frozen
R12 | Full website builder | Drag/drop, resize, arbitrary/nested layouts, responsive breakpoints, styling, animations, interactions, custom CSS/JS, reusable components, pages, templates/themes, extension/plugin capability, assets, preview, undo/redo, save/load, publish. | Admin/configurable + page-level permissions | Included without reducing scope | Mature editor engine integration boundary defined. | P0 | Frozen
R13 | New pages | Users/admins can create new website pages/sheets when permitted. | Permission-based | Included | Page entity, slug, content/editor state, publication and permissions defined. | P0 | Frozen
R14 | Scale | Initial ~20 users; architecture should not hardcode a 20-user ceiling and should remain usable as company approaches ~100 users. | Internal application | Included | No data model or permission logic depends on fixed headcount. | P0 | Frozen
R15 | Cost | Target ₹0 additional software/service spend beyond existing Google AI Pro; avoid mandatory paid SaaS/billing dependencies. | Architecture invariant | Included | Cost gate included; any unavoidable billing dependency requires explicit approval. | P0 | Frozen

## Architecture Decisions
PHASE 1 — ARCHITECTURE DECISION RECORD
ID | Decision area | Decision to make | Preferred direction | Reason / boundary | Human gate | Evidence required | Status
A1 | Application runtime | What application runtime/framework will be the implementation foundation? | Use the runtime/framework Google AI Studio generates/supports reliably for the project, with React + TypeScript where applicable. | Do not add a second framework unless required. | Only if AI Studio cannot support a needed capability. | Generated app builds and runs. | Open
A2 | Visual editor | What engine powers the full website builder? | GrapesJS or another mature open-source visual editor that demonstrably supports required capabilities. | Do not build drag/drop/editor internals from scratch in 2 days. | Only if engine choice requires user approval/license clarification. | Capability matrix mapped to engine features. | Open
A3 | Structured data | Where does application state live? | Firestore for users, projects, permissions, finance/HR records, pages and metadata. | One authoritative owner per entity; avoid giant opaque blobs. | No | Schema ownership map. | Open
A4 | File storage | Where do uploaded Excel/PDF/image files live? | Google Drive via supported API/integration; store file metadata/IDs in Firestore. | Avoid mandatory Firebase Storage/Blaze dependency. | Yes if Drive OAuth/permissions require user action. | Successful authorized Drive access or documented integration boundary. | Open
A5 | Authentication | How are users identified? | Firebase Auth / Google identity approach supported by the selected runtime. | No anonymous privileged access; protect sensitive modules. | Yes if OAuth configuration requires user action. | Authenticated user can be mapped to role. | Open
A6 | Email | How are MOM emails sent? | Gmail API or Google-supported mail mechanism available to the application, for low-volume internal use. | Do not introduce paid transactional email provider as a mandatory dependency. | Yes if Google OAuth consent is required. | Test email successfully delivered. | Open
A7 | Backend | Where do server-side mutations/business rules execute? | Use the server-side capabilities of the selected AI Studio/full-stack environment; avoid mandatory Firebase Cloud Functions. | All sensitive calculations and authorization remain server-side. | Yes if deployment/runtime configuration requires user action. | Mutation boundary diagram + test. | Open
A8 | Hosting | Where is the app deployed? | Use a Google AI Studio-supported no-cost deployment route or Firebase Hosting free option, subject to current eligibility/limits. | No billing-enabled deployment without explicit approval. | Yes if deployment authorization is required. | Production URL + smoke test. | Open
A9 | Permissions | Where is authorization enforced? | Server/API mutation boundaries plus UI visibility. | Never rely only on hidden UI controls. | No | Unauthorized mutation tests. | Open
A10 | Builder persistence | How is page/editor state saved? | Persist structured page metadata/editor state in the defined data layer; store large assets separately. | Reload must reproduce the saved page. | No | Save → reload → identical state test. | Open
A11 | Cost invariant | What happens if a chosen service requires paid billing? | STOP and ask the user; do not silently enable billing or substitute a paid service. | User controls financial authorization. | Yes | Explicit user approval if ever required. | Open

## Human Gates
PHASE 1 — HUMAN INTERVENTION GATES
Gate ID | Trigger | AI must STOP when… | AI must tell user | User action | Resume phrase | AI resume behavior | Status
HG-01 | GitHub/repository connection | AI Studio cannot access/connect the repository or requires OAuth approval. | Exact connection path, account/repository target, and what success looks like. Never ask for password/token in chat. | Complete the connection/authorization in the UI. | DONE — RESUME PHASE 1 | Re-test repository access, continue from paused task; do not restart. | Pending
HG-02 | Google Drive OAuth | Drive API/integration needs user consent. | Exact Google account/permission action and expected confirmation. | Grant requested Drive permission. | DONE — RESUME PHASE 1 | Verify file listing/access and continue. | Pending
HG-03 | Gmail OAuth | Gmail API/email sending requires consent. | Exact consent action and minimum scope requested. | Grant the required Gmail permission. | DONE — RESUME PHASE 1 | Send a controlled test only after authorization and verify result. | Pending
HG-04 | Firebase/Auth configuration | Authentication requires project setup, OAuth configuration or a console action unavailable to AI. | Exact console screen/action and required values; never request secrets in chat. | Complete setup securely. | DONE — RESUME PHASE 1 | Re-check auth configuration and continue. | Pending
HG-05 | Billing request | Any service asks to enable Blaze/billing or paid subscription. | State the exact service and why it requested billing; do not enable it. | Either approve explicitly or instruct AI to redesign around a no-cost alternative. | APPROVE BILLING — RESUME PHASE 1 / or REDESIGN — RESUME PHASE 1 | Proceed only according to user's explicit choice. | Pending
HG-06 | Product ambiguity | Requirement affects security, salary, reimbursement, permissions, or core architecture and cannot safely be defaulted. | Give the exact question, current interpretations, and recommended neutral default only as a proposed decision—not an assumption. | Choose/confirm the rule. | RESUME PHASE 1 | Record decision in architecture/context and continue. | Pending
HG-07 | Tool/license uncertainty | A proposed editor/plugin/service has unclear licensing or would add cost. | Identify the component and license/cost uncertainty. | Approve or choose open-source alternative. | RESUME PHASE 1 | Record selected tool and proceed. | Pending

## Context Deliverables
PHASE 1 — DURABLE AI CONTEXT FILES
File | Must exist after Phase 1? | Purpose | Required contents for this app | AI behavior | Verification | Status
agents.md | Yes | AI Studio execution entry point | Read order; phase protocol; stop/resume rules; no-guessing; one-unit execution; verification; progress updates. | AI must read this first every session. | File exists and points to all required context/specs. | Not Started
context/project-overview.md | Yes | Product truth | Company master website; users; modules; complete builder; cost target; scale; success criteria; in/out scope. | Authoritative product definition. | Matches Requirements Freeze. | Not Started
context/architecture-context.md | Yes | System blueprint | Runtime; editor engine; Firestore; Auth; Drive; Gmail; hosting; client/server boundaries; data ownership; permissions; cost invariant. | No technology may be introduced without a documented responsibility. | Architecture review passes. | Not Started
context/code-standards.md | Yes | Implementation consistency | TypeScript/React conventions; component patterns; naming; validation; error handling; security; file organization. | Follow existing project conventions before adding code. | No contradictions with selected runtime. | Not Started
context/ai-workflow-rules.md | Yes | Autonomous agent behavior | Read context; plan; implement exact scope; stop at human gates; resume; verify; no billing; no secrets in chat; update tracker. | This is the operational control contract. | Rules cover every Human Gate. | Not Started
context/ui-context.md | Yes | Visual system | Master site shell; dashboard; editor; navigation; responsive behavior; design tokens; accessibility baseline. | Use reusable primitives and preserve builder/editor usability. | UI direction defined before Phase 2. | Not Started
context/progress-tracker.md | Yes | Living project state | Current phase; completed; in progress; next; decisions; session notes; open questions; human gates; exact resume point. | Update after every meaningful checkpoint. | Can resume without chat history. | Not Started
context/feature-specs/README.md | Yes | Feature map entry | Phase 2–10 feature-unit sequence and dependencies; link to future specs. | Do not implement future units in Phase 1. | Feature roadmap exists. | Not Started

## Builder Architecture
PHASE 1 — FULL VISUAL BUILDER ARCHITECTURE CONTRACT
Capability | Required | Architecture responsibility | Phase 1 decision | Persistence/security boundary | Verification planned | Status | Notes
Drag/drop | Yes | Visual editor engine | Use mature editor capability; configure rather than reinvent. | Only authorized page editors can mutate page state. | Capability mapped to selected engine. | Open
Move/reposition | Yes | Visual editor engine | Enable supported positioning/layout modes. | Persist page state. | Move → save → reload. | Open
Resize | Yes | Visual editor engine | Enable sizing/handles and responsive values. | Persist responsive settings. | Resize desktop/mobile → reload. | Open
Arbitrary/nested columns | Yes | Visual editor + CSS layout | Use nested containers, flex/grid and layout primitives. | Persist component hierarchy. | Build multi-column nested layout. | Open
Responsive breakpoints | Yes | Visual editor devices/style manager | Define desktop/tablet/mobile behavior. | Persist breakpoint-specific values. | Preview all target widths. | Open
Typography/style controls | Yes | Style manager | Expose font, size, weight, line-height, color, spacing, borders, backgrounds. | Sanitize/validate stored styles. | Edit style → reload. | Open
Animations/interactions | Yes | Editor/plugin/custom integration | Use engine-native/open-source capability first. | Do not allow unsafe arbitrary execution by unauthorized users. | Create/test animation/interaction. | Open
Custom CSS | Yes | Editor code/style layer | Allow page-level custom CSS within permission boundary. | Sanitize/store page-scoped CSS. | Add CSS → preview/publish. | Open
Custom JavaScript | Yes | Editor code layer | Allow page-scoped JS only for authorized users; document security boundary. | Never execute untrusted code outside intended page sandbox/context. | Add simple JS → preview. | Open
Reusable components | Yes | Editor component system | Define reusable components/blocks without limiting free layout. | Version/persist component definitions. | Create → reuse → reload. | Open
Pages | Yes | Application page model | Page entity with title/slug/status/content/editor state. | Permission-aware CRUD. | Create/edit/publish page. | Open
Templates/themes | Yes | Editor/application layer | Define reusable page templates and theme tokens. | Admin-controlled global templates/themes. | Apply template/theme. | Open
Plugins/extensions | Yes | Extension architecture | Support open-source/custom extensions; no paid plugin dependency. | Only trusted extensions/admin installation. | Install/enable test extension. | Open
Assets | Yes | Google Drive + editor asset manager | Asset metadata in DB; binary files in Drive. | Access-controlled file references. | Upload/select/reuse asset. | Open
Undo/redo | Yes | Editor command/history system | Use mature editor command history. | Local/editor state + persistence checkpoints. | Undo/redo after changes. | Open
Save/load/autosave | Yes | Application persistence | Explicit save plus safe autosave strategy. | Server-side ownership check. | Edit → save → reload. | Open
Preview | Yes | Editor/runtime | Preview without editing controls. | Preview respects page permissions and safe execution boundary. | Preview matches published page. | Open
Publish/unpublish | Yes | Page lifecycle | Draft/published states with version-aware save. | Only authorized users publish protected pages. | Publish → public/internal view. | Open

## Acceptance Gate
PHASE 1 — DEFINITION OF DONE / ACCEPTANCE GATE
ID | Acceptance criterion | How AI verifies | Evidence to leave in project | If failed | Priority | Status
AC1 | Every user requirement is captured without silently reducing the full builder scope. | Compare Requirements Freeze against source workbook and all declared requirements. | Updated project-overview + requirements inventory. | Fix Phase 1 artifacts; do not proceed. | P0 | Not Started
AC2 | Architecture has one clear responsibility per technology/service. | Review architecture-context and Architecture Decisions for overlap/conflict. | Architecture context + decision record. | Resolve contradiction. | P0 | Not Started
AC3 | Full visual builder remains genuinely in scope. | Check Builder Architecture: all required capabilities present. | Builder architecture contract. | Do not downgrade; choose/reconfigure mature engine. | P0 | Not Started
AC4 | Cost invariant is preserved. | Scan dependencies/config for paid SaaS or billing-required services. | Cost decision record + dependency list. | STOP and redesign or ask user. | P0 | Not Started
AC5 | Admin vs standard-user authorization boundaries are explicit and server-enforced. | Review permissions matrix and mutation-boundary rules. | Permission model + security invariants. | Fix architecture before Phase 2. | P0 | Not Started
AC6 | Google Drive/Gmail/Auth dependencies are explicitly modeled with human gates. | Review integration decisions and Human Gates. | Integration boundary + gate records. | Add missing gate. | P0 | Not Started
AC7 | Seven durable context files plus feature-spec index exist and are internally consistent. | Open and cross-check each file. | All context files committed/saved. | Repair context and re-check. | P0 | Not Started
AC8 | Progress tracker contains exact Phase 2 starting point. | Read progress-tracker and compare with Phase roadmap. | Phase 2 handoff section. | Update tracker. | P0 | Not Started
AC9 | No business feature implementation was incorrectly marked complete during Phase 1. | Review change list/repo diff if available. | Phase boundary note. | Revert/record scope correction. | P0 | Not Started
AC10 | Phase 1 is explicitly marked COMPLETE only after all P0 checks pass. | Run final gate and write completion timestamp. | Progress tracker + phase completion record. | Continue work; do not claim completion. | P0 | Not Started

## Phase 2 Handoff
PHASE 1 OUTPUT → PHASE 2 HANDOFF
Handoff item | Must be produced | Content | Used by Phase 2 | Completion test | Status | Notes
Product contract | Yes | Frozen requirements, users, scope, success criteria, non-negotiables. | Foundation implementation | Phase 2 can build without asking what the product is. | Not Started
Architecture contract | Yes | Runtime, editor, DB, auth, file storage, email, hosting, boundaries, invariants. | Foundation implementation | Every component has one owner. | Not Started
Human gate status | Yes | Which integrations were completed, which remain, exact resume point if paused. | Phase 2 setup | No hidden blocked dependency. | Not Started
Context system | Yes | agents.md + six context files + feature-spec index. | Every future AI session | AI can resume from files alone. | Not Started
Builder engine decision | Yes | Selected engine + capability mapping + integration boundary. | Builder implementation | Phase 5/8 can start without re-evaluating the editor architecture. | Not Started
Cost architecture | Yes | Explicit no-additional-cost dependency list and prohibited mandatory services. | All phases | No accidental paid dependency. | Not Started
Permissions model | Yes | Admin/standard/user/page/project/file/finance boundaries. | Auth + CRUD + builder | Security tests can be written. | Not Started
Phase 2 next action | Yes | Exact first feature unit, files to read, expected output, verification. | Phase 2 execution | AI can start Phase 2 immediately. | Not Started

## Stop Resume Protocol
MANDATORY STOP / ASSISTANCE / RESUME PROTOCOL
Situation | AI behavior | What AI must say | What user does | Exact resume phrase | AI after resume | Forbidden behavior
Needs GitHub connection | STOP immediately. | I need one human action: connect/authorize GitHub in [exact UI]. I have completed [what is already done]. Success looks like [specific result]. | Complete the connection in the UI. | DONE — RESUME PHASE 1 | Re-check access, then continue from the paused step. | Do not claim GitHub is connected without verification.
Needs Google OAuth | STOP immediately. | I need you to approve [specific Google permission]. I will not request or store your password/token in chat. | Approve OAuth consent. | DONE — RESUME PHASE 1 | Verify the granted scope and continue. | Do not ask for credentials in chat.
Needs product decision | STOP immediately. | Decision required: [question]. Option A: [meaning]. Option B: [meaning]. I recommend [neutral implementation default if appropriate], but I will not assume it. | Choose/confirm decision. | RESUME PHASE 1 | Record decision, update context, continue. | Do not silently choose a consequential rule.
Hits paid billing | STOP immediately. | This service is requesting billing: [service]. I have NOT enabled it. I can redesign to avoid it or you can explicitly authorize it. | Choose redesign or explicit billing approval. | REDESIGN — RESUME PHASE 1 / APPROVE BILLING — RESUME PHASE 1 | Follow the chosen path and document it. | Never enable billing autonomously.
Tool unsupported | STOP only if no safe alternative is already documented. | [Capability] cannot be implemented with the selected tool as configured. Here is the smallest decision needed. | Approve documented alternative or provide access. | RESUME PHASE 1 | Update architecture decision and continue. | Do not invent a hidden dependency.
Verification failure | Do not ask user unless human action is required. | Capture exact error, identify boundary, attempt focused correction, rerun verification. | Only act if requested by the exact human gate. | RESUME PHASE 1 if asked. | Continue corrective loop. | Do not restart whole project or broaden scope.

## AI Studio Master Prompt
COPY-PASTE MASTER EXECUTION INSTRUCTION FOR GOOGLE AI STUDIO
MASTER PROMPT
You are the implementation agent for Phase 1 of this application. AUTHORITATIVE INPUT 1. This workbook is the Phase 1 execution contract. 2. The attached/full project-building playbook is the methodology reference. 3. Do not silently replace or reduce requirements. MISSION Complete ONLY Phase 1: Product Understanding, Requirements Freeze & Architecture. Do not start Phase 2 business implementation until Phase 1 passes its Acceptance Gate. AUTONOMOUS EXECUTION 1. Read every sheet in this workbook before changing anything. 2. Inspect the current project/repository/workspace state. 3. Execute the Autonomous Control sequence in order. 4. Create/update the durable context files defined in Context Deliverables. 5. Build no business feature merely because it is easy to implement in this phase. 6. The full visual website builder is NOT to be reduced to a block-only builder. Preserve the full requirement: drag/drop, arbitrary/nested layouts, resize, responsive breakpoints, styling, animations/interactions, custom CSS, custom JavaScript, reusable components, pages, templates/themes, extension/plugin capability, assets, preview, undo/redo, save/load and publish. 7. Prefer a mature open-source editor engine such as GrapesJS or an equivalent that actually covers the required capability set. Do not hand-build a complete visual-editor engine from scratch. 8. Preserve the ₹0 additional-cost target beyond the user's existing Google AI Pro subscription. Do not silently introduce paid SaaS, paid plugins, billing-required Firebase services, or a new subscription. 9. Prefer Google services and open-source libraries already specified by the architecture: Firestore/Auth, Google Drive, Gmail API, and an appropriate no-cost deployment route, subject to actual product availability/limits. 10. Never ask the user to paste passwords, private keys, OAuth client secrets, access tokens or other sensitive credentials into chat. 11. If human assistance is genuinely required, STOP. Use the Human Gates and Stop/Resume Protocol. Tell the user exactly what action is needed, where to do it, what success looks like, and the exact resume phrase. 12. When the user confirms completion, re-check the dependency yourself. Resume from the exact paused step. Do not restart completed work. 13. If an error occurs, use the focused corrective loop: capture exact error → identify smallest boundary → inspect relevant documentation/integration contract → make smallest correction → verify again. 14. Update progress-tracker.md after meaningful checkpoints. 15. At the end, run the Acceptance Gate. Phase 1 is COMPLETE only when every P0 acceptance criterion passes. 16. Before declaring completion, write the Phase 2 Handoff with the exact next task and dependencies. FINAL RESPONSE WHEN PHASE 1 IS COMPLETE Report: - Phase 1 status: COMPLETE - What was created/decided - Human gates completed - Remaining open questions (if any) - Exact Phase 2 starting point - Verification results - Any files changed Do not claim a service is connected or a test passed unless you actually verified it.

## Playbook Alignment
PHASE 1 ALIGNMENT TO THE UPLOADED APP-BUILDING PLAYBOOK
Playbook principle | Phase 1 implementation | Source-supported reason | Workbook location | Phase 1 test | Status
Architecture before coding | Requirement freeze + architecture decisions precede implementation. | The playbook says to clarify product, pressure-test, choose architecture and define boundaries before serious implementation. | Requirements Freeze; Architecture Decisions | No business feature begins before architecture gate. | Not Started
Durable context | Create agents.md + six context files. | The playbook uses durable context to prevent AI drift and enable resumption. | Context Deliverables | All files exist and cross-reference each other. | Not Started
Feature-unit execution | Phase 1 itself is decomposed into controlled units. | The playbook recommends one feature/unit at a time with dependencies and verification. | Autonomous Control | Each unit has a done condition. | Not Started
Human ambiguity handling | Stop instead of guessing when a consequential requirement is missing. | The playbook explicitly says missing requirements should be recorded and resolved rather than silently invented. | Stop Resume Protocol | No unresolved consequential assumption is hidden. | Not Started
Focused correction | Use exact errors and smallest affected boundary. | The playbook specifies a diagnosis-and-correction loop rather than broad re-prompts. | Stop Resume Protocol | Any Phase 1 failure is corrected narrowly. | Not Started
Progress persistence | Maintain progress tracker and next unit. | The playbook requires state to remain resumable across sessions. | Context Deliverables; Phase 2 Handoff | AI can resume without reconstructing chat history. | Not Started