## START HERE
PHASE 2 — AI CONTEXT, PROJECT FOUNDATION & DEVELOPMENT ENVIRONMENT ¦ GOOGLE AI STUDIO AUTONOMOUS HANDOFF
Item | Authoritative instruction
Phase | Phase 2 of 10. Target: Day 1 — 20-Sep-2026, 09:00–10:00.
Prerequisite | Phase 1 must be COMPLETE. Before coding, read the Phase 1 artifacts from the current repository/workspace: agents.md, all context files, progress-tracker.md, architecture-context.md, requirements/decision records and Phase 2 handoff.
Mission | Turn the approved Phase 1 architecture into a clean, runnable application foundation and development environment. Do not implement authentication/business modules yet; those belong to later phases.
Autonomous mode | Execute the phase in order. Plan each unit, implement it, verify it, update progress, then continue. Stop only at a Human Gate. Never pretend a connection/configuration is complete.
Human assistance | If GitHub/repository access, Google/Firebase project access, OAuth, environment secrets, or any console action is required, STOP and tell the user exactly what to do. Never request passwords/private keys/tokens in chat.
Resume | After the user performs the requested action, they should reply exactly: DONE — RESUME PHASE 2. Re-check the dependency and resume from the paused step; do not restart completed work.
Scope boundary | Phase 2 establishes the foundation. Do not implement login/roles, Projects, Finance, HR, salary, reimbursement, MOM, or full builder behavior. Only install/prepare the selected editor integration boundary if Phase 1 architecture requires it.
Cost invariant | Maintain ₹0 additional cost beyond existing Google AI Pro. Do not enable billing or add paid SaaS. If a selected setup asks for billing, STOP and invoke the Human Gate.
Expected result | A clean app runs locally/inside the AI Studio environment, source control is established or ready, dependencies are installed, environment configuration is documented, UI/design primitives and application shell are ready, the selected visual-editor package is integrated at the foundation boundary if approved, and Phase 3 can begin without redoing setup.

## Autonomous Control
PHASE 2 AUTONOMOUS EXECUTION CONTROL
Step | Time | Unit | AI action | Human gate? | STOP trigger | Resume phrase | Verification | Output | Status
P2-01 | 09:00–09:05 | Restore Phase 1 context | Read agents.md, all context files, progress tracker, Phase 1 handoff and architecture decisions. Inspect workspace/repo state. | No | Required Phase 1 artifact is missing or contradictory. | RESUME PHASE 2 after missing artifact is restored. | AI can state current architecture, scope, cost invariant and exact next unit without guessing. | Context restored | Not Started
P2-02 | 09:05–09:10 | Inspect existing project | Inspect current files, package manager, runtime, existing app status and any prior generated code. Do not overwrite useful work blindly. | No | Workspace cannot be read/modified or existing state is inconsistent in a way that needs user decision. | DONE — RESUME PHASE 2 | Inventory recorded; no destructive change made. | Foundation inventory | Not Started
P2-03 | 09:10–09:18 | Initialize/clean foundation | Create or clean the app foundation using the Phase 1-selected runtime. Establish predictable folder structure and remove irrelevant boilerplate. | Only if environment/repo setup requires human connection. | AI cannot create/modify workspace. | DONE — RESUME PHASE 2 | App starts; source structure matches architecture context. | Clean app foundation | Not Started
P2-04 | 09:18–09:25 | Install core tooling | Install React/TypeScript/runtime dependencies, Tailwind/shadcn if selected, lint/type/build tooling, and approved open-source editor package/dependencies. Do not add unrelated packages. | No unless package installation requires unavailable permission. | Package install blocked or package/license is unclear. | DONE — RESUME PHASE 2 | Install completes; dependency list is documented. | package.json/lockfile | Not Started
P2-05 | 09:25–09:32 | Environment configuration | Create safe env template, environment validation and documentation. Add placeholders, never secrets in source. Configure only services approved by Phase 1. | Yes if user must create/copy a secret or OAuth configuration. | Secret/OAuth/project ID is required and AI cannot obtain it through authorized UI. | DONE — RESUME PHASE 2 | Env validation works; secrets are not committed. | .env.example + env docs | Not Started
P2-06 | 09:32–09:40 | UI primitives + application shell | Implement design tokens, base typography, reusable UI primitives, top navigation/sidebar/container/dialog patterns, responsive shell. | No | Phase 1 UI decision is incomplete or requires user choice. | RESUME PHASE 2 | Build/lint/type pass; shell renders at desktop/mobile widths. | UI foundation | Not Started
P2-07 | 09:40–09:45 | Editor foundation boundary | Integrate/import the selected mature visual-editor engine at the architecture boundary only. Establish editor host, lifecycle, asset/page-state interfaces; do not build full builder features yet. | Only if package/API/license/configuration needs a human decision. | Selected engine cannot be installed/used as planned without a decision or paid dependency. | RESUME PHASE 2 | Editor host mounts and can initialize/destroy cleanly; no business features added. | Editor foundation | Not Started
P2-08 | 09:45–09:50 | Git/GitHub checkpoint | Initialize Git if needed, create baseline branch/commit, connect GitHub if approved and available. | Yes if GitHub OAuth/remote connection requires user action. | AI cannot authorize/connect repository. | DONE — RESUME PHASE 2 | Remote/branch/commit verified if connection is required; otherwise local Git baseline exists. | Baseline commit | Not Started
P2-09 | 09:50–09:55 | Foundation verification | Run build, type check, lint and local runtime smoke test. Fix only foundation issues using focused corrections. | No | A human-only environmental problem blocks verification. | DONE — RESUME PHASE 2 | All applicable checks pass. | Verification report | Not Started
P2-10 | 09:55–10:00 | Phase 2 completion + Phase 3 handoff | Update progress tracker, record files/decisions, freeze foundation, write exact Phase 3 starting point. | No | Any P0 gate failed. | Continue until gate passes. | 100% Phase 2 acceptance criteria pass. | Phase 3 handoff | Not Started

## Foundation Checklist
PHASE 2 FOUNDATION IMPLEMENTATION CHECKLIST
ID | Area | Exact work | Must exist after unit | Dependencies | Out of scope | Verification | Priority | Status
FND-01 | Repository | Inspect/create repository and preserve Phase 1 artifacts. | Working project repo with context files preserved. | Phase 1 | Business modules | Repo opens and context intact. | P0 | Not Started
FND-02 | Runtime | Create/clean the selected application runtime and scripts. | dev/build/lint/type scripts. | Phase 1 architecture | Auth/business logic | Commands execute successfully. | P0 | Not Started
FND-03 | TypeScript | Strict, predictable TypeScript configuration and path conventions. | tsconfig and source conventions. | Runtime | Feature models | Type check passes. | P0 | Not Started
FND-04 | UI system | Install/configure Tailwind and shadcn/ui or the exact Phase 1-approved equivalent; establish design tokens. | Reusable primitives and tokens. | Phase 1 UI context | Feature-specific UI | Import/render test passes. | P0 | Not Started
FND-05 | Icons/utilities | Add approved icon library and class-name/style utilities only if Phase 1 selected them. | Shared utilities. | UI system | Unrelated libraries | Build/lint pass. | P1 | Not Started
FND-06 | Application shell | Create master shell: top navigation, sidebar, content area, responsive container, page header, basic dialog/toast/error patterns. | Reusable shell ready for modules. | UI system | Deep module screens | Desktop/mobile smoke test. | P0 | Not Started
FND-07 | Error/loading boundaries | Create consistent loading, error, empty and not-found patterns. | Reusable boundaries. | Runtime | Business-specific error messages | Smoke test. | P0 | Not Started
FND-08 | Environment | Create .env.example, runtime env validation and secret-handling documentation. | Safe configuration contract. | Architecture decisions | Real secrets in repo | Missing-env failure is actionable. | P0 | Not Started
FND-09 | Editor package | Install/configure the Phase 1-selected mature editor engine and create a minimal host adapter. | Editor host component/service. | Architecture decision | Full builder feature set | Editor initializes without error. | P0 | Not Started
FND-10 | Editor state interface | Define the application-facing interfaces for page content/editor state/assets without implementing database persistence yet. | Stable interfaces for later phases. | Editor engine | Full persistence/permissions | Type/build checks. | P1 | Not Started
FND-11 | Security baseline | Establish secure headers/config patterns and basic server/client boundary conventions appropriate to the runtime. | Foundation security conventions. | Runtime | Full authorization | Static/config review. | P1 | Not Started
FND-12 | Documentation | Update code standards and AI workflow rules if implementation reveals concrete decisions; record them in context. | Context stays authoritative. | All foundation work | Future features | Context matches code. | P0 | Not Started

## Dependency & Cost Gate
PHASE 2 — DEPENDENCY, LICENSE & COST GATE
Check | Rule | AI action | STOP condition | Human action | Resume phrase | Verification | Status
AI Studio access | Use existing Google AI Pro/AI Studio; no new AI subscription. | Proceed with available environment. | AI requests paid upgrade for Phase 2 execution. | User decides whether to approve or redesign. | RESUME PHASE 2 | AI Studio environment is usable. | Not Started
Editor license | Use mature open-source editor core or an approved free alternative. | Inspect package license and docs before adoption. | License/cost is unclear or paid dependency is mandatory. | User approves or AI selects documented free alternative. | RESUME PHASE 2 | License recorded in dependency notes. | Not Started
Firebase | Use only services approved in Phase 1. Do not enable Blaze automatically. | Configure only free/no-cost route where applicable. | Console asks for billing for a required Phase 2 task. | User explicitly approves billing or requests redesign. | REDESIGN — RESUME PHASE 2 / APPROVE BILLING — RESUME PHASE 2 | No billing enabled unless explicitly approved. | Not Started
Google Drive/Gmail | OAuth scopes must be minimal and authorized securely. | Prepare integration boundary only if Phase 2 requires it. | Consent is required and unavailable to AI. | User completes OAuth in UI. | DONE — RESUME PHASE 2 | Scope granted and test access verified. | Not Started
npm dependencies | No unnecessary dependency sprawl. | Install only specified/justified packages. | Package has unclear license or unexpected paid service. | User decides or AI replaces it. | RESUME PHASE 2 | package/lockfile reviewed. | Not Started

## Human Gates
PHASE 2 — HUMAN ASSISTANCE GATES
Gate | When AI must stop | Exact message structure | User action | Resume phrase | AI must verify | Do not do | Status
HG2-01 GitHub | Repository/remote/OAuth cannot be connected autonomously. | I need you to connect GitHub at [location]. Target: [repo/account]. Do not paste credentials. Success: [observable state]. | Connect/authorize in UI. | DONE — RESUME PHASE 2 | Check remote/branch/access. | Never ask for password/token in chat. | Pending
HG2-02 Google/Firebase project | A required project/OAuth setting can only be completed in console. | I need one console action: [exact steps]. No billing should be enabled. Success: [state]. | Complete console setup. | DONE — RESUME PHASE 2 | Inspect configuration. | Never enable billing silently. | Pending
HG2-03 Secret/config | A secret/API credential is required. | I need you to add [secret name] through the secure environment/secret UI. Do not paste it in chat. | Add secret securely. | DONE — RESUME PHASE 2 | Check only presence/availability, never print secret. | Never expose secret. | Pending
HG2-04 Cost | A service requires payment/billing. | This dependency requests billing: [service]. I have stopped and have not enabled it. Choose redesign or explicit approval. | Choose path. | REDESIGN — RESUME PHASE 2 / APPROVE BILLING — RESUME PHASE 2 | Re-evaluate selected architecture. | Never enable billing autonomously. | Pending
HG2-05 Tool choice | Selected editor/package is unavailable, incompatible or paid. | [Tool] cannot satisfy [capability] under current constraints. Here are the smallest alternatives. | Approve alternative if needed. | RESUME PHASE 2 | Update architecture context before implementation. | Do not silently substitute. | Pending

## Verification Gate
PHASE 2 — VERIFICATION & DEFINITION OF DONE
ID | Verification | Expected result | How AI checks | Failure response | P0/P1 | Status | Evidence
V2-01 | Project starts | Application starts without fatal runtime error. | Run configured dev/start command and inspect output. | Focused fix; rerun. | P0 | Not Started
V2-02 | Build | Production build completes. | Run build. | Focused fix. | P0 | Not Started
V2-03 | Type check | No TypeScript errors. | Run type check. | Focused fix. | P0 | Not Started
V2-04 | Lint | Lint passes or only documented non-blocking warnings remain. | Run lint. | Focused fix. | P0 | Not Started
V2-05 | Shell | Master shell renders and is responsive. | Open app at desktop/tablet/mobile widths. | Focused UI fix. | P0 | Not Started
V2-06 | Editor host | Selected visual editor initializes and can be destroyed/reloaded without fatal error. | Open editor route/component and inspect console. | Focused integration fix. | P0 | Not Started
V2-07 | No scope leakage | No Projects/Finance/HR/Auth business implementation was added beyond foundation boundaries. | Review diff and feature map. | Revert/narrow change. | P0 | Not Started
V2-08 | Cost | No mandatory paid service or billing dependency introduced. | Review package/config/service list. | Stop and redesign or ask user. | P0 | Not Started
V2-09 | Secrets | No secrets committed or printed. | Scan repository/config and logs. | Remove/rotate if necessary; never expose secret. | P0 | Not Started
V2-10 | Context sync | Context files accurately describe current foundation. | Compare docs with implementation. | Update context. | P0 | Not Started
V2-11 | Git baseline | Baseline commit exists; remote connected if authorized. | Inspect git status/log/remote. | Human gate if connection blocked. | P1 | Not Started
V2-12 | Phase handoff | Phase 3 exact starting point is documented. | Read progress tracker/handoff. | Update tracker. | P0 | Not Started

## Context Updates
PHASE 2 — CONTEXT FILES THAT AI MUST UPDATE
File | Phase 2 update | Must reflect | Do not | Verification | Status | Notes
agents.md | Add Phase 2 execution protocol and current project entry point. | How to start/resume; current authoritative files; stop/resume rules. | Do not erase Phase 1 rules. | Read from top and confirm references. | Not Started
project-overview.md | Record foundation status and exact next phase. | Current product, scope, scale and Phase 3 next step. | Do not change product scope silently. | Matches requirements. | Not Started
architecture-context.md | Record actual runtime, packages, boundaries and final foundation choices. | What was actually implemented, not merely planned. | Do not leave stale architecture choices. | Compare to code/config. | Not Started
code-standards.md | Record conventions discovered/established in foundation. | File structure, naming, component/API patterns, validation and styling. | Do not invent rules not used. | Review representative files. | Not Started
ai-workflow-rules.md | Record any Phase 2-specific operational rules. | Stop/resume, dependency gates, testing commands, protected foundation files. | Do not weaken verification. | AI can follow without chat context. | Not Started
ui-context.md | Record actual design tokens/primitives/shell conventions. | Colors/tokens, spacing, typography, component rules, responsive shell. | Do not hardcode unrelated styling. | Shell matches context. | Not Started
progress-tracker.md | Mark Phase 2 units complete/in progress and set Phase 3 as next. | Exact changes, decisions, human gates, verification and next unit. | Do not mark incomplete work complete. | Tracker alone can reconstruct current state. | Not Started
feature-specs/README.md | Add Phase 3+ dependency map if not already present. | Phase 3 auth/users/roles is next. | Do not implement Phase 3. | Roadmap matches 10-phase plan. | Not Started

## AI Studio Master Prompt
COPY-PASTE / ATTACH THIS PHASE 2 EXECUTION CONTRACT TO GOOGLE AI STUDIO
MASTER EXECUTION PROMPT
You are the implementation agent for PHASE 2 of this application. AUTHORITATIVE INPUT 1. This Phase 2 workbook is the execution contract. 2. Phase 1 artifacts already completed in the repository/workspace are authoritative for product requirements and architecture. 3. The uploaded AI-Ready App Building Playbook is the methodology reference. MISSION Complete ONLY Phase 2: AI Context, Project Foundation & Development Environment. Target time: Day 1 — 20-Sep-2026, 09:00–10:00. Do not begin Phase 3 authentication/users/roles until the Phase 2 Verification Gate passes. FIRST ACTION Read this workbook completely. Then inspect the project/workspace. Then read: - agents.md - context/project-overview.md - context/architecture-context.md - context/code-standards.md - context/ai-workflow-rules.md - context/ui-context.md - context/progress-tracker.md - context/feature-specs/README.md and the Phase 1 handoff/decision records if present. EXECUTION RULES 1. Execute Autonomous Control P2-01 through P2-10 in order. 2. Before each unit, create a short implementation plan internally and stay within that unit's boundary. 3. Do not silently invent requirements. 4. Do not implement Phase 3+ business functionality. 5. Preserve the full visual website-builder requirement. Phase 2 may install/configure the selected mature editor engine and create its host/adapter boundary, but full builder behavior belongs to Phases 5 and 8. 6. Use the Phase 1-selected runtime and architecture. If implementation reveals a real contradiction, update the authoritative architecture context before proceeding. 7. Maintain the ₹0 additional-cost constraint. Do not enable billing, add paid SaaS, or add paid editor plugins without explicit user approval. 8. Never paste or request passwords, private keys, access tokens, or secrets in chat. Use secure environment/secret UI. 9. If human assistance is genuinely required, STOP immediately. Use the Human Gates format: - exact action required - exact location/UI - why it is needed - expected success state - what you have already completed - exact resume phrase 10. When the user says “DONE — RESUME PHASE 2”, verify the dependency yourself, then continue from the exact paused step. 11. Never restart Phase 2 because of a human gate. 12. For errors, use focused correction: exact error → smallest affected boundary → current provider/framework documentation if needed → smallest fix → rerun verification. 13. Update progress-tracker.md after each meaningful completed unit. 14. Keep context files synchronized with actual implementation. FOUNDATION SCOPE Implement only: - project/runtime foundation - package/dependency setup - TypeScript/build/lint/type checks - environment template and safe configuration - UI/design primitives - application shell - loading/error/empty/not-found boundaries - approved visual-editor package/host boundary - Git baseline/remote setup where available - foundation documentation/context synchronization DO NOT IMPLEMENT YET - authentication - user registration/login screens - role enforcement - Projects CRUD - Finance - HR - salary - reimbursement - investments - MOM/email workflow - full website-builder feature set - production deployment VERIFICATION Run every applicable check in Verification Gate. Do not claim completion unless: - app starts - build passes - type check passes - lint passes or documented non-blocking warnings are acceptable - shell renders - editor host initializes - no secrets are exposed - no paid dependency/billing requirement was introduced - no Phase 3+ business implementation leaked into scope - context files match the code - progress tracker identifies Phase 3 as next PHASE 2 COMPLETION Only after every P0 criterion passes: 1. Mark Phase 2 COMPLETE. 2. Record exact files changed. 3. Record dependencies installed. 4. Record human gates completed. 5. Record unresolved questions, if any. 6. Write the Phase 3 handoff: “Phase 3 — Authentication, Users, Roles & Permissions” 7. Stop and report completion. Do not start Phase 3 automatically.

## Phase 3 Handoff
PHASE 2 OUTPUT → PHASE 3 HANDOFF
Handoff | Required output | Content | Phase 3 uses it for | Completion test | Status | Evidence | Notes
Foundation | Clean runnable app | Runtime, folder structure, scripts, dependencies. | Auth integration. | Phase 3 can modify without rebuilding foundation. | Not Started
UI shell | Reusable master shell | Navigation, layout, tokens, primitives, loading/error patterns. | Login and role-aware navigation. | Auth UI fits existing shell. | Not Started
Environment | Safe env contract | Variables, validation, docs, no secrets committed. | Auth/Google/Firebase configuration. | Missing env produces actionable error. | Not Started
Editor boundary | Selected editor host | Editor package, initialization adapter and state interfaces. | Later builder phases. | Editor can mount and unload cleanly. | Not Started
Git | Baseline history | Commit/branch/remote state. | All later feature units. | Rollback point exists. | Not Started
Context | Updated durable context | All seven context files + feature roadmap. | All future AI sessions. | AI can resume from files. | Not Started
Verification | Foundation evidence | Build/type/lint/runtime/editor checks. | Prevents broken baseline. | All P0 checks pass. | Not Started
Next unit | Exact Phase 3 starting point | Authentication → users → roles → permissions. | Phase 3 execution. | No ambiguity about next task. | Not Started

## Playbook Alignment
PHASE 2 ALIGNMENT TO THE APP-BUILDING PLAYBOOK
Principle | Phase 2 implementation | Why | Workbook section | Verification | Status | Source note
Clean foundation before features | Runtime, UI primitives, shell, env and checks are established before business features. | The playbook explicitly separates foundation from feature execution. | Foundation Checklist | Build/type/lint/runtime pass. | Not Started | Source methodology
Context remains authoritative | Context files are updated to reflect the actual foundation. | The playbook uses durable context to prevent AI drift. | Context Updates | Docs match implementation. | Not Started | Source methodology
One feature/unit at a time | Phase 2 is decomposed into P2-01…P2-10. | The playbook says to split work into small verifiable units. | Autonomous Control | Each unit has a completion condition. | Not Started | Source methodology
Provider-native integration | Use the selected editor/runtime capabilities rather than inventing infrastructure. | The playbook emphasizes established provider/library patterns. | Foundation + editor boundary | Editor initializes with documented integration. | Not Started | Source methodology
Focused correction | Foundation failures are corrected at the smallest boundary. | The playbook describes exact-error focused correction. | Verification Gate | Failed check → focused fix → rerun. | Not Started | Source methodology
Progress persistence | Progress tracker records current state and Phase 3 next unit. | The playbook requires progress state for resumption. | Context Updates + Handoff | Tracker reconstructs state. | Not Started | Source methodology