## START HERE
PHASE 3 — AUTHENTICATION, USERS, ROLES & PERMISSIONS ¦ AUTONOMOUS GOOGLE AI STUDIO BUILD
Purpose | Upload this workbook to Google AI Studio after Phase 2 is complete. The AI must execute Phase 3 autonomously, stop only when a genuine human action is required, explain the exact action, and resume from the exact paused unit after the user confirms completion.
Phase window | Day 1 — 20-Sep-2026 ¦ 10:00–11:00
Mission | Implement secure authentication, employee identity, Admin/Standard User roles, project/page permissions, protected routes/UI, server-side authorization, and an auditable admin bootstrap path.
Hard cost constraint | ₹0 additional cost beyond the existing Google AI Pro subscription. Do not introduce paid authentication, RBAC products, email providers, or infrastructure.
Required predecessor | Phase 1 approved architecture + Phase 2 runnable foundation/context. If either is missing or inconsistent, STOP and request the specific human action needed.
Explicit boundary | Do NOT implement Finance, HR salary, reimbursement, investments, MOM/email automation, full project module, or the full visual-builder feature set in this phase. Only build the identity/access foundation those later phases depend on.
Autonomous rule | Read the entire workbook first. Inspect the actual repository before editing. Plan each unit, implement one unit, verify it, update progress, then continue. Never claim completion without evidence.
Human gate rule | If OAuth/Firebase/GitHub/configuration/secret/admin-bootstrap action requires the human, STOP immediately. Give exact UI/action steps without requesting passwords or private keys in chat. Wait for: DONE — RESUME PHASE 3.
Resume rule | On resume, re-read the current progress state, verify the human action actually succeeded, then continue from the exact incomplete unit. Do not restart completed units.
Phase completion | All P0 acceptance criteria pass, authorization is enforced server-side, unauthorized tests fail safely, no secrets are committed, context/progress is updated, and Phase 4 handoff is written.

## Autonomous Control
AUTONOMOUS EXECUTION CONTROL — PHASE 3
Unit | Execution Stage | AI Must Do | Verification Before Continue | Human Gate? | Status | Resume Behavior
P3-01 | Restore context | Read Phase 1 architecture, master requirements, Permissions Matrix, Phase 2 context/progress, repo state and this workbook. Confirm predecessor is complete. | Required context files exist; repo matches Phase 2 handoff; no contradictory auth architecture. | No | NOT STARTED | Continue to P3-02 only after context consistency check.
P3-02 | Inspect current foundation | Inspect auth-ready shell, env handling, routes, API/server boundaries, dependency versions and existing tests. Do not assume file paths. | Write an implementation map tied to actual files. Identify missing auth boundary. | No | NOT STARTED | Continue after map is recorded.
P3-03 | Configure authentication | Implement Firebase Authentication / Google identity using the Phase 1 selected approach. Configure client and server verification boundaries. | Login/logout/session persistence works in development; invalid identity rejected. | Possible | NOT STARTED | If console/OAuth action is needed, stop with exact steps; resume after confirmation.
P3-04 | Employee identity model | Create authoritative employee/user profile model and identity linkage. Store only required business identity fields. | Authenticated user resolves to exactly one permitted employee profile or controlled onboarding state. | No | NOT STARTED | Continue after identity tests pass.
P3-05 | Role model | Implement Admin and Standard User roles; keep role values centralized and type-safe. | Role is persisted and cannot be changed by client-only payload manipulation. | No | NOT STARTED | Continue after server-side role test passes.
P3-06 | Permission model | Implement project/page/module permissions needed by the master matrix: project membership/editor access, employee self-access, admin-only sensitive areas. | Permissions are evaluated from authoritative server-side data, not UI visibility. | No | NOT STARTED | Continue after positive/negative permission tests pass.
P3-07 | Protected routes & UI | Protect app routes and navigation based on authenticated identity/permissions. UI may hide inaccessible controls but cannot be the only security layer. | Direct URL access to restricted UI is blocked/redirected safely; authorized routes load. | No | NOT STARTED | Continue after route matrix test.
P3-08 | Server/API authorization | Enforce authorization at every relevant mutation/query boundary created in this phase. Prevent IDOR/cross-user profile access and role escalation. | Direct requests with forged user IDs/roles are denied; authorized requests succeed. | No | NOT STARTED | Continue only when denial tests are demonstrated.
P3-09 | Admin bootstrap & onboarding gate | Implement a safe first-admin bootstrap mechanism and controlled handling of users without an approved employee profile. | No accidental public admin path; first admin process is explicit and auditable. | Possible | NOT STARTED | If human must identify initial admin or configure provider, stop and request it.
P3-10 | Security regression + context | Run auth/permission tests, build/type/lint, update context/progress, document decisions and hand off Phase 4. | All P0 verification criteria pass; no secrets; progress and handoff current. | No | NOT STARTED | If all pass, mark PHASE 3 COMPLETE and hand off Phase 4.

## Requirements Freeze
PHASE 3 REQUIREMENTS FREEZE — AUTHENTICATION, USERS, ROLES & PERMISSIONS
ID | Source Requirement | Phase 3 Interpretation | Implementation Requirement | Access/Security Rule | Acceptance Evidence | Priority
P3-R01 | Master website has Projects / Finance / HR. | Identity layer must support all three modules without implementing their business logic yet. | Authenticated application shell with extensible authorization context. | Unauthenticated users cannot enter protected application. | Login → protected shell → logout evidence. | P0
P3-R02 | Anyone with access can edit permitted content. | Permission system must distinguish authentication from authorization and support configurable access. | Permission evaluation service/model; do not hardcode all users as editors. | Access is granted by role + resource permission/membership. | User A allowed; User B denied; server confirms both. | P0
P3-R03 | Some pages are admin-only. | Sensitive modules must be represented in authorization policy. | Admin role + protected sensitive route/API policy. | Salary and other sensitive areas remain Admin-only by default. | Direct URL/API access by Standard User denied. | P0
P3-R04 | Employees record their own OOP expenses. | Employee self-access must be represented without exposing other employees' claims. | Self ownership rule/policy primitive. | Employee can access own record; cannot access another employee's record by changing ID. | IDOR negative test. | P0
P3-R05 | Permissions Matrix requires server enforcement. | UI hiding is insufficient. | Central authorization helper/middleware/policy boundary. | Every protected query/mutation checks authoritative identity + role/resource access. | Forged request tests denied. | P0
P3-R06 | Admin salary sheet. | Phase 3 only establishes the Admin-only permission boundary; salary implementation belongs later. | Permission key/route policy for salary. | Standard User denied at route and server/API layer. | Negative test stub or policy test. | P0
P3-R07 | Project create/edit/delete configurable. | Phase 3 establishes configurable capability model; Projects CRUD belongs Phase 5. | Permission keys for project creation/edit/delete/member/editor. | No blanket assumption that every Standard User can create/delete. | Policy unit tests. | P0
P3-R08 | Cost target ₹0 additional. | Use Firebase Auth / Google identity as selected; no paid RBAC provider. | No paid auth/authorization service. | No unexpected billing dependency. | Dependency/cost audit. | P0
P3-R09 | Human gates must pause/resume. | External console/OAuth/admin bootstrap cannot be faked. | Checkpoint state + exact resume token phrase. | Never ask for secrets in chat. | Human gate simulation/test. | P0

## Identity & Role Model
IDENTITY, USER, EMPLOYEE & ROLE MODEL
Entity/Concept | Field/Key | Purpose | Rules | Security Notes | Verification
Authenticated Identity | providerUserId | Stable provider identity reference. | Must be unique; never trust a client-supplied identity ID for authorization. | Use verified server session/token identity. | Two sessions resolve correctly.
User Profile | userId | Application-level user record. | Exactly one authoritative profile per identity. | Client cannot change own role/status. | Role escalation denied.
Employee Profile | employeeId | Business employee identity used by HR/expense modules. | Must be linkable to a user profile without exposing unnecessary sensitive data. | Employee ownership checks use authoritative employeeId. | Self-access test passes.
Role | role | Coarse authorization role. | Initial roles: ADMIN, STANDARD_USER. Keep centralized and extensible. | Role changes require trusted admin/server operation. | Forged role rejected.
Account Status | status | Controls active/inactive/invited/pending state. | Only active/approved users enter protected app. | Inactive users denied even with valid identity. | Status denial test.
Project Membership | projectId + userId | Resource-level project access. | Membership and editor capability are separate concepts if needed. | Server checks membership/editor rights. | Member vs non-member test.
Permission Key | permission | Fine-grained capability. | Examples: PROJECT_CREATE, PROJECT_EDIT, PROJECT_DELETE, SALARY_READ, EMPLOYEE_SELF_READ, OOP_SELF_WRITE. | Sensitive permissions default deny. | Policy tests.
Admin Bootstrap | bootstrap state | Safe initial admin establishment. | Must be explicit, one-time or controlled; no public self-admin endpoint. | Never accept role=ADMIN from signup payload. | Bootstrap test/audit.

## Phase 3 Permission Matrix
PHASE 3 PERMISSION MATRIX — IMPLEMENTATION BASELINE
Capability | Admin | Standard User | Employee Self | Server Enforcement | Default Rule | Negative Test
Dashboard | Read/write | Read/write permitted modules | Read own | YES | Authenticated only | Anonymous direct route
Create project | YES | Configurable | NO | YES | Admin yes; Standard configurable | Standard without permission
Edit project | YES | Yes if member/editor | NO | YES | Resource permission | Non-member edit
Delete project | YES | Configurable | NO | YES | Admin or explicit permission | Unauthorized delete
Event date | YES | Yes if editor | NO | YES | Project permission | Read-only user mutation
Checklist Excel | YES | Yes if editor | NO | YES | Project permission | Non-member file access
Expense Excel | YES | Yes if editor | NO | YES | Project permission | Non-member file access
Budget allocations | YES | Yes if permitted | NO | YES | Explicit permission | Unauthorized mutation
Own OOP claim | YES | YES | YES | YES | Owner or admin | Change employeeId to another
Other employee OOP | YES | Configurable/no by default | NO | YES | Admin or explicit permission | Cross-user read
Salary | YES | NO | NO | YES | Admin only | Direct API/route
Salary report | YES | NO | NO | YES | Admin only | Direct API/route
Investments | YES | NO by default | NO | YES | Admin only | Direct API/route
User role change | YES | NO | NO | YES | Admin-only trusted operation | Self role escalation
Admin bootstrap | Controlled | NO | NO | YES | Explicit bootstrap only | Public admin creation

## Human Gates
HUMAN INTERVENTION GATES — STOP / INSTRUCT / RESUME
Gate ID | When Triggered | AI Must STOP Because | Exact User Action to Request | What AI Verifies After Resume | Resume Phrase
HG3-01 | Firebase/Google Auth console setup required. | External account/project configuration cannot be safely completed autonomously. | Open the Firebase/Google console for the project, enable the selected authentication provider, configure the required authorized origins/redirect settings, then return here and say DONE — RESUME PHASE 3. | Re-check configuration, run provider/session test, confirm no secret is exposed. | DONE — RESUME PHASE 3
HG3-02 | Environment variables/secrets required. | AI must not ask the user to paste private credentials into chat. | Add required values through the project's secure environment/secrets mechanism; do not paste private keys into chat; then say DONE — RESUME PHASE 3. | Check variables exist without printing secret values; run auth config validation. | DONE — RESUME PHASE 3
HG3-03 | Initial admin identity must be selected. | The AI cannot invent who should control company-wide administration. | User specifies the approved initial admin account through the secure project/configuration mechanism, then says DONE — RESUME PHASE 3. | Verify exactly one intended bootstrap path/identity and test admin-only access. | DONE — RESUME PHASE 3
HG3-04 | OAuth consent/verification or provider warning blocks testing. | External provider requires human approval. | Complete the provider's displayed approval/consent steps; do not provide credentials in chat; then resume. | Repeat login/session test and record result. | DONE — RESUME PHASE 3
HG3-05 | Architecture conflict discovered. | Proceeding would silently change Phase 1/2 decisions. | AI must report the exact conflict, affected files/requirements, and proposed choices; wait for user decision. | Verify chosen decision is recorded in context before implementation. | DONE — RESUME PHASE 3

## Verification Gate
PHASE 3 VERIFICATION GATE — DO NOT MARK COMPLETE WITHOUT EVIDENCE
Test ID | Verification | Expected Result | Evidence AI Must Record | Priority | If Failed
V3-01 | Anonymous access to protected app route | Blocked/redirected; no protected data returned. | Test result + route/API observed. | P0 | Focused correction; retest.
V3-02 | Valid authentication | Session established and protected shell loads. | Auth/session test. | P0 | Fix auth boundary.
V3-03 | Logout/session invalidation | Protected route/API becomes inaccessible after logout/session invalidation. | Negative test. | P0 | Fix session handling.
V3-04 | Standard user accessing Admin-only salary | Denied at UI and server/API boundary. | Direct request denial evidence. | P0 | Fix server policy first.
V3-05 | Standard user changing own role to ADMIN | Denied; authoritative role unchanged. | Forged mutation test. | P0 | Fix role mutation boundary.
V3-06 | Employee A reading Employee B OOP | Denied unless explicit authorized permission exists. | IDOR/cross-user test. | P0 | Fix ownership check.
V3-07 | Project member vs non-member edit | Member/editor succeeds according to permission; non-member denied. | Two-user resource test. | P0 | Fix resource authorization.
V3-08 | Project create permission | Admin succeeds; Standard User follows configured permission. | Positive/negative policy tests. | P0 | Fix capability policy.
V3-09 | Inactive/unapproved account | Cannot access protected app even with valid identity. | Status test. | P0 | Fix account gate.
V3-10 | Admin bootstrap | Only intended bootstrap path creates/assigns admin; no public admin signup. | Bootstrap test + audit record. | P0 | Stop and correct security boundary.
V3-11 | Secret hygiene | No private credentials committed or printed in logs/chat. | Repository/config scan. | P0 | Remove secret and rotate if exposed.
V3-12 | Build/type/lint | All required checks pass. | Command results. | P0 | Focused correction.
V3-13 | Regression of Phase 2 shell | Foundation still starts and renders correctly. | Smoke test. | P0 | Correct regression.
V3-14 | Cost/dependency audit | No paid auth/RBAC service introduced. | Dependency and config audit. | P0 | Remove/replace dependency.
V3-15 | Context/progress sync | All context files and progress tracker reflect Phase 3 reality. | File diff/checklist. | P0 | Update context before completion.

## Context Updates
MANDATORY CONTEXT & PROGRESS UPDATES
Artifact | What Phase 3 Must Update | Required Content | Completion Check
agents.md | Add/confirm auth and authorization execution rules. | Identity verification, server-side authorization, human-gate behavior, secret handling, focused correction loop. | File exists and matches actual implementation.
project-overview.md | Record Phase 3 completion and user/role scope. | Authentication, employee identity, Admin/Standard User, protected modules. | No stale Phase 2-only status.
architecture-context.md | Record authoritative auth/data boundaries. | Provider, session verification, user/employee linkage, policy boundary, admin bootstrap. | Matches code.
code-standards.md | Record security coding conventions. | No client-trusted role, no insecure direct object access, central authorization helpers. | Matches tests.
ai-workflow-rules.md | Record Phase 3 resume/verification behavior. | Stop at human gates; verify after resume; never skip negative tests. | Matches workbook.
ui-context.md | Record protected navigation conventions. | Hide inaccessible controls but never rely on UI-only authorization. | Matches implementation.
progress-tracker.md | Mark P3 units with status/evidence and Phase 4 next action. | Completed units, blocked gates, test evidence, exact next unit. | Current and resumable.
feature-specs/README.md | Reference identity/permissions specs if repository uses feature specs. | Scope and dependency map for later modules. | No contradiction.

## Dependency & Cost Gate
DEPENDENCY / COST / SECURITY GATE
Check | Required Choice | AI Must Verify | Forbidden Without Explicit Approval | Status
Authentication | Firebase Auth / Google identity selected in Phase 1 | No paid auth provider added; configuration matches architecture. | Clerk/Auth0/paid RBAC substitution | NOT CHECKED
Authorization | Application-owned policy layer | No third-party paid authorization dependency required. | Paid policy engine | NOT CHECKED
Database dependency | Phase 1/2 selected backend | Auth model integrates with existing backend; no parallel database introduced. | New paid database | NOT CHECKED
Secrets | Secure environment/config mechanism | No private key/password/token in source or chat. | Hardcoded secrets | NOT CHECKED
Packages | Open-source/free packages only | Dependency audit has no unexpected paid runtime license. | Paid visual/auth plugin | NOT CHECKED
Billing | No billing request required for Phase 3 unless external console explicitly blocks required setup | AI must stop rather than silently enabling paid services. | Enable billing as a workaround | NOT CHECKED

## Completion & Phase 4 Handoff
PHASE 3 COMPLETION GATE + PHASE 4 HANDOFF
Gate | Required State | Evidence | Status
Predecessor integrity | Phase 2 foundation still works. | Build/smoke evidence. | NOT CHECKED
Authentication | Users can authenticate and session is verified. | Positive + negative tests. | NOT CHECKED
Identity | Authenticated identity links to controlled user/employee profile. | Identity resolution test. | NOT CHECKED
Roles | ADMIN and STANDARD_USER are authoritative. | Role escalation negative test. | NOT CHECKED
Permissions | Resource/module permissions work and are server-enforced. | Permission matrix tests. | NOT CHECKED
Admin-only boundary | Salary/sensitive routes are denied to Standard User. | Direct route/API denial. | NOT CHECKED
Self-ownership | Employee self-access is enforced. | OOP IDOR test. | NOT CHECKED
Admin bootstrap | Safe and explicit. | Bootstrap evidence. | NOT CHECKED
Security hygiene | No secrets, insecure client trust, or accidental public admin path. | Audit results. | NOT CHECKED
Cost invariant | No additional paid service introduced. | Dependency/cost audit. | NOT CHECKED
Context | All required context/progress artifacts updated. | File checks/diff. | NOT CHECKED
Git checkpoint | Changes committed/available for rollback when Git is configured. | Commit/checkpoint evidence. | NOT CHECKED
Phase 4 trigger | Phase 3 complete; core data/storage/application shell can be implemented next. | Handoff note written. | NOT CHECKED

## Phase 4 Handoff
PHASE 4 HANDOFF — DATABASE, STORAGE, CORE SHELL & MASTER DASHBOARD
Item | Phase 3 Must Hand Off | Phase 4 Uses It For
Authentication | Verified auth/session boundary and current provider configuration. | Protect all data and dashboard routes.
User/employee identity | Authoritative user + employee linkage model. | Employee directory and ownership.
Roles | ADMIN / STANDARD_USER. | Module access.
Permission engine | Central policy/capability evaluation + resource membership hooks. | Projects, Finance, HR and custom pages.
Admin bootstrap | Controlled initial admin mechanism. | Admin-only configuration.
Protected shell | Authenticated navigation/route boundaries. | Master dashboard.
Security tests | Negative authorization test patterns. | Repeat for every new data API.
Context | Updated architecture/code/AI workflow/progress files. | Resume-safe implementation.
Cost invariant | No paid dependency introduced. | Continue ₹0 target architecture.

## Stop Resume Protocol
STOP / RESUME PROTOCOL — MANDATORY
Situation | AI Behavior | User / Resume Behavior
Human action genuinely required | STOP before performing the blocked action. State current unit, why it is blocked, exact UI/configuration action, what not to share, and the resume phrase. | Perform the action outside chat, then reply exactly: DONE — RESUME PHASE 3.
Human says DONE | Re-read progress state. Verify the claimed action; do not trust the confirmation blindly. | No additional confirmation if verification succeeds.
Verification fails after resume | Do not continue downstream. Explain the failing check and give the smallest correction needed. | Perform correction, then resume with the same phrase.
Requirement ambiguity | STOP only if ambiguity materially changes security/architecture. Present the exact conflicting options and wait. | Choose one option; resume.
Tool unavailable | Do not invent a substitute silently. Check whether the Phase 1 fallback was approved. | User approves fallback or restores tool.
Phase complete | Only after all P0 gates pass and handoff is written. | AI reports completion and Phase 4 trigger.

## AI Studio Master Prompt
COPY-READY MASTER PROMPT — UPLOAD WORKBOOK AND EXECUTE PHASE 3
PROMPT | You are the implementation agent for PHASE 3 of an internal company master website.
PROMPT
PROMPT | MISSION
PROMPT | Implement ONLY Authentication, Users, Roles & Permissions, using the approved Phase 1 architecture and the runnable Phase 2 foundation. Execute autonomously. Stop only when a genuine human action is required. After the user completes that action and says “DONE — RESUME PHASE 3”, verify it and continue from the exact paused point.
PROMPT
PROMPT | SOURCE OF TRUTH
PROMPT | 1. This workbook: Phase 3 Authentication, Users, Roles & Permissions — Autonomous.
PROMPT | 2. The approved Phase 1 architecture/context already in the repository.
PROMPT | 3. The Phase 2 foundation/progress state already in the repository.
PROMPT | 4. The master requirements and permissions matrix reflected in this workbook.
PROMPT | Never silently replace those decisions with a different architecture.
PROMPT
PROMPT | FIRST ACTIONS
PROMPT | 1. Read this entire workbook before coding.
PROMPT | 2. Inspect the repository and current branch/state.
PROMPT | 3. Read agents.md, project-overview.md, architecture-context.md, code-standards.md, ai-workflow-rules.md, ui-context.md and progress-tracker.md if present.
PROMPT | 4. Verify Phase 2 completion. If Phase 2 is incomplete, STOP and report the exact missing prerequisite.
PROMPT | 5. Create an execution checklist in progress-tracker.md using P3-01 through P3-10.
PROMPT
PROMPT | EXECUTION LOOP
PROMPT | For each unit:
PROMPT | - inspect actual files;
PROMPT | - plan the smallest implementation;
PROMPT | - implement only that unit;
PROMPT | - run targeted verification;
PROMPT | - correct failures with focused changes;
PROMPT | - update progress;
PROMPT | - then continue.
PROMPT | Do not make speculative broad refactors.
PROMPT
PROMPT | PHASE 3 SCOPE
PROMPT | Implement:
PROMPT | - Firebase Authentication / Google identity according to the approved architecture;
PROMPT | - verified sessions;
PROMPT | - user profile and employee identity linkage;
PROMPT | - ADMIN and STANDARD_USER roles;
PROMPT | - account status/approval state if required by the approved model;
PROMPT | - project/resource permission primitives;
PROMPT | - admin-only sensitive-area policy;
PROMPT | - employee self-ownership policy;
PROMPT | - protected routes/navigation;
PROMPT | - server-side/API/mutation authorization;
PROMPT | - safe admin bootstrap;
PROMPT | - security regression tests;
PROMPT | - context/progress updates;
PROMPT | - Phase 4 handoff.
PROMPT
PROMPT | DO NOT IMPLEMENT
PROMPT | - Finance business logic;
PROMPT | - salary ledger/reporting;
PROMPT | - reimbursement workflow;
PROMPT | - investment ledger;
PROMPT | - MOM/email automation;
PROMPT | - full Projects CRUD;
PROMPT | - full Excel workflows;
PROMPT | - full visual website-builder feature set;
PROMPT | - production deployment.
PROMPT | Only create the authorization primitives needed by later phases.
PROMPT
PROMPT | SECURITY RULES
PROMPT | - Never trust a client-supplied user ID, employee ID, role, permission, or admin flag.
PROMPT | - Resolve authenticated identity from the verified server-side session/token.
PROMPT | - Enforce authorization at server/API/mutation boundaries.
PROMPT | - UI hiding is supplemental, never the security boundary.
PROMPT | - Prevent cross-user access/IDOR.
PROMPT | - Prevent self-role escalation.
PROMPT | - Keep Admin-only sensitive areas denied by default to Standard User.
PROMPT | - Do not create a public “make me admin” endpoint.
PROMPT | - Do not print or request private secrets in chat.
PROMPT | - Never commit credentials.
PROMPT | - Keep custom JavaScript/plugin security decisions for later builder phases; do not weaken this phase to accommodate them.
PROMPT
PROMPT | COST RULE
PROMPT | Maintain the project’s hard ₹0 additional-cost constraint. Use the approved Firebase/Google identity approach and open-source/application-owned authorization. Do not add paid auth/RBAC services. Do not enable billing as a workaround without a human gate and explicit approval.
PROMPT
PROMPT | HUMAN GATES
PROMPT | If Firebase/Google console setup, OAuth configuration, secure environment values, initial admin identity selection, or another genuinely external action is required:
PROMPT | 1. STOP immediately.
PROMPT | 2. State the exact unit and blocker.
PROMPT | 3. Give exact user actions.
PROMPT | 4. Explicitly tell the user not to paste passwords/private keys/tokens into chat.
PROMPT | 5. End with: DONE — RESUME PHASE 3
PROMPT | Do not continue until the user returns with that phrase.
PROMPT | On resume, verify the action before proceeding.
PROMPT
PROMPT | VERIFICATION
PROMPT | You must run all P0 checks in the Verification Gate sheet, including:
PROMPT | - anonymous denial;
PROMPT | - valid authentication;
PROMPT | - logout/session invalidation;
PROMPT | - Standard User denied from Admin-only salary boundary;
PROMPT | - role escalation denied;
PROMPT | - Employee A cannot access Employee B OOP by changing IDs;
PROMPT | - project membership/editor authorization;
PROMPT | - project-create permission behavior;
PROMPT | - inactive/unapproved account denial;
PROMPT | - safe admin bootstrap;
PROMPT | - secret hygiene;
PROMPT | - build/type/lint;
PROMPT | - Phase 2 regression;
PROMPT | - dependency/cost audit;
PROMPT | - context/progress sync.
PROMPT
PROMPT | COMPLETION RULE
PROMPT | Do not declare Phase 3 complete merely because code was written.
PROMPT | Phase 3 is complete only when every P0 acceptance criterion passes, evidence is recorded, context files are updated, progress-tracker.md is current, and Phase 4 handoff is written.
PROMPT
PROMPT | RESUME SAFETY
PROMPT | Never restart completed units unless verification proves they are invalid.
PROMPT | If interrupted, resume from progress-tracker.md and the last verified unit.
PROMPT | If a human gate was previously passed, verify its current state but do not repeat the setup unnecessarily.
PROMPT
PROMPT | FINAL OUTPUT
PROMPT | When complete, report:
PROMPT | - Phase 3 status;
PROMPT | - units completed;
PROMPT | - human gates encountered and resolved;
PROMPT | - verification results;
PROMPT | - files/context updated;
PROMPT | - Git checkpoint if available;
PROMPT | - known non-blocking issues;
PROMPT | - exact Phase 4 starting point.

## Playbook Alignment
PLAYBOOK ALIGNMENT — PHASE 3
Playbook Principle | Phase 3 Application | Evidence | Status
Architecture before coding | Restore Phase 1/2 architecture before changing auth. | Architecture context + implementation map. | Applied
Durable context | Update six-file context + agents.md + progress tracker. | Context Updates sheet. | Applied
Feature units | P3-01 through P3-10 are independently verifiable. | Autonomous Control. | Applied
One unit at a time | No broad uncontrolled refactor. | Execution loop in master prompt. | Applied
Server-side authorization | Every protected mutation/query has authoritative policy check. | Verification tests. | Applied
Focused correction loop | Fix only the failing boundary, then retest. | Verification Gate. | Applied
Human gates | External configuration pauses execution instead of being guessed. | Human Gates + Stop Resume Protocol. | Applied
Cost-aware architecture | No paid auth/RBAC dependency. | Dependency & Cost Gate. | Applied
Review before completion | Negative security tests required before completion. | Verification Gate. | Applied
Resume-safe progress | Progress state is updated after every unit and gate. | Progress tracker requirement. | Applied