## START HERE
PHASE 4 — DATABASE, STORAGE, CORE APPLICATION SHELL & MASTER DASHBOARD ¦ AUTONOMOUS GOOGLE AI STUDIO BUILD
Purpose | Upload this workbook after Phase 3 is complete. Google AI Studio must execute Phase 4 autonomously: inspect the real repository, implement the authoritative data/storage layer, core application services, protected shell and master dashboard, verify every P0 gate, and stop only for genuine human actions.
Phase window | Day 1 — 20-Sep-2026 ¦ 11:00–13:00
Mission | Turn the Phase 3 identity/authorization foundation into a usable application core: Firestore data model, Google Drive file-storage boundary, data-access/API layer, master navigation shell, Projects/Finance/HR dashboard surfaces, loading/error states, and persistent configuration foundations.
Source of truth | Uploaded master workbook + approved Phase 1/2 context + completed Phase 3 context/progress. Do not silently change architecture decisions.
Cost invariant | ₹0 additional cost beyond existing Google AI Pro. Prefer Firestore, Google Drive, Firebase Auth, open-source libraries, and existing Google services. Do not introduce paid database/storage/backend services.
Required predecessor | Phase 3 must be verified complete. If authentication/authorization is missing or inconsistent, STOP and report the exact blocker rather than building an insecure parallel access system.
Scope boundary | Implement core data/storage and dashboard foundations only. Do NOT implement Projects business CRUD, Excel parsing workflows, salary, reimbursement, investments, MOM/email, notes workflows, or the full visual builder feature set.
Storage boundary | Google Drive is authoritative for uploaded Excel/PDF/image files. Firestore stores file metadata, ownership, project association and permissions—not duplicated binary content.
Database boundary | Firestore is authoritative for structured application state. Create a clear repository/data-access layer so later feature units use the same boundary.
Dashboard boundary | The dashboard is a navigation and summary shell. Deep module logic is deferred to later phases.
Autonomous rule | Read this workbook completely; restore context; plan each unit; implement; verify; update progress; continue. Never declare success from code presence alone.
Human gate rule | If Google/Firebase console, Drive OAuth, billing, secrets, GitHub, or another external action is required, STOP and provide exact instructions. Never request private credentials in chat. Resume only after: DONE — RESUME PHASE 4.
Completion | All P0 verification gates pass; context/progress are updated; Git checkpoint exists when configured; Phase 5 handoff is written.

## Autonomous Control
AUTONOMOUS EXECUTION CONTROL — PHASE 4
Unit | Stage | AI Must Do | Verification Before Continue | Human Gate? | Status | Resume Behavior
P4-01 | Restore Phase 3 context | Read master requirements, Phase 1 architecture, Phase 2 foundation, Phase 3 auth/permission context and progress. Inspect repo. | Predecessor state consistent; auth/permissions present. | No | NOT STARTED | Continue only after integrity check.
P4-02 | Inspect current application | Map actual routes, server boundaries, env/config, auth, existing data services and UI shell. | Written implementation map tied to real files; no guessed paths. | No | NOT STARTED | Continue after map.
P4-03 | Define Firestore model | Implement authoritative core collections/documents, IDs, timestamps, ownership and relation strategy required by current/future features. | Schema supports Projects, users/employees, page ACL hooks, files metadata and later Finance/HR entities without duplicating ownership. | No | NOT STARTED | Continue after model review tests.
P4-04 | Build data-access boundary | Create typed repositories/services for Firestore reads/writes and authorization-aware access. | No feature code writes Firestore ad hoc; server-side policy is respected. | No | NOT STARTED | Continue after unit tests.
P4-05 | Configure Google Drive storage boundary | Implement secure file metadata + Drive integration boundary for uploaded Excel/PDF/image files. | Files have authoritative Drive ID + metadata in Firestore; access is permission checked. | Possible | NOT STARTED | If OAuth/config is needed, stop and resume after verification.
P4-06 | Core API/service layer | Create reusable server endpoints/actions for dashboard/core data and future modules without implementing business workflows. | Validated requests; unauthorized calls denied; errors normalized. | No | NOT STARTED | Continue after API smoke tests.
P4-07 | Application shell | Implement authenticated master layout, header/sidebar/navigation, responsive shell, loading/error/empty states and role-aware navigation. | Admin/Standard User see permitted navigation; direct restricted routes still server-protected. | No | NOT STARTED | Continue after route smoke tests.
P4-08 | Master dashboard | Create dashboard landing page with Projects, Finance, HR and custom-page entry points; summary placeholders may be data-backed where core entities exist. | Dashboard loads real authenticated identity and module access state; no fake sensitive data. | No | NOT STARTED | Continue after dashboard tests.
P4-09 | Security/data integrity verification | Test ownership, server authorization, invalid IDs, malformed payloads, missing records, duplicate writes and cross-user access. | All P0 negative/positive tests pass. | No | NOT STARTED | Focused correction loop.
P4-10 | Context + Git + Phase 5 handoff | Update context/progress, record schema/API/storage decisions, checkpoint Git, and write Projects+builder handoff. | Build/type/lint and P0 gates pass; handoff complete. | No | NOT STARTED | Mark Phase 4 COMPLETE only then.

## Requirements Freeze
PHASE 4 REQUIREMENTS FREEZE — DATABASE, STORAGE, CORE SHELL & MASTER DASHBOARD
ID | Master Requirement | Phase 4 Interpretation | Implementation Boundary | Access Rule | Acceptance Evidence | Priority
P4-R01 | Master website: Projects / Finance / HR | Create master navigation and protected module entry points. | Shell/dashboard only; deep business logic later. | Auth + Phase 3 permissions. | All three modules visible only when permitted. | P0
P4-R02 | Create/edit projects | Prepare project data model, membership relation and API boundary. | Do not implement full Project CRUD here. | Server authorization. | Schema/API supports later Project feature. | P0
P4-R03 | Event date countdown | Prepare project event-date fields/data shape. | Countdown UI belongs Projects phase. | Project access. | Event-date field validated. | P1
P4-R04 | Checklist Excel upload | Establish Drive file metadata/storage abstraction. | Do not implement Excel workflow here. | Project access later. | Test file metadata/storage boundary. | P0
P4-R05 | Expense Excel upload | Establish file metadata/storage abstraction for expense workbook. | No expense ledger business logic. | Project access later. | File metadata boundary. | P0
P4-R06 | Budget/spending records | Prepare extensible structured-data ownership patterns. | No budget/expense workflow. | Future project permissions. | Data model can support later records. | P1
P4-R08 | OOP reimbursement | Prepare employee ownership and future finance relations. | No reimbursement workflow. | Phase 3 ownership policy. | Schema relation available. | P1
P4-R10 | Admin-only salary | Create protected Finance/HR entry point and policy hook only. | No salary ledger. | Admin-only. | Direct route denied to Standard User. | P0
P4-R14 | Admin-only investments | Create protected Finance entry point/policy hook only. | No investment ledger. | Admin-only. | Direct route denied. | P0
P4-R15 | Anyone with access can edit | Core app must carry resource/page ACL context. | Full editor permissions later. | Server-enforced. | Permission context reaches shell. | P0
P4-R16 | Admin-controlled pages | Create page/ACL-ready core data shape. | Full page builder later. | Admin/configurable. | ACL structure exists. | P0
P4-R17 | Create new website page | Prepare page entity/storage relationship. | Page builder implementation later. | Configurable. | Page model can persist later. | P0
P4-R27 | Fully customizable pages | Prepare persistent page/document boundary for editor. | Do not implement builder features here. | ACL. | Page state can be stored safely. | P0

## Firestore Data Model
AUTHORITATIVE FIRESTORE DATA MODEL — PHASE 4
Collection/Entity | Key Fields | Purpose | Ownership / Relation | Security Boundary | Verification
users | userId, providerUserId, role, status, employeeId, createdAt, updatedAt | Application identity/profile. | One profile per verified provider identity; links to employee. | Server-derived identity; role/status not client-trusted. | Unique identity + role escalation test.
employees | employeeId, displayName, email, userId, status, createdAt, updatedAt | Business employee identity for later HR/OOP flows. | Linked to user; avoid unnecessary sensitive fields. | Self-access only unless admin. | Cross-user access test.
projects | projectId, name, description, eventDate, status, createdBy, createdAt, updatedAt | Project root entity for later Projects module. | createdBy + membership subcollection/records. | Project ACL enforced server-side. | Authorized create/read; unauthorized denied.
projectMembers | projectId, userId, role/editor flags, createdAt | Project-level access. | Composite project/user relation. | Only permitted admins/editors manage membership. | Member vs non-member test.
files | fileId, driveFileId, projectId, category, filename, mimeType, size, uploadedBy, createdAt, updatedAt | Metadata for Drive-hosted files. | References project and uploader; binary remains Drive. | Read/download checks project/page permission. | Metadata + authorization test.
pages | pageId, siteId, name, slug, status, contentRef/version, createdBy, updatedBy, createdAt, updatedAt | Persistent custom-page root for future visual builder. | Site/page hierarchy; ACL-ready. | Page access enforced server-side. | Create/read/update policy test.
pageAcl | pageId, principalType, principalId, permission, createdAt | Page-level permissions. | Links page to user/role/group-like principal. | Admin or authorized owner manages. | Allow/deny test.
sites | siteId, name, status, ownerId, createdAt, updatedAt | Master/custom website container. | Owner/admin relationship. | Admin/authorized access. | Authorized site read.
auditEvents | eventId, actorUserId, action, resourceType, resourceId, result, createdAt, metadata | Security-sensitive audit trail for role/admin/storage changes as appropriate. | Actor derived from server identity. | Append-only server writes. | Forged actor denied.
systemConfig | configId, key, value/structuredValue, updatedBy, updatedAt | Small administrative configuration, if required. | Admin-owned. | Admin-only; validate keys. | Unauthorized config mutation denied.

## Storage Architecture
STORAGE ARCHITECTURE — FIRESTORE + GOOGLE DRIVE
Data | Authoritative Owner | What Firestore Stores | What Drive Stores | Access Rule | Acceptance Test
Structured app data | Firestore | Entities, relations, metadata, permissions, statuses, timestamps. | Nothing binary. | Server authorization. | CRUD smoke test.
Checklist Excel | Google Drive binary + Firestore metadata | driveFileId, projectId, category, filename, MIME, size, uploader, timestamps. | Actual XLSX file. | Project permission. | Upload/reference/retrieve test.
Expense Excel | Google Drive binary + Firestore metadata | Same metadata boundary; structured expense records later. | Actual XLSX file. | Project permission. | Upload/reference/retrieve test.
PDF/image attachments | Google Drive binary + Firestore metadata | Metadata and relationship. | Actual binary. | Resource/page permission. | Metadata + access test.
Visual-builder assets | Drive binary + Firestore metadata later | Asset metadata, ownership and page/site association. | Actual images/media. | Page/editor permission. | Phase 5/8 integration hook.
Page/editor state | Firestore | Versioned page content/state references, settings, status. | Optional large assets only. | Page ACL. | Save/load contract test.

## Application Shell & Dashboard
CORE APPLICATION SHELL + MASTER DASHBOARD
Surface | Required Behavior | Data Source | Authorization | Empty/Error/Loading | Acceptance
Authenticated app shell | Header/sidebar/main content; responsive; identity display; logout. | Phase 3 auth + user profile. | Protected route + server session. | All states handled. | Admin/Standard User shell loads.
Projects entry | Navigation card/link to Projects. | Permission context. | Project permission. | No projects state later; do not fake data. | Correct route/access.
Finance entry | Navigation card/link to Finance. | Permission context. | Sensitive subroutes admin-only where defined. | Safe placeholder/empty state. | Standard User cannot open admin-only areas.
HR entry | Navigation card/link to HR. | Permission context. | Sensitive subroutes admin-only where defined. | Safe placeholder/empty state. | Access behavior correct.
Custom Pages entry | Navigation/entry boundary for future page builder. | sites/pages model. | Page ACL. | Empty custom-pages state. | Authorized user can reach boundary.
Dashboard summary | Show authenticated user and permitted modules; only real core data. | Firestore core entities. | Server-provided access context. | No invented metrics. | Refresh/reload stable.
Global error boundary | Normalize unexpected UI/server failures. | App runtime. | No sensitive error leakage. | User-safe error message. | Forced error handled.
Loading states | Show explicit loading during auth/data fetch. | App runtime. | Protected state only. | No flash of protected data. | Smoke test.

## Data API Contract
CORE DATA/API CONTRACT — PHASE 4
Boundary | Operation | Purpose | Authorization Rule | Error Contract | Verification
Users | GET current user | Resolve authenticated profile. | Session-derived user only. | 401/403/404 normalized. | Session test.
Projects | GET project shell | Prepare later Project module reads. | Project membership/admin. | 403 on unauthorized; 404 only where safe. | Member/non-member test.
Projects | CREATE project boundary | Prepare controlled project creation. | Capability permission checked server-side. | 400 validation / 403 auth. | Admin/configured user test.
Files | CREATE metadata + Drive reference | Persist uploaded file metadata. | Project/page permission + uploader identity. | Validation + 403. | Forged project ID denied.
Files | GET metadata/download reference | Access stored file safely. | Resource permission checked server-side. | 403/404 safe. | Cross-project denial.
Pages | GET page | Prepare builder page persistence. | Page ACL. | 403/404 safe. | ACL test.
Pages | CREATE page boundary | Prepare future builder. | Site/page create permission. | 403 unauthorized. | Permission test.
ACL | GET effective permissions | Supply shell/editor permission context. | Caller sees only permitted data. | No leakage of other users' ACLs. | Permission response test.
Audit | WRITE security event | Record important admin/security actions. | Actor derived server-side. | No client actor override. | Forged actor denied.

## Human Gates
HUMAN INTERVENTION GATES — STOP / INSTRUCT / RESUME
Gate ID | Trigger | Why AI Must Stop | Exact User Action | AI Verification After Resume | Resume Phrase
HG4-01 | Firebase project/Firestore configuration requires console action. | External console/account action cannot be safely invented. | Complete the required Firebase project/Firestore setup in the project's authorized console, then return and say DONE — RESUME PHASE 4. | Verify connectivity/config without exposing secrets; run a read/write smoke test. | DONE — RESUME PHASE 4
HG4-02 | Google Drive OAuth/consent blocks file-storage integration. | Drive authorization requires user-controlled consent. | Complete the displayed Google Drive authorization/consent steps for the app; never paste tokens/private keys into chat; then resume. | Verify authenticated Drive access with a harmless test file/reference and remove test artifact if appropriate. | DONE — RESUME PHASE 4
HG4-03 | Secure environment variable/configuration required. | Private values must not be entered in chat. | Add required configuration through the project's secure environment/secrets mechanism, without sharing values in chat. | Check variable presence without printing values; run config validation. | DONE — RESUME PHASE 4
HG4-04 | Billing prompt appears. | ₹0 target forbids silently enabling paid infrastructure. | STOP. Tell the user exactly which operation triggered billing and wait for explicit approval or an approved free alternative. | Verify selected free path before continuing. | DONE — RESUME PHASE 4
HG4-05 | Phase 3 auth/permission state is incomplete or contradictory. | Building data APIs around broken security would create unsafe architecture. | Report exact missing/contradictory predecessor evidence and wait for correction. | Re-read Phase 3 progress and run auth/permission smoke tests. | DONE — RESUME PHASE 4
HG4-06 | Architecture choice is ambiguous (e.g. storage/provider). | AI must not silently replace an approved architecture. | Present exact conflict and smallest set of choices; wait for decision. | Record decision in architecture context before coding. | DONE — RESUME PHASE 4

## Verification Gate
PHASE 4 VERIFICATION GATE — P0 EVIDENCE REQUIRED
Test ID | Verification | Expected Result | Evidence | Priority | If Failed
V4-01 | Phase 3 predecessor smoke test | Valid login/session and server authorization still work. | Auth + permission test results. | P0 | Stop feature work; correct regression.
V4-02 | Firestore connectivity | Read/write test works through the application data boundary. | Test record/result. | P0 | Fix config/data boundary.
V4-03 | Core schema integrity | Required collections/relations/keys work; timestamps and ownership are valid. | Schema/data tests. | P0 | Focused correction.
V4-04 | No ad-hoc Firestore writes | Feature code uses the defined repository/service boundary. | Code inspection/search. | P0 | Refactor boundary before continuing.
V4-05 | Drive metadata boundary | Drive file reference can be stored/retrieved without storing binary in Firestore. | Integration test. | P0 | Fix storage boundary.
V4-06 | Cross-project file access | User cannot retrieve file metadata/reference for an unauthorized project. | Negative test. | P0 | Fix authorization.
V4-07 | Admin-only Finance/HR sensitive routes | Standard User denied by server; navigation also respects permissions. | Direct route/API test. | P0 | Fix server policy.
V4-08 | Dashboard identity | Dashboard shows current verified user/profile, not client-supplied identity. | Session test. | P0 | Fix identity source.
V4-09 | Dashboard module access | Projects/Finance/HR/custom page entries match permissions. | Role/access test. | P0 | Fix navigation/access context.
V4-10 | Loading/error states | No protected data flash; failures are safe and recoverable. | Smoke tests. | P0 | Fix boundary.
V4-11 | Responsive shell | Desktop/mobile layouts do not break core navigation. | Viewport smoke test. | P0 | Fix shell.
V4-12 | Build/type/lint | All checks pass. | Command results. | P0 | Focused correction.
V4-13 | No secrets committed | No credentials/tokens/private keys in source or logs. | Secret scan/audit. | P0 | Remove/rotate if exposed.
V4-14 | Cost/dependency audit | No paid DB/storage/backend dependency introduced. | Dependency/config audit. | P0 | Replace dependency.
V4-15 | Context/progress sync | Context and progress match actual implementation. | Diff/readback. | P0 | Update before completion.
V4-16 | Git checkpoint | Changes are recoverable when Git is configured. | Commit/status evidence. | P0 | Create checkpoint or stop at Git gate.

## Context Updates
MANDATORY CONTEXT + PROGRESS UPDATES
Artifact | Required Update | Content | Verification
agents.md | Data/storage/security execution rules. | Firestore/Drive ownership, repository boundary, authorization, human gates, cost rule. | Matches actual code.
project-overview.md | Phase 4 completion/state. | Core data, storage, shell, dashboard and next feature units. | No stale Phase 3-only state.
architecture-context.md | Authoritative data/storage boundaries. | Firestore entities, Drive metadata boundary, API/data-access layer, dashboard architecture. | Matches implementation.
code-standards.md | Data access conventions. | Typed repository/services, server validation, authorization before mutation, safe errors. | Matches code.
ai-workflow-rules.md | Resume/verification behavior. | P4 units, stop/resume, no secret sharing, focused corrections. | Matches workflow.
ui-context.md | Core shell conventions. | Navigation, loading/error/empty states, responsive layout, permission-aware visibility. | Matches UI.
progress-tracker.md | P4-01 through P4-10 evidence. | Status, tests, human gates, exact next step. | Current and resumable.
feature-specs/README.md | Core data/storage specs index. | Reference schema/API/storage contracts and later feature dependencies. | No contradiction.

## Dependency & Cost Gate
DEPENDENCY / COST / BILLING GATE
Check | Required Choice | AI Must Verify | Forbidden Without Explicit Approval | Status
Structured database | Firestore per approved architecture | No parallel paid DB; correct project/config. | PostgreSQL/Prisma or paid DB introduced as mandatory. | NOT CHECKED
File storage | Google Drive + Firestore metadata | Binary files not duplicated into paid storage. | Firebase Storage as mandatory component. | NOT CHECKED
Authentication | Existing Phase 3 auth | No new auth provider. | Clerk/paid auth substitution. | NOT CHECKED
Backend runtime | Approved Google AI Studio/full-stack/server route approach | No paid server runtime dependency added. | Paid backend platform as mandatory. | NOT CHECKED
Libraries | Open-source/free packages | License/dependency audit. | Paid builder/storage plugins. | NOT CHECKED
Billing | No billing unless explicitly approved | If billing prompt appears, STOP. | Silent billing enablement. | NOT CHECKED

## Completion & Phase 5 Handoff
PHASE 4 COMPLETION GATE + PHASE 5 HANDOFF
Gate | Required State | Evidence | Status
Predecessor integrity | Phase 3 authentication/authorization remains functional. | Auth/security smoke tests. | NOT CHECKED
Firestore | Core model and data boundary implemented. | Schema + repository tests. | NOT CHECKED
Drive storage | Secure file metadata/storage boundary implemented. | Drive integration test. | NOT CHECKED
Core APIs | Typed/validated data boundaries exist. | API/service tests. | NOT CHECKED
Master shell | Protected responsive shell works. | UI smoke tests. | NOT CHECKED
Dashboard | Projects/Finance/HR/custom-page entry points work with permissions. | Dashboard tests. | NOT CHECKED
Sensitive boundaries | Finance/HR sensitive routes denied to Standard User. | Negative tests. | NOT CHECKED
Data ownership | Authoritative ownership rules are enforced. | Cross-user/project tests. | NOT CHECKED
Error/loading states | Safe app behavior under delay/failure. | UI tests. | NOT CHECKED
Cost invariant | No additional paid dependency introduced. | Dependency audit. | NOT CHECKED
Context | All context/progress files updated. | File checks. | NOT CHECKED
Git checkpoint | Recoverable checkpoint exists when Git configured. | Commit/status evidence. | NOT CHECKED
Phase 5 trigger | Project + builder implementation can begin on stable data/storage/shell foundation. | Handoff written. | NOT CHECKED

## Phase 5 Handoff
PHASE 5 HANDOFF — PROJECTS MODULE + FULL VISUAL WEBSITE BUILDER
Foundation | Phase 4 Must Hand Off | Phase 5 Uses It For
Project data model | projects + projectMembers + event-date fields. | Projects CRUD, membership, event countdown.
File storage | Drive file boundary + files metadata. | Checklist/expense Excel upload and project files.
Data access | Typed repository/service/API boundary. | Project business APIs and calculations.
Permissions | Server-enforced role/resource/page ACL hooks. | Project editor access and builder permissions.
Pages/sites | sites/pages/pageAcl persistence foundation. | Full multi-page visual builder.
Dashboard | Master shell/navigation. | Projects module UI integration.
Error/loading | Reusable app states. | Feature workflows.
Audit | Audit-event pattern. | Project/member/page/security changes.
Cost invariant | Firestore + Drive + approved open-source architecture. | Continue ₹0 target.
Git/context | Checkpoint and updated durable context. | Safe continuation in Phase 5.

## Stop Resume Protocol
STOP / RESUME PROTOCOL — MANDATORY
Situation | AI Behavior | Resume Behavior
Human external setup required | STOP. State exact unit, blocker, exact user action, and what not to share. | User completes action and replies DONE — RESUME PHASE 4.
User resumes | Read progress state and verify action before proceeding. | Continue from exact incomplete unit.
Verification fails | Do not continue downstream; identify smallest root correction. | Correct and rerun failed test.
Architecture ambiguity | STOP; present exact conflict and choices; do not silently replace architecture. | Record decision then resume.
Billing appears | STOP; identify trigger; preserve ₹0 constraint. | Continue only with approved free route or explicit approval.
Phase complete | Only after all P0 gates, context, checkpoint and handoff are complete. | Report Phase 4 completion and Phase 5 starting point.

## AI Studio Master Prompt
COPY-READY MASTER PROMPT — AUTONOMOUS PHASE 4 EXECUTION
PROMPT | You are the implementation agent for PHASE 4 of an internal company master website.
PROMPT
PROMPT | MISSION
PROMPT | Implement ONLY the database, storage, core application shell, and master dashboard foundation. Execute autonomously. Stop only when a genuine human action is required. After the user completes that action and says “DONE — RESUME PHASE 4”, verify it and continue from the exact paused point.
PROMPT
PROMPT | SOURCE OF TRUTH
PROMPT | 1. This entire Phase 4 workbook.
PROMPT | 2. The uploaded master build checklist.
PROMPT | 3. Approved Phase 1 architecture/context.
PROMPT | 4. Completed Phase 2 foundation.
PROMPT | 5. Completed Phase 3 authentication/users/roles/permissions.
PROMPT | Never silently replace these decisions.
PROMPT
PROMPT | FIRST ACTIONS
PROMPT | 1. Read this entire workbook.
PROMPT | 2. Inspect the actual repository, not assumptions.
PROMPT | 3. Read agents.md, project-overview.md, architecture-context.md, code-standards.md, ai-workflow-rules.md, ui-context.md and progress-tracker.md.
PROMPT | 4. Verify Phase 3 predecessor integrity.
PROMPT | 5. Record P4-01 through P4-10 in progress-tracker.md.
PROMPT | 6. Build only after the predecessor passes.
PROMPT
PROMPT | PHASE 4 SCOPE
PROMPT | Implement:
PROMPT | - authoritative Firestore data model for current core entities and later feature hooks;
PROMPT | - typed repository/data-access boundary;
PROMPT | - Google Drive file-storage integration boundary with Firestore metadata;
PROMPT | - validated server/API/service layer;
PROMPT | - authenticated responsive master application shell;
PROMPT | - role/permission-aware navigation;
PROMPT | - Projects, Finance, HR and Custom Pages entry points;
PROMPT | - safe loading/error/empty states;
PROMPT | - core audit-event pattern where required;
PROMPT | - tests and context/progress updates;
PROMPT | - Phase 5 handoff.
PROMPT
PROMPT | DO NOT IMPLEMENT
PROMPT | - full Projects CRUD/business workflows;
PROMPT | - event countdown implementation;
PROMPT | - checklist/expense Excel parsing workflows;
PROMPT | - expense ledger;
PROMPT | - salary;
PROMPT | - reimbursement;
PROMPT | - investment details;
PROMPT | - MOM/email;
PROMPT | - notes;
PROMPT | - full visual website builder capabilities;
PROMPT | - production deployment.
PROMPT | Create only the data/storage/shell foundations later phases depend on.
PROMPT
PROMPT | DATA RULES
PROMPT | - Firestore is authoritative for structured application state.
PROMPT | - Google Drive is authoritative for uploaded Excel/PDF/image binary files.
PROMPT | - Firestore stores Drive metadata/reference, not duplicated binary content.
PROMPT | - Use stable IDs, server timestamps, ownership and relations.
PROMPT | - Do not create ad-hoc direct database writes throughout UI components.
PROMPT | - Use a typed repository/service/data-access boundary.
PROMPT | - Validate all server inputs.
PROMPT | - Preserve Phase 3 server-side authorization.
PROMPT
PROMPT | SECURITY RULES
PROMPT | - Never trust client-supplied userId, employeeId, role, projectId, pageId, permission or actor identity.
PROMPT | - Resolve actor from verified server session/token.
PROMPT | - Enforce authorization before reads of protected resources and before every mutation.
PROMPT | - Prevent cross-user and cross-project access.
PROMPT | - Standard Users must not access Admin-only Finance/HR sensitive boundaries.
PROMPT | - UI visibility is not security.
PROMPT | - Do not expose raw storage credentials or private tokens.
PROMPT | - Do not print secrets in logs or chat.
PROMPT
PROMPT | COST RULE
PROMPT | Maintain ₹0 additional cost. Use the approved Firestore + Google Drive + Firebase Auth architecture and open-source libraries. Do not make Firebase Storage, paid databases, paid backend services or paid plugins mandatory. If a billing prompt appears, STOP rather than enabling it.
PROMPT
PROMPT | HUMAN GATES
PROMPT | When Firebase/Firestore setup, Drive OAuth, secure environment configuration, GitHub, billing, or another external action is genuinely required:
PROMPT | 1. STOP.
PROMPT | 2. State the exact unit and blocker.
PROMPT | 3. Give exact UI/configuration steps.
PROMPT | 4. Tell the user never to paste passwords, private keys or tokens into chat.
PROMPT | 5. End with: DONE — RESUME PHASE 4
PROMPT | After resume, verify the action before continuing.
PROMPT
PROMPT | EXECUTION LOOP
PROMPT | For P4-01 through P4-10:
PROMPT | - inspect;
PROMPT | - plan;
PROMPT | - implement the smallest scoped change;
PROMPT | - run targeted verification;
PROMPT | - correct failures;
PROMPT | - update progress;
PROMPT | - continue.
PROMPT | Never batch unrelated changes merely to save time.
PROMPT
PROMPT | VERIFICATION
PROMPT | Run every P0 check in the Verification Gate sheet:
PROMPT | - Phase 3 auth/authorization regression;
PROMPT | - Firestore connectivity/schema;
PROMPT | - no ad-hoc Firestore writes;
PROMPT | - Drive metadata boundary;
PROMPT | - cross-project file denial;
PROMPT | - Admin-only Finance/HR denial;
PROMPT | - dashboard identity;
PROMPT | - permission-aware navigation;
PROMPT | - loading/error states;
PROMPT | - responsive shell;
PROMPT | - build/type/lint;
PROMPT | - secret hygiene;
PROMPT | - dependency/cost audit;
PROMPT | - context/progress sync;
PROMPT | - Git checkpoint.
PROMPT
PROMPT | COMPLETION
PROMPT | Do not declare completion because the dashboard renders.
PROMPT | Phase 4 is complete only when every P0 gate passes, evidence is recorded, context files are updated, progress-tracker.md is current, the Git checkpoint exists when configured, and the Phase 5 handoff is written.
PROMPT
PROMPT | RESUME SAFETY
PROMPT | Never restart verified units unnecessarily.
PROMPT | If interrupted, read progress-tracker.md and continue from the last incomplete unit.
PROMPT | If a human gate was passed previously, verify its current state rather than repeating setup.
PROMPT
PROMPT | FINAL REPORT
PROMPT | Report:
PROMPT | - P4 units completed;
PROMPT | - human gates encountered/resolved;
PROMPT | - Firestore model and storage boundary implemented;
PROMPT | - shell/dashboard implemented;
PROMPT | - verification results;
PROMPT | - context files changed;
PROMPT | - Git checkpoint;
PROMPT | - known non-blocking issues;
PROMPT | - exact Phase 5 starting point.

## Playbook Alignment
PLAYBOOK ALIGNMENT — PHASE 4
Playbook Principle | Phase 4 Application | Evidence | Status
Architecture before coding | Restore Phase 1–3 context and inspect actual repository before data changes. | P4-01/P4-02. | Applied
Durable context | Update project/architecture/code/AI/UI/progress context. | Context Updates. | Applied
Feature units | P4-01 through P4-10 are separately verifiable. | Autonomous Control. | Applied
One unit at a time | Plan → implement → verify → update progress. | Master Prompt. | Applied
Data ownership | Firestore owns structured state; Drive owns binaries. | Data Model/Storage sheets. | Applied
Authorization boundary | All core data reads/writes preserve Phase 3 server-side rules. | API Contract + Verification. | Applied
Focused correction | Failures trigger smallest root fix and retest. | Verification Gate. | Applied
Human gates | External configuration pauses execution rather than guessing. | Human Gates/Stop Resume. | Applied
Cost-aware architecture | No mandatory paid DB/storage/backend service. | Cost Gate. | Applied
Review before completion | P0 verification evidence is mandatory. | Verification Gate. | Applied
Resume-safe progress | Every unit and gate is recorded. | Progress tracker requirement. | Applied