## START HERE
PHASE 5 — PROJECTS MODULE + FULL VISUAL WEBSITE BUILDER ¦ AUTONOMOUS GOOGLE AI STUDIO BUILD
Purpose | Upload this workbook to Google AI Studio after Phase 4 is verified. The AI must autonomously implement the Projects module and the visual-editor core, verify each unit, stop only for genuine human actions, then resume from the exact checkpoint.
Phase window | Day 1 — 20-Sep-2026 ¦ 13:00–17:00
Mission | Implement project CRUD/access, event-date countdown, checklist/expense Excel artifact workflows, project budget/spending foundations, and the mature visual editor engine integration required for drag/drop, selection, move, resize, duplicate, undo/redo and HTML/CSS rendering.
Source of truth | This workbook + uploaded master checklist + completed Phase 1–4 context/progress. Preserve source terminology and sequencing. Do not silently move Day 2 builder expansion work into this phase.
Important sequencing | The master workbook calls Phase 5 'Projects module + full visual website builder', while its detailed Day-1 tasks put the editor engine integration at D1-19 and the advanced builder capabilities at D2-10 through D2-18. Therefore Phase 5 must deliver a working editor core and stable persistence boundary; Phase 8 completes the advanced expansion.
Cost invariant | ₹0 additional cost beyond existing Google AI Pro. Use the approved open-source visual editor core (GrapesJS or the Phase-1-selected equivalent), Google Drive + Firestore boundaries, and no paid editor plugins.
Required predecessor | Phase 4 must be complete: Firestore/data-access, Drive storage boundary, protected shell/dashboard, and Phase 3 authorization must work. If not, STOP.
Scope | Implement Projects + editor core only. Do not implement salary, reimbursement, investments, MOM/email, notes, advanced responsive/CSS/JS/themes/plugins/publishing expansion, or production deployment.
Project files | Checklist and Expense Excel are uploaded as artifacts. Keep binary Excel authoritative in Drive and metadata in Firestore. Do not silently rewrite the original workbook.
Excel interpretation | Per the source Open Question Q04, default to displaying/downloading the uploaded Excel artifact while structured expense records remain separately editable/calculable. Do not corrupt or silently transform the authoritative workbook.
Autonomous loop | Read workbook → inspect repo → plan unit → implement → verify → update progress → continue. If a human gate is encountered: STOP → explain exact action → wait for DONE — RESUME PHASE 5 → verify → continue.
Completion | All P0 Phase 5 tests pass, editor core works in browser, project permissions are server-enforced, files persist, context/progress is updated, Git checkpoint exists when configured, and Phase 6 handoff is written.

## Autonomous Control
AUTONOMOUS EXECUTION CONTROL — PHASE 5
Unit | Stage | AI Must Do | Verification Before Continue | Human Gate? | Status | Resume Behavior
P5-01 | Restore Phase 4 context | Read master checklist, Phase 1–4 context/progress, builder matrix, open questions and actual repo. | Phase 4 foundation works; no contradictory state. | No | NOT STARTED | Continue after predecessor smoke test.
P5-02 | Inspect project architecture | Map project routes, Firestore entities, Drive files, permission helpers, editor host boundary and current UI. | Implementation map uses actual files/APIs. | No | NOT STARTED | Continue after map recorded.
P5-03 | Project data contract | Implement Project CRUD data/API boundary: title, description, event date/time, links, status, createdBy, members. | Validation, ownership and server permissions pass. | No | NOT STARTED | Continue after CRUD API tests.
P5-04 | Project UI + access members | Build project list/detail/create/edit/delete UI and member/access management according to configurable permissions. | Authorized users succeed; unauthorized direct API calls fail. | No | NOT STARTED | Continue after role/member tests.
P5-05 | Event countdown | Add isolated live countdown with future/expired states and timezone-safe date handling. | Countdown updates correctly and expired state is deterministic. | No | NOT STARTED | Continue after component tests.
P5-06 | Checklist Excel artifact | Upload ready-made Excel to Drive, persist metadata/title/project association, display safe representation/download/preview where supported. | File persists; original binary is not altered; authorization enforced. | Possible | NOT STARTED | Stop if Drive/OAuth/config action required.
P5-07 | Expense Excel artifact | Upload ready-made expense Excel, title it, associate it with project and establish link to structured expense/budget records without treating workbook parsing as authoritative. | File persists; project association correct; no silent data corruption. | Possible | NOT STARTED | Stop if storage/config gate occurs.
P5-08 | Budget/spending foundation | Implement project budget/given-to-person and employee spending records needed by the master requirement: amount, recipient/employee, purpose, date, project, attachment, status. | Server APIs validate ownership and permissions; totals reconcile for records created here. | No | NOT STARTED | Continue after reconciliation tests.
P5-09 | Visual editor engine integration | Integrate the Phase-1-selected mature editor (GrapesJS or approved equivalent): canvas/iframe, component palette, selection, tree/layers, drag/drop, move, resize, delete, duplicate, undo/redo, HTML/CSS rendering. | Browser test can build a simple page, manipulate components, undo/redo and save/load through the integration boundary. | Possible | NOT STARTED | If package/license/config ambiguity appears, stop and request decision.
P5-10 | Editor persistence boundary | Persist editor state/page draft in the Phase 4 page/site model without implementing advanced publishing. | Reload restores component structure/styles; permission checks apply to save/load. | No | NOT STARTED | Continue after round-trip test.
P5-11 | Builder core verification | Run capability matrix for drag/drop, move, resize, layers, nesting basics, delete, duplicate, undo/redo, HTML/CSS rendering and persistence. | Every P0 core capability passes; no advanced Day-2 feature is falsely marked complete. | No | NOT STARTED | Focused correction loop.
P5-12 | Context + Git + Phase 6 handoff | Update durable context/progress, record unresolved builder expansion items, checkpoint Git and prepare Finance/HR handoff. | Build/type/lint and all P0 tests pass; handoff is complete. | No | NOT STARTED | Mark Phase 5 COMPLETE only after all gates pass.

## Requirements Freeze
PHASE 5 REQUIREMENTS FREEZE — PROJECTS + VISUAL BUILDER CORE
ID | Source Requirement | Phase 5 Interpretation | Implementation | Access Rule | Acceptance Evidence | Priority
R02 | Create/edit projects | Full project CRUD and members. | Project entity + UI + APIs. | Configurable role/resource permission. | CRUD + membership tests. | P0
R03 | Event date countdown | Live countdown on project page. | Isolated countdown component. | Project access. | Future + expired test. | P0
R04 | Checklist Excel | Upload ready Excel and reflect on project page. | Drive artifact + Firestore metadata + preview/download boundary. | Project access. | Upload/reload/download/authorization. | P0
R05 | Expense Excel | Upload ready Excel and display/link to structured records. | Drive artifact + metadata + structured-link boundary. | Project access. | File persists + correct project. | P0
R06 | Budget/spending | Given-to-person and employee spending records. | Core structured records and totals. | Project permission + ownership. | Reconciliation test. | P0
R15 | Anyone with access can edit | Project/editor access must flow from Phase 3 permission system. | Permission-aware editor save/load. | Server enforced. | Direct API denial test. | P0
R17 | Create new website sheet/page | Phase 5 creates editor page boundary; full page management is expanded in Phase 8. | Page draft persistence. | Configurable. | Create/load draft page. | P0
R18 | Drag anything anywhere | Editor core drag/drop and reposition. | Use mature editor engine. | Editor permission. | Browser drag/move test. | P0
R19 | Resize | Editor core resize. | Engine style/canvas controls. | Editor permission. | Resize/reload test. | P0
R20 | Arbitrary columns/layouts | Phase 5 supports engine nesting/container basics; advanced flex/grid/breakpoint work is Phase 8. | Configure available container components. | Editor permission. | Nested layout smoke test. | P0
R21 | Animations | Deferred to Phase 8 advanced expansion. | Do not falsely mark complete. | Editor permission later. | Phase 8 tracker item. | P0
R22 | Custom CSS | Basic engine HTML/CSS rendering only in Phase 5; dedicated CSS editor in Phase 8. | Persistence boundary reserved. | Permission later. | Phase 8 tracker item. | P0
R23 | Custom JavaScript | Dedicated isolated script runtime is Phase 8. | No arbitrary JS in Phase 5. | Admin-only later. | Phase 8 security gate. | P0
R24 | Themes | Phase 8. | No full theme system now. | Admin/configurable later. | Phase 8 tracker item. | P0
R25 | Plugins | Phase 8 plugin registration boundary. | No arbitrary third-party runtime now. | Admin later. | Phase 8 tracker item. | P0
R26 | Responsive breakpoints | Phase 8. | No false completion in Phase 5. | Editor permission later. | Phase 8 tracker item. | P0
R27 | Fully customizable pages | Phase 5 establishes stable editor core + persistence; Phase 8 completes advanced builder/publishing. | Draft editor state is durable. | ACL enforced. | End-to-end builder expansion later. | P0

## Projects Data Model
PROJECTS + BUILDER CORE DATA MODEL
Entity | Key Fields | Purpose | Relations | Security | Verification
projects | projectId, name/title, description, eventDateTime, links[], status, createdBy, createdAt, updatedAt | Project root. | createdBy → user; members; files; pages. | Server ACL on every read/write. | CRUD test.
projectMembers | projectId, userId, projectRole/editor flag, createdAt, updatedAt | Project access. | project ↔ user. | Only authorized admin/owner/editor manages membership. | Member/non-member test.
files | fileId, driveFileId, projectId, category, title, filename, mimeType, size, uploadedBy, createdAt | Checklist/expense artifacts. | project ↔ Drive file. | Project access. | Cross-project denial.
expenseRecords | expenseId, projectId, employeeId, amount, purpose, date, attachmentFileId, status, createdBy, createdAt | Structured spending source. | project + employee + file. | Owner/editor/admin rules. | Totals reconcile.
budgetAllocations | allocationId, projectId, recipientEmployeeId, amount, purpose, date, status, createdBy | Given-to-person budget records. | project + employee. | Project permission/admin policy. | Allocation total.
pages | pageId, siteId/projectId, name, draftStateRef, status, createdBy, updatedBy, createdAt, updatedAt | Editor draft/page root. | project/site ↔ page. | Page/editor permission. | Save/load.
pageVersions | versionId, pageId, editorState, html, css, metadata, createdBy, createdAt | Future version snapshots. | page ↔ versions. | Authorized editor only. | Round-trip state.
editorAssets | assetId, driveFileId, projectId/pageId, filename, mimeType, uploadedBy | Builder asset metadata. | Drive + page/project. | ACL. | Upload/reuse boundary.

## Projects Workflow
PROJECTS MODULE — IMPLEMENTATION WORKFLOW
Workflow | Steps | Server Rule | UI Behavior | Acceptance
Create project | Validate → authorize → create project → create owner membership → audit. | Caller must have PROJECT_CREATE capability. | Form with validation. | Project appears only to permitted users.
Edit project | Load → authorize → validate → update → audit. | Editor/admin only. | Edit form. | Changes persist.
Delete project | Load → authorize → confirm → delete/archive according to approved model. | Delete permission required; never client-only. | Confirmation + safe error. | Unauthorized delete denied.
Membership | Admin/authorized owner selects user + project role/editor capability. | Cannot grant permissions beyond caller's own grant authority. | Member list. | Non-member denied; member allowed.
Event date | Store timezone-aware eventDateTime. | Only authorized project editor can change. | Countdown component. | Accurate future/expired display.
Checklist artifact | Upload → Drive → metadata → project association → display/download. | Project file permission. | Artifact card. | Binary unchanged.
Expense artifact | Upload → Drive → metadata → link to structured records. | Project permission. | Artifact + records entry point. | No silent parsing/corruption.
Spending record | Validate employee/amount/purpose/date/project → save → calculate totals. | Server ownership/role checks. | Entry/list/summary. | Totals reconcile.

## Builder Core Matrix
FULL VISUAL BUILDER — PHASE 5 CORE CAPABILITY MATRIX
Capability | Required | Engine Responsibility | Our Integration | Persistence/Security | Acceptance Test | Phase | Status
Drag & drop components | Yes | Editor canvas/component system | Configure palette/components | Persist component tree; ACL on save | Drag text/image/button/container and save | P5 | NOT STARTED
Move/reposition | Yes | Canvas selection/commands | Configure commands | Persist positions/state | Move component and reload | P5 | NOT STARTED
Resize | Yes | Canvas/style manager | Configure handles/dimensions | Persist width/height | Resize and reload | P5 | NOT STARTED
Delete | Yes | Editor command system | Expose delete command | Persist tree changes | Delete and undo | P5 | NOT STARTED
Duplicate | Yes | Editor command system | Expose duplicate command | Persist tree changes | Duplicate and reload | P5 | NOT STARTED
Layers/component tree | Yes | Editor layer manager | Expose tree panel | Persist hierarchy | Select nested component from tree | P5 | NOT STARTED
Basic nested containers | Yes | Editor component system | Configure containers/columns where supported | Persist hierarchy | Create nested multi-column layout | P5 | NOT STARTED
Undo/redo | Yes | Editor history system | Configure history | Draft/version boundary | Multiple undo/redo operations | P5 | NOT STARTED
HTML/CSS rendering | Yes | Editor runtime | Integrate canvas/iframe and output | Persist draft state | Render and reload | P5 | NOT STARTED
Flex/grid advanced controls | Yes | Style manager | Reserved for Phase 8 expansion | Persist style rules | Phase 8 acceptance | P8 | NOT STARTED
Responsive breakpoints | Yes | Device manager | Phase 8 | Persist per-device rules | Phase 8 acceptance | P8 | NOT STARTED
Animations/interactions | Yes | Commands/plugins/CSS | Phase 8 | Persist definitions | Phase 8 acceptance | P8 | NOT STARTED
Custom CSS editor | Yes | CSS/style system | Phase 8 | Scoped persistence | Phase 8 acceptance | P8 | NOT STARTED
Custom JavaScript | Yes | Sandboxed runtime | Phase 8 | Isolated execution | Phase 8 security acceptance | P8 | NOT STARTED
Themes/templates | Yes | Global style/template system | Phase 8 | Versioned persistence | Phase 8 acceptance | P8 | NOT STARTED
Plugins/extensions | Yes | Editor plugin API | Phase 8 | Allowlist/versioning | Phase 8 acceptance | P8 | NOT STARTED
Pages/assets/preview/publish | Yes | Page manager/storage/runtime | Phase 8 expansion | ACL + versioning | Phase 8 acceptance | P8 | NOT STARTED

## Editor Architecture
VISUAL EDITOR ARCHITECTURE — SAFE INTEGRATION BOUNDARY
Layer | Responsibility | Phase 5 | Security | Verification
Editor host | Mount mature editor in application page. | Implement canvas/iframe and lifecycle. | Editor only mounts for authorized users. | Load/unmount test.
Component registry | Expose safe components/blocks. | Text/image/button/container/basic layout blocks. | No arbitrary executable code. | Registry smoke test.
Command/history | Move/resize/delete/duplicate/undo/redo. | Configure engine commands. | Do not bypass app save authorization. | Command tests.
Persistence adapter | Convert editor state to app page draft/version model. | Implement save/load contract. | Server checks page/project ACL. | Round-trip test.
Storage adapter | Editor asset metadata → Drive boundary. | Wire basic asset/file reference if needed. | ACL before file access. | Authorization test.
Preview boundary | Render editor output without editing controls. | Basic preview if engine provides it. | No privileged app APIs exposed to canvas. | Preview isolation test.
Advanced runtime | Responsive/animation/CSS/JS/themes/plugins/publish. | Deferred to Phase 8. | No arbitrary JS in Phase 5. | Phase 8 handoff items recorded.

## Human Gates
HUMAN INTERVENTION GATES — STOP / INSTRUCT / RESUME
Gate ID | Trigger | Why AI Must Stop | Exact User Action | AI Verification After Resume | Resume Phrase
HG5-01 | Editor package/license/version decision is ambiguous. | The master workbook leaves GrapesJS/equivalent as an open choice; AI must not silently choose a conflicting tool. | If the current approved architecture has not selected the engine, choose/confirm the mature open-source engine proposed by AI. Then say DONE — RESUME PHASE 5. | Verify dependency/license and update architecture context before integration. | DONE — RESUME PHASE 5
HG5-02 | Google Drive OAuth/config blocks checklist/expense upload. | External authorization requires human-controlled consent. | Complete the displayed Google Drive authorization/configuration; do not paste credentials/tokens into chat; then resume. | Run harmless upload/reference test and verify permission enforcement. | DONE — RESUME PHASE 5
HG5-03 | Project creation permission is ambiguous. | Source Q02 says configurable and does not specify the default. | Choose the default Standard User project-creation policy or confirm the approved configurable setting; then resume. | Record policy and run positive/negative tests. | DONE — RESUME PHASE 5
HG5-04 | Excel interpretation is challenged by a new requirement. | Source Q04 defaults to artifact display/download + separately structured expense records. | Confirm whether to preserve that boundary; do not silently parse/overwrite authoritative Excel. | Record decision; verify no binary corruption. | DONE — RESUME PHASE 5
HG5-05 | Billing or paid editor plugin is requested/required. | ₹0 is a hard constraint. | Stop and report the exact paid dependency. Approve an exception explicitly or choose the free/open-source path. | Verify no paid dependency remains mandatory. | DONE — RESUME PHASE 5
HG5-06 | Phase 4 predecessor/security fails. | Building project/editor APIs would create unsafe access. | Fix Phase 4 or provide explicit architecture decision; do not bypass authorization. | Re-run Phase 4 security smoke tests. | DONE — RESUME PHASE 5

## Verification Gate
PHASE 5 VERIFICATION GATE — P0 EVIDENCE REQUIRED
Test ID | Verification | Expected Result | Evidence | Priority | If Failed
V5-01 | Phase 4 regression | Auth, Firestore, Drive boundary and shell still work. | Smoke-test output. | P0 | Fix regression before feature continuation.
V5-02 | Project create | Authorized user can create valid project. | UI/API test. | P0 | Focused correction.
V5-03 | Project edit | Authorized editor can update title/description/date/links/status. | UI/API test. | P0 | Focused correction.
V5-04 | Project delete | Only authorized capability can delete/archive. | Direct API negative test. | P0 | Fix authorization.
V5-05 | Membership | Member/editor permissions are enforced server-side. | Two-user test. | P0 | Fix ACL.
V5-06 | Event countdown | Future event counts accurately; expired event is handled. | Component/browser test. | P0 | Fix date handling.
V5-07 | Checklist Excel | Original Excel uploads to Drive, metadata persists, authorized user can access. | Integration test. | P0 | Fix storage/ACL.
V5-08 | Expense Excel | Original Excel persists and is linked to project/structured records. | Integration test. | P0 | Fix boundary.
V5-09 | Spending totals | Structured budget/spending records reconcile. | Calculation/API test. | P0 | Fix calculation/data boundary.
V5-10 | Cross-project file access | Unauthorized user cannot access another project's file metadata/reference. | Direct request test. | P0 | Fix server authorization.
V5-11 | Editor mount | Authorized editor loads mature editor canvas. | Browser smoke test. | P0 | Fix integration.
V5-12 | Drag/drop | Components can be dragged onto canvas and repositioned. | Browser test. | P0 | Fix engine configuration.
V5-13 | Resize | Selected components resize and state persists. | Browser + reload test. | P0 | Fix integration.
V5-14 | Delete/duplicate | Commands work and persist. | Browser test. | P0 | Fix commands.
V5-15 | Layers/tree | Nested component can be selected through tree/layer panel. | Browser test. | P0 | Fix editor config.
V5-16 | Undo/redo | Multiple edits can be undone/redone. | Browser test. | P0 | Fix history config.
V5-17 | Editor persistence | Draft editor state survives reload for authorized editor. | Save/load test. | P0 | Fix persistence adapter.
V5-18 | Unauthorized editor save | Non-editor cannot save editor state by direct API call. | Negative API test. | P0 | Fix server authorization.
V5-19 | Build/type/lint | All checks pass. | Command results. | P0 | Focused correction.
V5-20 | Secret hygiene | No credentials/tokens committed or logged. | Audit. | P0 | Remove/rotate if exposed.
V5-21 | Cost/dependency audit | No paid editor plugin/service introduced. | Dependency audit. | P0 | Replace dependency.
V5-22 | Context/progress sync | All durable context reflects actual Phase 5 state and Phase 8 deferred items. | File checks. | P0 | Update before completion.

## Decision Register
PHASE 5 DECISION REGISTER — SOURCE OPEN QUESTIONS
ID | Question | Source Default | Phase 5 Handling | Status | Impact
Q01 | Which visual editor engine? | GrapesJS or equivalent mature editor. | Use the Phase 1-selected engine if already decided. If not decided, trigger HG5-01; do not silently substitute. | OPEN | High
Q02 | Should Standard Users create projects? | Configurable permission; admin can enable. | Implement capability permission, preserve configurable policy. | OPEN | Medium
Q04 | Should uploaded Excel be parsed into editable web tables? | Display/download artifact; structured expense records separately editable. | Preserve original artifact and structured-record boundary. | RESOLVED FOR PHASE 5 | High
Builder | How much of full builder belongs Phase 5? | Detailed checklist places advanced builder expansion in D2-10:D2-18. | Deliver stable editor core in Phase 5; Phase 8 completes advanced builder/publishing. | RESOLVED BY SOURCE SEQUENCE | High
Cost | Must app remain ₹0 additional cost? | Yes — hard constraint. | No paid editor plugins/services. | RESOLVED | High

## Context Updates
MANDATORY CONTEXT + PROGRESS UPDATES
Artifact | Required Update | Content | Verification
agents.md | Record Projects/editor execution rules. | Feature-unit loop, editor safety, file integrity, server ACL, human gates. | Matches implementation.
project-overview.md | Mark Phase 5 state. | Projects + editor core status; Phase 8 deferred capabilities. | No stale phase.
architecture-context.md | Record Project/editor/storage boundaries. | Project schema, editor host, persistence adapter, Drive artifacts, ACL. | Matches code.
code-standards.md | Record project/editor coding conventions. | Typed APIs, server validation, editor state isolation, no ad-hoc storage writes. | Matches code.
ai-workflow-rules.md | Record Phase 5 resume behavior. | Stop/resume, no silent architecture changes, exact test gates. | Matches workflow.
ui-context.md | Record project/editor UI patterns. | Project list/detail, editor host, panels, loading/error states. | Matches UI.
progress-tracker.md | Record P5-01:P5-12 with evidence. | Completed units, blockers, deferred Phase 8 matrix, next Phase 6. | Current/resumable.
feature-specs/README.md | Index Project + Builder Core specs. | Links/contracts and known Phase 8 expansion dependencies. | No contradiction.

## Dependency & Cost Gate
DEPENDENCY / COST / LICENSE GATE
Check | Required Choice | AI Must Verify | Forbidden Without Explicit Approval | Status
Visual editor | Open-source mature editor core selected in Phase 1/decision gate. | License and package version; no paid plugin mandatory. | Paid editor/plugin as required dependency. | NOT CHECKED
Storage | Google Drive + Firestore metadata. | No new paid object storage. | Paid storage mandatory. | NOT CHECKED
Database | Existing Firestore boundary. | No parallel paid DB. | Paid database mandatory. | NOT CHECKED
Auth | Phase 3 authentication. | No new auth provider. | Paid auth/RBAC substitution. | NOT CHECKED
Packages | Open-source/free packages. | License/dependency audit. | Paid package required for core feature. | NOT CHECKED
Billing | No billing as workaround. | STOP on billing prompt. | Silent billing enablement. | NOT CHECKED

## Completion & Phase 6 Handoff
PHASE 5 COMPLETION GATE + PHASE 6 HANDOFF
Gate | Required State | Evidence | Status
Predecessor | Phase 4 data/storage/shell/security intact. | Regression tests. | NOT CHECKED
Project CRUD | Create/edit/delete + membership works. | P5 verification. | NOT CHECKED
Countdown | Accurate future/expired state. | Browser test. | NOT CHECKED
Checklist artifact | Drive-backed Excel artifact persists and is authorized. | Upload/reload test. | NOT CHECKED
Expense artifact | Drive-backed artifact + structured-record link persists. | Integration test. | NOT CHECKED
Budget/spending | Structured records reconcile. | Calculation test. | NOT CHECKED
Editor core | Drag/drop, move, resize, delete, duplicate, layers, undo/redo, HTML/CSS rendering work. | Builder matrix + browser evidence. | NOT CHECKED
Editor persistence | Authorized editor save/load works; unauthorized save denied. | API + reload test. | NOT CHECKED
Advanced builder scope | Phase 8 expansion items explicitly tracked, not falsely marked complete. | Decision/context record. | NOT CHECKED
Cost/license | No paid dependency introduced. | Audit. | NOT CHECKED
Context | All context/progress updated. | File checks. | NOT CHECKED
Git | Checkpoint available when configured. | Commit/status. | NOT CHECKED
Phase 6 trigger | Finance + HR + expense/reimbursement can build on stable project/data foundation. | Handoff written. | NOT CHECKED

## Phase 6 Handoff
PHASE 6 HANDOFF — FINANCE + HR + EXPENSE/REIMBURSEMENT
Foundation | Phase 5 Must Hand Off | Phase 6 Uses It For
Project model | Projects + members + event dates + permissions. | Budget, spending, employee/project expense relations.
File model | Drive artifact metadata and ACL. | Expense proofs and workbook attachments.
Employee linkage | Phase 3 identity/employee relation. | HR directory and OOP claims.
Data-access layer | Typed server repository/API boundary. | Salary, claims, investments.
Authorization | Server-enforced role/resource permissions. | Admin salary/investment and employee self-claims.
Dashboard | Finance/HR protected entry points. | Finance/HR screens.
Audit | Security/event audit pattern. | Salary, reimbursement, approvals.
Editor | Stable editor core + page persistence boundary. | Later builder expansion, not a Phase 6 dependency.
Cost invariant | No paid dependencies introduced. | Continue ₹0 architecture.

## Stop Resume Protocol
STOP / RESUME PROTOCOL — MANDATORY
Situation | AI Behavior | Resume Behavior
Human action required | STOP before the blocked action. State unit, blocker, exact action, security caution, and resume phrase. | User completes action and replies DONE — RESUME PHASE 5.
Resume | Read progress tracker and verify the external action. | Continue exact incomplete unit.
Verification fails | Do not continue downstream. Identify smallest failing boundary and correct. | Retest before continuing.
Architecture conflict | STOP and ask for explicit decision; do not silently substitute. | Record decision then resume.
Advanced builder request appears during Phase 5 | Keep scope at Phase 5 core and record Phase 8 work item unless source explicitly authorizes moving it. | Continue Phase 5 after documenting handoff.
Billing appears | STOP; preserve ₹0 invariant. | Continue only with approved free route or explicit exception.
Phase complete | Only after P0 gates + context + checkpoint + handoff. | Report completion and Phase 6 starting point.

## AI Studio Master Prompt
COPY-READY MASTER PROMPT — AUTONOMOUS PHASE 5 EXECUTION
PROMPT | You are the implementation agent for PHASE 5 of an internal company master website.
PROMPT
PROMPT | MISSION
PROMPT | Implement the Projects module and the visual-editor core described by this workbook. Execute autonomously. Stop only for genuine human actions. After the user completes a human action and says “DONE — RESUME PHASE 5”, verify it and continue from the exact paused point.
PROMPT
PROMPT | SOURCE OF TRUTH
PROMPT | 1. This entire Phase 5 workbook.
PROMPT | 2. The uploaded master build checklist.
PROMPT | 3. Completed Phase 1–4 context and progress state.
PROMPT | 4. The actual repository/code, which must be inspected before editing.
PROMPT | Do not silently invent architecture or replace approved choices.
PROMPT
PROMPT | IMPORTANT SOURCE SEQUENCING
PROMPT | The master checklist labels Phase 5 as “Projects module + full visual website builder,” but its detailed implementation schedule places:
PROMPT | - Day 1: Project CRUD, countdown, checklist Excel, expense Excel, budget/spending, and D1-19 editor engine integration.
PROMPT | - Day 2 / Phase 8: advanced layout, responsive breakpoints, styling system, animations/interactions, custom CSS, custom JavaScript, themes/templates, plugins/extensions, pages/assets/publish.
PROMPT | Therefore, in this phase deliver a working, persisted visual-editor core and explicitly track the advanced capabilities for Phase 8. Do not falsely claim advanced Day-2 capabilities are complete.
PROMPT
PROMPT | FIRST ACTIONS
PROMPT | 1. Read this entire workbook.
PROMPT | 2. Read Phase 1–4 durable context and progress.
PROMPT | 3. Inspect actual repository/routes/data services/editor boundary.
PROMPT | 4. Verify Phase 4 predecessor.
PROMPT | 5. Create P5-01 through P5-12 execution state in progress-tracker.md.
PROMPT
PROMPT | PROJECT SCOPE
PROMPT | Implement:
PROMPT | - Project create/edit/delete;
PROMPT | - project title, description, event date/time, links, status;
PROMPT | - project membership/editor access;
PROMPT | - live countdown;
PROMPT | - checklist Excel artifact upload/title/project association/display/download/preview where supported;
PROMPT | - expense Excel artifact upload/title/project association;
PROMPT | - structured budget allocation and employee spending records;
PROMPT | - mature visual editor integration with canvas/iframe, component palette, selection, tree/layers, drag/drop, move, resize, delete, duplicate, undo/redo and HTML/CSS rendering;
PROMPT | - editor draft save/load persistence through the existing page/data boundary;
PROMPT | - server-side editor/project authorization;
PROMPT | - tests, context/progress and Phase 6 handoff.
PROMPT
PROMPT | DO NOT IMPLEMENT IN PHASE 5
PROMPT | - salary;
PROMPT | - reimbursement;
PROMPT | - investments;
PROMPT | - MOM/email;
PROMPT | - notes;
PROMPT | - advanced responsive breakpoint system;
PROMPT | - full styling system;
PROMPT | - animations/interactions;
PROMPT | - custom CSS editor;
PROMPT | - custom JavaScript runtime;
PROMPT | - themes/templates;
PROMPT | - plugin/extension runtime;
PROMPT | - full multi-page publishing/unpublishing;
PROMPT | - production deployment.
PROMPT | Track those as Phase 8/7/6 work exactly according to the master checklist.
PROMPT
PROMPT | PROJECT DATA RULES
PROMPT | - Preserve original uploaded Excel binaries in Google Drive.
PROMPT | - Firestore stores metadata/reference, not duplicated workbook binary.
PROMPT | - Structured spending/budget records are authoritative for calculations.
PROMPT | - Do not silently overwrite or transform the uploaded Excel.
PROMPT | - Validate project IDs, employee IDs, file IDs and amounts server-side.
PROMPT | - Reuse Phase 4 repository/service boundary.
PROMPT
PROMPT | SECURITY
PROMPT | - Resolve actor from verified Phase 3 session.
PROMPT | - Never trust client role, userId, projectId, permission or owner fields.
PROMPT | - Enforce project membership/editor rights at server/API boundaries.
PROMPT | - Prevent cross-project file access.
PROMPT | - Prevent unauthorized project creation/edit/delete.
PROMPT | - UI visibility is not security.
PROMPT | - Do not execute arbitrary custom JavaScript in Phase 5.
PROMPT | - Do not add a paid security/editor service.
PROMPT
PROMPT | EDITOR INTEGRATION
PROMPT | Use the Phase-1-selected mature open-source editor, such as GrapesJS if that is the approved choice.
PROMPT | Do not hand-code an editor engine.
PROMPT | Configure the engine for:
PROMPT | - drag/drop;
PROMPT | - move/reposition;
PROMPT | - resize;
PROMPT | - delete;
PROMPT | - duplicate;
PROMPT | - component tree/layers;
PROMPT | - basic nested containers/columns;
PROMPT | - undo/redo;
PROMPT | - HTML/CSS rendering.
PROMPT | Create a thin integration boundary so Phase 8 can add advanced capabilities without replacing the core.
PROMPT
PROMPT | HUMAN GATES
PROMPT | If Drive OAuth, editor selection/license ambiguity, environment configuration, project-creation policy, billing, or another external action is genuinely required:
PROMPT | 1. STOP.
PROMPT | 2. State exact unit and blocker.
PROMPT | 3. Give exact action.
PROMPT | 4. Never ask for passwords/private keys/tokens in chat.
PROMPT | 5. End with: DONE — RESUME PHASE 5
PROMPT | On resume, verify the action before continuing.
PROMPT
PROMPT | COST RULE
PROMPT | ₹0 additional cost is a hard constraint. Do not make paid editor plugins, paid storage, paid database, paid auth, or billing a mandatory path. If a billing prompt appears, STOP.
PROMPT
PROMPT | EXECUTION LOOP
PROMPT | For each P5 unit:
PROMPT | inspect → plan → implement → targeted test → focused correction if needed → update progress → continue.
PROMPT | Do not batch unrelated refactors.
PROMPT | Do not mark a feature complete without its acceptance evidence.
PROMPT
PROMPT | VERIFICATION
PROMPT | Run every P0 item in the Verification Gate sheet, especially:
PROMPT | - Project CRUD;
PROMPT | - membership/access;
PROMPT | - countdown;
PROMPT | - checklist and expense artifact persistence;
PROMPT | - budget/spending reconciliation;
PROMPT | - cross-project file denial;
PROMPT | - editor mount;
PROMPT | - drag/drop;
PROMPT | - move;
PROMPT | - resize;
PROMPT | - delete/duplicate;
PROMPT | - layers/tree;
PROMPT | - undo/redo;
PROMPT | - editor save/load;
PROMPT | - unauthorized editor save denial;
PROMPT | - build/type/lint;
PROMPT | - secret hygiene;
PROMPT | - cost/license audit;
PROMPT | - context/progress synchronization.
PROMPT
PROMPT | COMPLETION
PROMPT | Only declare Phase 5 complete when every P0 Phase 5 gate passes, context files and progress tracker are updated, Git checkpoint exists when configured, advanced Phase 8 items are explicitly recorded, and Phase 6 handoff is written.
PROMPT
PROMPT | RESUME SAFETY
PROMPT | Never restart completed verified units.
PROMPT | If interrupted, read progress-tracker.md and continue from the exact last incomplete unit.
PROMPT | If a human gate was previously resolved, verify current state rather than repeating setup.
PROMPT
PROMPT | FINAL REPORT
PROMPT | Report:
PROMPT | - P5 units completed;
PROMPT | - project features completed;
PROMPT | - editor core capabilities completed;
PROMPT | - advanced builder items deferred to Phase 8;
PROMPT | - human gates encountered/resolved;
PROMPT | - verification results;
PROMPT | - files/context updated;
PROMPT | - Git checkpoint;
PROMPT | - known non-blocking issues;
PROMPT | - exact Phase 6 starting point.

## Playbook Alignment
PLAYBOOK ALIGNMENT — PHASE 5
Playbook Principle | Phase 5 Application | Evidence | Status
Architecture before coding | Restore Phase 1–4 context and inspect actual repository. | P5-01/P5-02. | Applied
Durable context | Update project/architecture/code/AI/UI/progress context. | Context Updates. | Applied
Feature units | P5-01 through P5-12 are independently verifiable. | Autonomous Control. | Applied
One unit at a time | Inspect → plan → implement → verify → record. | Master Prompt. | Applied
Use mature engine | Configure editor rather than rebuilding primitives. | Builder Core Matrix. | Applied
Data integrity | Original Excel artifact remains authoritative; structured records are separate. | Requirements/Projects Workflow. | Applied
Server authorization | Project/file/editor save/load enforce Phase 3 permissions. | Verification Gate. | Applied
Focused correction | Fix exact failing boundary and retest. | Verification Gate. | Applied
Human gates | Stop for external setup/ambiguity/billing. | Human Gates. | Applied
Scope discipline | Advanced builder features are tracked for Phase 8, not falsely completed. | Decision Register. | Applied
Cost-aware | No paid editor/storage/database/auth dependency. | Dependency Gate. | Applied
Resume-safe | Progress is durable and exact resume phrase is defined. | Stop Resume Protocol. | Applied