## START HERE
PHASE 6 — FINANCE + HR + EXPENSE/REIMBURSEMENT SYSTEM ¦ AUTONOMOUS GOOGLE AI STUDIO BUILD
Purpose | Upload this workbook to Google AI Studio after Phase 5 is verified. The AI must autonomously implement the Finance + HR + expense/reimbursement system, verify every unit, stop only for genuine human actions, and resume from the exact checkpoint after confirmation.
Phase window | Day 1 — 20-Sep-2026 ¦ 17:00–20:00
Mission | Complete the employee directory/foundation, admin salary ledger, monthly salary due/paid/pending carry-forward foundation, employee out-of-pocket claims and approval flow, configurable ₹5,000 OOP policy engine foundation, and Finance/HR protected UI.
Source of truth | This workbook + uploaded master checklist + completed Phase 1–5 context/progress + actual repository. Preserve the source workbook's terminology and feature-unit boundaries.
Required predecessor | Phase 5 must be complete and Phase 3 authorization/Phase 4 data layer must remain functional. If predecessor security/data boundaries fail, STOP and fix the predecessor rather than bypassing it.
Cost invariant | ₹0 additional cost beyond existing Google AI Pro. Do not introduce paid payroll, HR, reimbursement, reporting, database, storage, auth, or SaaS dependencies.
Critical open question | The master workbook marks Q05 as OPEN: exact interpretation of the ₹5,000 OOP rule. Default for the 2-day build is configurable threshold + requested extra ₹5,000 line item. Do not hardcode a disputed interpretation; create configuration and clearly surface the pending decision.
Scope | Implement Phase 6 Finance + HR + expense/reimbursement system. Do NOT implement MOM/email, general notes, investment details beyond the scheduled Phase 6 boundary, advanced visual-builder expansion, production deployment, or final security/QA phase.
Source schedule | Day 1 D1-16 Employee records; D1-17 Salary foundation; D1-18 OOP claims. Day 2 D2-02 allowance engine; D2-03 salary + reimbursement payout; D2-04 carry-forward; D2-05 salary report; D2-06 investment details.
Human-gate behavior | If configuration, OAuth, secure environment setup, billing, report-library ambiguity, or policy decision genuinely requires the human: STOP, explain exact action, never request private credentials, and wait for DONE — RESUME PHASE 6.
Completion | All P0 Phase 6 tests pass, financial calculations reconcile, Admin-only boundaries are server-enforced, employee self-access is enforced, context/progress is updated, Git checkpoint exists when configured, and Phase 7 handoff is written.

## Autonomous Control
AUTONOMOUS EXECUTION CONTROL — PHASE 6
Unit | Stage | AI Must Do | Verification Before Continue | Human Gate? | Status | Resume Behavior
P6-01 | Restore Phase 5 context | Read master checklist, Phase 1–5 context/progress, permissions, data model, project/employee/file boundaries and actual repo. | Phase 5 foundation works; auth/data/Project relations pass smoke test. | No | NOT STARTED | Continue after predecessor integrity.
P6-02 | Inspect Finance/HR implementation state | Map actual employee, project, expense, salary and authorization structures. Avoid duplicate entities/services. | Implementation map tied to real code; gaps recorded. | No | NOT STARTED | Continue after map.
P6-03 | Employee directory | Implement employee records: name, email, role, salary basis, active status, reimbursement settings; link to authenticated user. | Admin can manage; self-access follows policy; inactive handling works. | No | NOT STARTED | Continue after employee tests.
P6-04 | Salary foundation | Implement Admin-only monthly salary setup by employee/month: due amount, paid amount, pending balance, status and carry-forward-ready records. | Direct API/UI access denied to Standard User; ledger totals reconcile. | No | NOT STARTED | Continue after ledger tests.
P6-05 | OOP claim workflow | Employees create monthly OOP claims with date, purpose, amount, project, proof; approval/status flow; admin review. | Employee can only access own claims; admin can review/approve; cross-user access denied. | No | NOT STARTED | Continue after ownership/approval tests.
P6-06 | ₹5,000 policy configuration | Implement configurable monthly threshold/allowance policy and calculation parameters. Preserve source ambiguity; do not hardcode disputed accounting semantics. | Threshold, eligibility and line-item configuration can be tested for <=, = and > threshold. | Possible | NOT STARTED | If human decision is required, stop; otherwise implement configurable default.
P6-07 | Salary + reimbursement payout | Connect approved OOP claims to salary-period payout calculation: salary due + approved reimbursement + configured applicable line items. | Approved claims included once; rejected/pending claims excluded; duplicate payout prevented. | No | NOT STARTED | Continue after reconciliation.
P6-08 | Carry-forward | Carry unpaid salary into next due balance without deleting original month/history. | Original month preserved; next month reflects pending amount exactly once. | No | NOT STARTED | Continue after multi-month test.
P6-09 | Salary report | Generate downloadable salary/reimbursement report with employee/month/due/paid/pending/claim details. | Report totals match authoritative ledger; sensitive report is Admin-only. | Possible | NOT STARTED | If report library/config needs action, stop.
P6-10 | Investment details | Implement Admin-only investment ledger: source/person, amount, taken date, expected return date, actual return date, status, notes. | Standard User cannot read/write through UI or direct API. | No | NOT STARTED | Continue after denial tests.
P6-11 | Finance/HR UI integration | Integrate protected Finance/HR screens into master dashboard with role-aware navigation and safe states. | Admin sees permitted screens; Standard User denied from sensitive data. | No | NOT STARTED | Continue after UI/API matrix.
P6-12 | Financial integrity + context | Run full P0 financial/security tests, update context/progress, checkpoint Git, write Phase 7 handoff. | All P0 tests pass; no duplicate payout/carry-forward errors; handoff complete. | No | NOT STARTED | Mark Phase 6 COMPLETE only then.

## Requirements Freeze
PHASE 6 REQUIREMENTS FREEZE — FINANCE, HR & EXPENSE/REIMBURSEMENT
ID | Source Requirement | Phase 6 Interpretation | Implementation Boundary | Access Rule | Acceptance Evidence | Priority
R06 | Budget given to whom + employee spending purpose/date | Use project spending/budget structures from Phase 5 and connect employee/project expense records. | Financial records + reconciliation; no banking. | Project/admin/owner rules. | Budget vs spent totals reconcile. | P0
R08 | OOP monthly reimbursement | Employee claims + admin approval + payout integration. | Claims, approvals, payout calculation; no automatic bank transfer. | Employee own; admin approval. | Claim lifecycle test. | P0
R10 | Admin-only salary sheet | Admin salary ledger by employee/month. | Salary setup + ledger. | Admin only. | Direct API denial. | P0
R11 | Monthly due salary + carry-forward | Preserve monthly ledger and pending balance. | Carry-forward engine. | Admin only. | Multi-month test. | P0
R12 | Generate salary report | Server-side downloadable report. | Report generation. | Admin only. | Totals reconcile. | P0
R13 | ₹5,000 OOP rule | Configurable policy because Q05 is unresolved. | Threshold + extra line-item configuration; do not hardcode disputed interpretation. | Admin configuration; employee claim input. | <= / = / > tests. | P0
R14 | Admin-only investment details | Investment ledger. | CRUD + audit. | Admin only. | Direct API denial. | P0
R01 | Finance / HR module | Protected module screens and navigation. | UI integration only for current phase. | Role/permission aware. | Route/access tests. | P0
R15 | Anyone with access can edit | Use existing permission model for permitted financial/project records. | No blanket edit rights. | Server-enforced. | Permission tests. | P0

## HR Employee Model
HR EMPLOYEE DATA MODEL + OWNERSHIP
Entity | Key Fields | Purpose | Relations | Security | Verification
employees | employeeId, userId, name, email, role, salaryBasis, activeStatus, reimbursementSettings, createdAt, updatedAt | Authoritative employee directory. | Links to authenticated user, claims, salary ledger, projects. | Admin management; self read of allowed profile fields. | Admin create/edit; employee self-read.
reimbursementSettings | employeeId, eligible, monthlyThreshold, policyVersion, effectiveFrom, updatedBy | Employee-specific configuration where required. | Employee ↔ policy. | Admin-only configuration. | Unauthorized change denied.
employeeAudit | eventId, employeeId, actorUserId, action, timestamp | Audit sensitive HR changes. | Employee + actor. | Server-derived actor. | Forged actor denied.

## Salary Model
SALARY LEDGER + CARRY-FORWARD MODEL
Entity | Key Fields | Purpose | Rules | Security | Verification
salaryLedger | salaryId, employeeId, periodYear, periodMonth, dueAmount, approvedAdjustment, paidAmount, pendingAmount, status, createdAt, updatedAt | Monthly authoritative salary record. | One authoritative period record per employee; never overwrite historical paid/pending evidence. | Admin-only. | Duplicate-period + total tests.
salaryPayment | paymentId, salaryId, paymentDate, amount, source, reference, createdAt | Payment events if needed by approved model. | Payments sum into paidAmount; immutable history preferred. | Admin-only. | Payment reconciliation.
carryForward | carryId, employeeId, sourceSalaryId, targetSalaryId/period, amount, createdAt | Explicit traceability of unpaid salary moved forward. | Never delete original month; carry once. | Admin-only. | Two-month carry test.
payoutSummary | employeeId, period, salaryDue, approvedReimbursement, configuredExtra, totalPayout, generatedAt | Derived period total. | Derived from authoritative records; prevent duplicate inclusion. | Admin-only. | Recalculate/reload equality.

## OOP & Reimbursement Model
OUT-OF-POCKET CLAIM + REIMBURSEMENT MODEL
Entity | Key Fields | Purpose | Rules | Security | Verification
oopClaim | claimId, employeeId, projectId, period, date, purpose, amount, proofFileId, status, submittedAt, approvedAt, approvedBy | Employee monthly claim. | Status lifecycle: DRAFT → SUBMITTED → APPROVED/REJECTED → INCLUDED_IN_PAYOUT. | Employee owner + admin approver. | Lifecycle + cross-user test.
claimLine | claimId, category, amount, notes | Optional line breakdown. | Sum equals claim amount if used. | Owner/admin. | Reconciliation.
reimbursementPolicy | policyId, thresholdAmount, eligibleRule, extraLineItemAmount, calculationMode, effectiveFrom, updatedBy | Configurable interpretation of Q05. | Default threshold 5000 and extra line item 5000 may be represented as configuration, not immutable business law. | Admin-only. | Threshold test matrix.
payoutLink | claimId, salaryId/period, includedAmount, includedAt | Prevents duplicate inclusion. | One approved claim included once per payout. | Admin/server only. | Duplicate inclusion test.

## ₹5000 Policy Decision Gate
₹5,000 OOP RULE — CONFIGURABLE POLICY + DECISION GATE
Case | Source Wording | Configurable Calculation | Required Test | Human Decision? | Status
At threshold | Eligible expenses are exactly ₹5,000. | System must support threshold=₹5,000 and produce a deterministic configured result. | ₹5,000 claim/period. | Only if final accounting interpretation is needed. | NOT STARTED
Below threshold | Eligible expenses below ₹5,000. | Policy engine evaluates below-threshold behavior from configuration. | ₹4,999 test. | Only if interpretation differs from default. | NOT STARTED
Above threshold | Source says excess is reimbursed with salary and ₹5,000 extra is included per stated requirement. | Represent threshold and extra line item separately; calculation mode configurable. | ₹5,001; ₹7,500; ₹10,000 tests. | YES if company wants a different meaning. | NOT STARTED
Multiple claims | Multiple eligible claims in one month. | Aggregate according to policy before payout inclusion; prevent duplicate inclusion. | 3 claims totaling above threshold. | No if policy configuration is sufficient. | NOT STARTED
Rejected/pending | Claims not approved should not be paid. | Only APPROVED claims enter payout calculation. | Pending/rejected claim test. | No. | NOT STARTED
Policy change | Admin changes policy effective date. | Historical periods retain prior policy/version; future periods use new policy. | Change threshold between months. | No if versioning works. | NOT STARTED

## Finance Workflows
FINANCE WORKFLOWS — IMPLEMENTATION CONTRACT
Workflow | Steps | Server Rule | UI Behavior | Acceptance
Salary setup | Admin selects employee/month → enters due salary → validate → save ledger. | Admin only; one authoritative period record. | Monthly salary grid/form. | Reload retains exact values.
Salary payment | Admin records payment → validate → update paid/pending derived values. | Admin only; immutable/payment history preferred. | Payment entry + balance. | Paid + pending reconcile.
OOP claim | Employee enters date/purpose/amount/project/proof → submit. | Owner only for creation/edit before approval. | Claim form + status. | Employee cannot submit for another.
Claim approval | Admin reviews → approve/reject → audit. | Admin only; approved claim cannot be silently altered. | Review queue. | Approval audit.
Payout | Period calculation → salary due + approved reimbursement + configured policy line items → save summary. | Server-derived; prevent duplicate claim inclusion. | Payout preview/report. | Totals reconcile.
Carry-forward | At next period, carry prior pending balance without deleting source. | Admin/server only; idempotent. | Carry-forward visible. | Original + new period trace.
Investment | Admin enters source/person, amount, dates, status, notes. | Admin only. | Investment ledger. | Standard User denied.

## Finance HR UI
FINANCE + HR UI INTEGRATION
Surface | Required Behavior | Data | Authorization | Acceptance
HR Employee Directory | Admin manages employees; employee sees only permitted self data. | employees | Admin write; self read. | Direct route/API test.
Salary Portal | Admin sees monthly salary ledger, paid/pending and payout summary. | salaryLedger, payments, payoutSummary | Admin only. | Standard User denied.
OOP Claims | Employee creates/views own claims; Admin reviews/approves. | oopClaim, claimLine, payoutLink | Owner/admin. | Cross-user denial.
Finance Budget/Spending | Project-linked allocation/spending view from Phase 5. | budgetAllocations, expenseRecords | Project permission/admin. | Totals reconcile.
Investments | Admin-only ledger. | investments | Admin only. | Direct API denial.
Policy Settings | Admin configures OOP policy. | reimbursementPolicy | Admin only. | Policy version test.
Reports | Admin downloads salary/reimbursement report. | salary + claims + payout | Admin only. | Report totals match ledger.

## Human Gates
HUMAN INTERVENTION GATES — STOP / INSTRUCT / RESUME
Gate ID | Trigger | Why AI Must Stop | Exact User Action | AI Verification After Resume | Resume Phrase
HG6-01 | Q05 ₹5,000 accounting interpretation must be decided. | Source explicitly marks exact interpretation OPEN and financial behavior must not be invented. | Confirm the intended threshold/extra-line-item calculation through the app's approved configuration/decision mechanism. Do not paste financial credentials. Then say DONE — RESUME PHASE 6. | Verify policy values/version and run threshold tests. | DONE — RESUME PHASE 6
HG6-02 | Secure environment/config required. | Private credentials must not enter chat. | Add required configuration through secure environment/secrets mechanism; then resume. | Check presence without printing values. | DONE — RESUME PHASE 6
HG6-03 | Report library/configuration requires external action or paid service. | Cannot silently introduce paid dependency. | Complete approved free configuration or explicitly choose another free/open-source report route. | Dependency audit + report generation test. | DONE — RESUME PHASE 6
HG6-04 | Billing prompt appears. | ₹0 is a hard constraint. | STOP and identify exact trigger; do not enable paid service silently. | Verify free route or explicit exception. | DONE — RESUME PHASE 6
HG6-05 | Phase 5 predecessor/security fails. | Financial records must not bypass existing authorization. | Fix predecessor or provide explicit decision; do not create a parallel insecure path. | Re-run predecessor tests. | DONE — RESUME PHASE 6
HG6-06 | Payroll/reimbursement semantics conflict with source. | AI must preserve source wording and not silently invent accounting rules. | Show exact conflict and options; wait for decision. | Record decision in policy/config context. | DONE — RESUME PHASE 6

## Verification Gate
PHASE 6 VERIFICATION GATE — P0 EVIDENCE REQUIRED
Test ID | Verification | Expected Result | Evidence | Priority | If Failed
V6-01 | Phase 5 regression | Project/data/file/auth foundations still work. | Regression output. | P0 | Fix before continuing.
V6-02 | Employee create/update | Admin can manage employee records; validation works. | UI/API test. | P0 | Focused correction.
V6-03 | Employee self-access | Employee can access permitted own profile/claims only. | Ownership test. | P0 | Fix ACL.
V6-04 | Salary Admin-only | Standard User cannot read/write salary via UI or direct API. | Negative API test. | P0 | Fix server policy.
V6-05 | Salary ledger | Due/paid/pending values reconcile exactly. | Calculation/reload test. | P0 | Fix ledger logic.
V6-06 | OOP claim creation | Employee creates valid claim with date/purpose/amount/project/proof. | Lifecycle test. | P0 | Fix validation.
V6-07 | Cross-user OOP denial | Employee A cannot read/change Employee B claim by ID manipulation. | IDOR test. | P0 | Fix ownership.
V6-08 | Approval flow | Admin approve/reject changes status and records actor/time. | Workflow test. | P0 | Fix approval boundary.
V6-09 | ₹5000 threshold matrix | Below/equal/above threshold behavior follows configured policy. | Test matrix evidence. | P0 | Fix policy engine or stop for decision.
V6-10 | Duplicate payout prevention | Approved claim included once only. | Repeat payout test. | P0 | Fix idempotency.
V6-11 | Salary + reimbursement total | Payout equals authoritative salary + approved reimbursement + configured applicable line items. | Reconciliation evidence. | P0 | Fix calculation.
V6-12 | Carry-forward | Pending balance carries to next period without deleting source month. | Two/three-month test. | P0 | Fix carry-forward.
V6-13 | Salary report | Report totals match ledger and is downloadable. | Report test. | P0 | Fix report.
V6-14 | Investment Admin-only | Standard User cannot read/write investment records. | Direct API denial. | P0 | Fix server policy.
V6-15 | Financial audit | Sensitive mutations have appropriate actor/time/status history. | Audit evidence. | P0 | Fix audit.
V6-16 | Finance/HR UI access | Navigation and routes respect roles; no sensitive data flash. | Browser/direct route test. | P0 | Fix UI/API.
V6-17 | Build/type/lint | All checks pass. | Command output. | P0 | Focused correction.
V6-18 | Secret hygiene | No credentials/tokens/private keys committed/logged. | Audit. | P0 | Remove/rotate if exposed.
V6-19 | Cost/dependency audit | No paid finance/HR/reporting service introduced. | Dependency audit. | P0 | Replace dependency.
V6-20 | Context/progress sync | All durable context reflects Phase 6 reality and Phase 7 scope. | File checks. | P0 | Update before completion.

## Dependency & Cost Gate
DEPENDENCY / COST / FINANCIAL SAFETY GATE
Check | Required Choice | AI Must Verify | Forbidden Without Explicit Approval | Status
Database | Existing Firestore/data layer. | No parallel paid DB. | Paid payroll DB/service. | NOT CHECKED
Storage | Existing Google Drive + metadata. | No new paid object storage. | Paid storage mandatory. | NOT CHECKED
Auth | Existing Phase 3 identity. | No new auth service. | Paid HR/payroll identity. | NOT CHECKED
Reports | Open-source/free report library or approved runtime capability. | License and dependency audit. | Paid reporting SaaS. | NOT CHECKED
Payroll | Application-owned ledger/calculation. | No paid payroll processor required. | External payroll SaaS as mandatory dependency. | NOT CHECKED
Reimbursement | Application-owned workflow. | No paid expense-management SaaS. | Paid expense SaaS mandatory. | NOT CHECKED
Billing | No billing required for core Phase 6. | STOP on billing prompt. | Silent billing enablement. | NOT CHECKED
Financial security | Server-side validation + audit + least privilege. | No client-trusted financial totals/roles. | Client-only calculations as authoritative. | NOT CHECKED

## Context Updates
MANDATORY CONTEXT + PROGRESS UPDATES
Artifact | Required Update | Content | Verification
agents.md | Finance/HR execution and financial safety rules. | No client-trusted totals, server validation, approval authority, secret handling, human gates. | Matches code.
project-overview.md | Phase 6 completion state. | Employee directory, salary, OOP, policy engine, carry-forward, report, investments. | No stale state.
architecture-context.md | Financial data boundaries. | Salary ledger, claims, policy versioning, payout/carry-forward, audit. | Matches implementation.
code-standards.md | Financial calculation conventions. | Decimal-safe money representation, validation, idempotency, immutable history where applicable. | Matches code.
ai-workflow-rules.md | Phase 6 stop/resume and decision-gate behavior. | Q05 ambiguity must not be silently resolved. | Matches workbook.
ui-context.md | Finance/HR UI patterns. | Admin-only screens, employee self-service, safe loading/error states. | Matches UI.
progress-tracker.md | P6-01:P6-12 evidence. | Completed units, Q05 decision state, tests, exact Phase 7 start. | Current/resumable.
feature-specs/README.md | Index HR/Salary/OOP/Investments specs. | Dependencies and later MOM/notes boundaries. | No contradiction.

## Completion & Phase 7 Handoff
PHASE 6 COMPLETION GATE + PHASE 7 HANDOFF
Gate | Required State | Evidence | Status
Predecessor | Phase 5 project/file/editor foundation intact. | Regression tests. | NOT CHECKED
Employee directory | Employee records + ownership work. | HR tests. | NOT CHECKED
Salary foundation | Admin monthly salary ledger works. | Ledger tests. | NOT CHECKED
OOP claims | Employee claim + admin approval works. | Lifecycle tests. | NOT CHECKED
₹5000 policy | Configurable threshold/policy engine with decision state. | Policy matrix. | NOT CHECKED
Payout integration | Approved reimbursement flows into salary-period payout exactly once. | Reconciliation/idempotency tests. | NOT CHECKED
Carry-forward | Pending salary preserves historical month and moves forward. | Multi-month tests. | NOT CHECKED
Salary report | Downloadable report totals reconcile. | Report test. | NOT CHECKED
Investments | Admin-only investment ledger works. | Negative API test. | NOT CHECKED
Financial security | No IDOR/role escalation; audit and server enforcement pass. | Security tests. | NOT CHECKED
Cost | No paid finance/HR/reporting dependency. | Audit. | NOT CHECKED
Context | All durable context/progress updated. | File checks. | NOT CHECKED
Git | Checkpoint exists when configured. | Commit/status. | NOT CHECKED
Phase 7 trigger | MOM, email automation, notes and remaining workflows can proceed. | Handoff written. | NOT CHECKED

## Phase 7 Handoff
PHASE 7 HANDOFF — MOM, EMAIL AUTOMATION, NOTES & REMAINING BUSINESS WORKFLOWS
Foundation | Phase 6 Must Hand Off | Phase 7 Uses It For
Projects | Stable project/member/event/file foundation. | MOM editor, participants and notes.
Employees | Authoritative employee directory + user linkage. | MOM recipients and employee context.
Permissions | Admin/editor/self ownership rules. | MOM and notes access.
Data layer | Firestore repository/API boundary. | MOMs, recipients, notes, audit.
Files | Drive metadata boundary. | MOM attachments if needed.
Finance/HR | Salary, claims, payout and investment data stable. | Remaining business workflow integration.
Audit | Financial/security audit pattern. | Email send logs and MOM history.
Cost invariant | No paid services introduced. | Gmail API/open-source/free route per approved architecture.
Open decisions | Q05 policy decision recorded. | No unresolved financial ambiguity should be reinterpreted.

## Stop Resume Protocol
STOP / RESUME PROTOCOL — MANDATORY
Situation | AI Behavior | Resume Behavior
Human decision required | STOP. State exact unit, financial/policy question, available choices, impact, and safe action. Never request credentials. | User completes/decides and replies DONE — RESUME PHASE 6.
Q05 ₹5000 ambiguity | Do not silently decide accounting meaning. Keep policy configurable and ask only when the unresolved choice blocks correctness. | Verify stored policy/decision and rerun threshold matrix.
Resume | Read progress tracker and verify external action/decision. | Continue exact incomplete unit.
Calculation failure | Do not patch totals blindly. Trace authoritative inputs, fix smallest root cause, rerun reconciliation. | Proceed only after tests pass.
Security failure | Stop downstream financial work. Fix server authorization/ownership first. | Rerun security tests.
Billing appears | STOP and preserve ₹0 constraint. | Use approved free route or wait for explicit exception.
Phase complete | Only after P0 gates, context, checkpoint and handoff. | Report completion and Phase 7 starting point.

## AI Studio Master Prompt
COPY-READY MASTER PROMPT — AUTONOMOUS PHASE 6 EXECUTION
PROMPT | You are the implementation agent for PHASE 6 of an internal company master website.
PROMPT
PROMPT | MISSION
PROMPT | Implement the Finance + HR + expense/reimbursement system described in this workbook. Execute autonomously. Stop only for genuine human actions or decisions. After the user completes a human action and says “DONE — RESUME PHASE 6”, verify it and continue from the exact paused point.
PROMPT
PROMPT | SOURCE OF TRUTH
PROMPT | 1. This entire Phase 6 workbook.
PROMPT | 2. The uploaded master checklist.
PROMPT | 3. Completed Phase 1–5 context/progress.
PROMPT | 4. Actual repository/code.
PROMPT | Do not silently replace source decisions with invented architecture.
PROMPT
PROMPT | FIRST ACTIONS
PROMPT | 1. Read this entire workbook before coding.
PROMPT | 2. Read all durable context/progress files.
PROMPT | 3. Inspect the real repository and current branch.
PROMPT | 4. Verify Phase 5 predecessor.
PROMPT | 5. Record P6-01 through P6-12 in progress-tracker.md.
PROMPT | 6. Do not begin financial mutations until authorization/data boundaries are verified.
PROMPT
PROMPT | PHASE 6 SCOPE
PROMPT | Implement:
PROMPT | - employee directory: name, email, role, salary basis, active status, reimbursement settings;
PROMPT | - admin-only salary ledger by employee/month;
PROMPT | - due amount, paid amount, pending amount and carry-forward-ready structure;
PROMPT | - employee monthly OOP claims with date, purpose, amount, project, proof;
PROMPT | - claim status and admin approval/rejection;
PROMPT | - configurable ₹5,000 OOP policy engine;
PROMPT | - salary + approved reimbursement payout calculation;
PROMPT | - carry-forward of unpaid salary;
PROMPT | - downloadable salary/reimbursement report;
PROMPT | - admin-only investment ledger;
PROMPT | - protected Finance/HR UI;
PROMPT | - tests, audit, context/progress and Phase 7 handoff.
PROMPT
PROMPT | DO NOT IMPLEMENT
PROMPT | - MOM/email automation;
PROMPT | - general notes;
PROMPT | - advanced visual builder;
PROMPT | - production deployment;
PROMPT | - final integration/security/QA phase.
PROMPT | Use the existing Project/Drive/editor foundations but do not expand unrelated modules.
PROMPT
PROMPT | CRITICAL Q05 RULE
PROMPT | The master workbook explicitly marks the exact ₹5,000 interpretation as OPEN.
PROMPT | Default for the two-day build is:
PROMPT | - configurable threshold;
PROMPT | - configurable eligibility/calculation mode;
PROMPT | - separate configurable extra line-item amount;
PROMPT | - default threshold 5000 and requested extra 5000 may be represented as configuration;
PROMPT | - historical periods must retain policy version.
PROMPT | Do NOT hardcode a disputed accounting interpretation.
PROMPT | If a human decision is needed to finalize accounting behavior, STOP and use the Human Gate.
PROMPT
PROMPT | MONEY SAFETY
PROMPT | - Use a precise money representation appropriate to the approved stack; do not use unsafe floating-point arithmetic for authoritative totals.
PROMPT | - Validate nonnegative/allowed amounts server-side.
PROMPT | - Recalculate authoritative totals on the server.
PROMPT | - Never trust client-submitted salary totals, reimbursement totals, payout totals or role/admin flags.
PROMPT | - Prevent duplicate claim inclusion in a payout.
PROMPT | - Preserve historical salary periods and carry-forward traceability.
PROMPT | - Approved claims only enter payout.
PROMPT | - Rejected/pending claims do not enter payout.
PROMPT
PROMPT | AUTHORIZATION
PROMPT | - Resolve actor from verified Phase 3 identity.
PROMPT | - Salary, salary reports and investments are Admin-only.
PROMPT | - Employees can create/read permitted own OOP claims.
PROMPT | - Employee A must never access Employee B claims by changing IDs.
PROMPT | - Admin approval must be server-enforced.
PROMPT | - Financial configuration is Admin-only.
PROMPT | - UI hiding is not security.
PROMPT
PROMPT | EXECUTION LOOP
PROMPT | For P6-01 through P6-12:
PROMPT | inspect → plan → implement smallest scoped unit → targeted verification → focused correction → update progress → continue.
PROMPT | Do not batch unrelated refactors.
PROMPT | Do not declare a unit complete without evidence.
PROMPT
PROMPT | HUMAN GATES
PROMPT | STOP if:
PROMPT | - Q05 financial interpretation requires human decision;
PROMPT | - secure environment/configuration is required;
PROMPT | - a report dependency requires external configuration;
PROMPT | - billing appears;
PROMPT | - Phase 5 security/data layer is broken;
PROMPT | - source requirements conflict materially.
PROMPT | When stopping:
PROMPT | 1. State exact unit and blocker.
PROMPT | 2. Explain exact action/decision required.
PROMPT | 3. Never ask for passwords, private keys or tokens in chat.
PROMPT | 4. End with: DONE — RESUME PHASE 6
PROMPT | After resume, verify the action/decision before proceeding.
PROMPT
PROMPT | COST RULE
PROMPT | ₹0 additional cost is a hard constraint. Do not add paid payroll, HR, expense, reporting, database, storage, auth or SaaS dependencies. If a paid service is suggested by a library/tool, stop and seek an approved free alternative.
PROMPT
PROMPT | VERIFICATION
PROMPT | Run every P0 check in the Verification Gate sheet:
PROMPT | - Phase 5 regression;
PROMPT | - employee create/update/self-access;
PROMPT | - Admin-only salary;
PROMPT | - salary ledger reconciliation;
PROMPT | - OOP lifecycle;
PROMPT | - cross-user denial;
PROMPT | - approval flow;
PROMPT | - ₹5,000 threshold matrix;
PROMPT | - duplicate payout prevention;
PROMPT | - salary + reimbursement reconciliation;
PROMPT | - carry-forward;
PROMPT | - salary report;
PROMPT | - Admin-only investments;
PROMPT | - financial audit;
PROMPT | - Finance/HR UI access;
PROMPT | - build/type/lint;
PROMPT | - secret hygiene;
PROMPT | - cost/dependency audit;
PROMPT | - context/progress sync.
PROMPT
PROMPT | COMPLETION
PROMPT | Phase 6 is complete only when all P0 gates pass, evidence is recorded, context/progress are current, Git checkpoint exists when configured, and Phase 7 handoff is written.
PROMPT
PROMPT | RESUME SAFETY
PROMPT | Never restart completed verified units unnecessarily.
PROMPT | If interrupted, read progress-tracker.md and continue from the exact incomplete unit.
PROMPT | If a human gate was resolved earlier, verify current state instead of repeating setup.
PROMPT
PROMPT | FINAL REPORT
PROMPT | Report:
PROMPT | - P6 units completed;
PROMPT | - employee/HR features;
PROMPT | - salary features;
PROMPT | - OOP/reimbursement features;
PROMPT | - ₹5,000 policy decision/configuration state;
PROMPT | - carry-forward/report/investment results;
PROMPT | - human gates encountered/resolved;
PROMPT | - verification results;
PROMPT | - context files updated;
PROMPT | - Git checkpoint;
PROMPT | - known non-blocking issues;
PROMPT | - exact Phase 7 starting point.

## Playbook Alignment
PLAYBOOK ALIGNMENT — PHASE 6
Playbook Principle | Phase 6 Application | Evidence | Status
Architecture before coding | Restore Phase 1–5 context and inspect actual finance/HR state. | P6-01/P6-02. | Applied
Durable context | Update project/architecture/code/AI/UI/progress context. | Context Updates. | Applied
Feature units | P6-01 through P6-12 are independently verifiable. | Autonomous Control. | Applied
One unit at a time | Inspect → plan → implement → verify → record. | Master Prompt. | Applied
Financial correctness | Server-derived precise totals, idempotency and reconciliation. | Models + Verification. | Applied
Authorization | Admin-only salary/investments and employee self-ownership enforced server-side. | Verification Gate. | Applied
Human decision gate | Q05 is explicitly unresolved in source; no silent accounting invention. | ₹5000 Policy Decision Gate. | Applied
Focused correction | Fix smallest failing financial/security boundary and retest. | Verification Gate. | Applied
Cost-aware | No paid finance/HR/payroll/reporting dependency. | Dependency Gate. | Applied
Resume-safe | Every unit/gate is recorded and exact resume phrase defined. | Stop Resume Protocol. | Applied
Handoff | Phase 7 receives stable employee/financial/project foundation. | Phase 7 Handoff. | Applied