## START HERE
PHASE 7 — MOM, EMAIL AUTOMATION, NOTES & REMAINING BUSINESS WORKFLOWS
Standalone autonomous execution workbook for Google AI Studio. Upload this workbook after Phase 6. The AI must execute, verify, stop only at human gates, and resume from the exact saved point after confirmation.
Purpose | Complete Phase 7 of the approved 10-phase build without expanding into Phase 8 advanced builder work, Phase 9 security/QA, or Phase 10 deployment.
Execution mode | Autonomous: read workbook → restore context → inspect actual repo → plan → implement one unit → verify → update progress/context → continue.
Human-gate behavior | If a required human action is encountered, STOP. State exactly what is needed. Do not continue by guessing. Resume only after the user sends: DONE — RESUME PHASE 7.
Phase scope | D2-07 MOM editor; D2-08 MOM email; D2-09 Notes; close only explicitly scheduled business-workflow gaps that are necessary for these units.
Do not pull forward | Do not implement D2-10:D2-18 advanced builder expansion, D2-19:D2-20 security/ACL audit, D2-21:D2-25 QA/review/deploy/closeout except lightweight prerequisite checks needed to protect Phase 7.
Cost invariant | ₹0 additional cost beyond the existing Google AI Pro subscription. Prefer Firebase Auth/Firestore, Google Drive, Gmail API, open-source libraries and the existing supported runtime. Stop if billing is required.
Source-of-truth rule | The uploaded master workbook and existing phase context are authoritative. Preserve its terminology, unresolved questions, permissions and architecture decisions.
Critical unresolved source item | Q03: Who receives MOM emails? Source default = registered project participant emails. Treat this as a human decision gate if still unresolved.
Critical email boundary | Email sending must be behind an explicit server-side boundary; record send status; design retryability; never expose Gmail credentials/tokens in chat or client code.
Phase completion | Only mark Phase 7 complete after every unit is verified, human gates are resolved, context/progress are updated, a Git checkpoint exists if Git is configured, and the Phase 8 handoff is written.

## Autonomous Control
AUTONOMOUS CONTROL
Rules the AI must obey throughout Phase 7.
Rule ID | Rule | Required behavior | Stop condition | Resume trigger | Evidence | Failure handling | Status
A7-01 | Read the whole workbook before coding | Read all sheets and identify scope, dependencies, open questions, permissions, tools and acceptance criteria. | Workbook cannot be read or key source data is missing. | User resolves access/data issue. | AI records source-read completion. | STOP; do not invent missing requirements. | Mandatory
A7-02 | Restore Phase 6 context | Read project-overview, architecture-context, code-standards, ai-workflow-rules, ui-context, progress-tracker, agents.md and Phase 6 handoff if present. | Required context is missing, contradictory or stale enough to affect implementation. | User approves repair or AI reconstructs only from source evidence. | Context consistency check. | STOP if architectural ambiguity affects implementation. | Mandatory
A7-03 | Inspect actual repository | Determine current implementation state before editing. Never assume prior units are complete because a tracker says so. | Predecessor implementation is absent/broken or security boundary is unsafe. | User resolves predecessor issue or AI performs only in-scope repair. | Repo inspection notes + test output. | STOP if Phase 6 regression blocks Phase 7. | Mandatory
A7-04 | Plan before implementation | For each unit: identify inputs, files/modules, data contract, side effects, tests, rollback path. | Implementation plan reveals an unresolved material decision. | Human gate or source-backed decision only. | Plan recorded in progress tracker. | STOP; ask only the essential question. | Mandatory
A7-05 | One unit at a time | Complete and verify one unit before starting the next. | Unit acceptance fails. | Focused correction then rerun unit tests. | Unit evidence + tracker update. | Do not stack unrelated fixes. | Mandatory
A7-06 | Server-side authorization | MOM edit/publish/send and Notes read/write must enforce permissions at mutation/API boundaries. | Any sensitive mutation relies only on UI hiding. | Fix boundary before proceeding. | Direct API denial tests. | STOP if boundary cannot be safely enforced. | Mandatory
A7-07 | No secret exposure | Never request, print, commit or place passwords, private keys, OAuth refresh tokens or secrets in chat/client code. | Credential is required but cannot be configured through a safe human gate. | User configures secret securely. | Secret names/config status only. | STOP; give exact secure setup instructions. | Mandatory
A7-08 | Zero-cost gate | Do not introduce paid email/SaaS/storage or billing-required infrastructure without explicit approval. | Billing/Blaze/paid service becomes mandatory. | User explicitly resolves the cost gate. | Dependency and billing inspection. | STOP immediately. | Mandatory
A7-09 | Preserve unrelated work | No broad refactor or builder rewrite while implementing Phase 7. | Change would alter unrelated modules without dependency need. | User explicitly authorizes expansion or defer. | Diff review. | Revert/defer unrelated change. | Mandatory
A7-10 | Progress persistence | After each unit, update progress tracker and phase evidence so the AI can resume after interruption. | Tracker/context cannot be updated. | User resolves repo/file issue. | Saved tracker state. | STOP if resumption would be unsafe. | Mandatory
A7-11 | Resume exact point | On DONE — RESUME PHASE 7, reread saved state and verify the human action before continuing. | Human action cannot be verified. | Ask for missing verification only. | Gate status + evidence. | Do not assume completion. | Mandatory
A7-12 | Completion gate | Phase 7 is complete only when all P0 acceptance criteria and handoff criteria pass. | Any P0 item unresolved. | Continue within Phase 7 or stop at a gate. | Final evidence matrix. | Do not declare completion early. | Mandatory

## Requirements Freeze
PHASE 7 REQUIREMENTS FREEZE
Directly grounded in the master workbook. No silent reinterpretation.
ID | Source requirement | Phase 7 implementation | Access | Acceptance | Source checklist | Open dependency | Status
R07 | MOM automatically emailed after update | MOM editor + explicit publish/update action + server-side email job + recipient resolution + send log + retryable failure state | Project access; recipient source must be authoritative | Registered IDs receive update; send logged | D2-07,D2-08 | Q03; Gmail API configuration | Open
R09 | General notes | Persistent project notes with edit/history and permission control | Page/project access | Notes survive refresh and respect access | D2-09 | Phase 5 project access model | Open
R15 | Anyone with access can edit | Apply existing page/project ACL to MOM and Notes | Per page/site/project | Allowed user can edit and save | D2-19 (later phase) | Use existing permissions without pulling full D2-19 into Phase 7 | Constrained
R16 | Admin-controlled pages | Do not weaken protected areas while adding MOM/Notes | Admin for protected pages/modules | Unauthorized direct API access blocked | D2-19,D2-20 (later) | Phase 7 only verifies relevant boundaries | Constrained
R01 | Master website Projects / Finance / HR | Phase 7 must preserve working navigation and previously completed modules | Existing roles/access | Each module remains accessible as permitted | All | Phase 6 regression | Regression check

## Phase 7 Units
PHASE 7 EXECUTION UNITS
Execute strictly in order unless a dependency requires a focused correction.
Unit | Source | Objective | Dependencies | AI execution | Verification | Human gate | Evidence to save | Out of scope | Status | Started | Completed
P7-01 | D2-01 / Phase 6 handoff | Restore Phase 6 context and verify predecessor state. | Phase 6 complete/context files | Read workbook + context + repo; reconcile tracker against actual code; run targeted predecessor smoke tests; write Phase 7 start state. | Projects/Finance/HR navigation, project access, employee/finance prerequisites still work. | If Phase 6 completion/security state is materially inconsistent. | context audit; test output; tracker | No unrelated repairs. | Not Started
P7-02 | D2-07 | Create/update MOM editor for each project, with participant/recipient source, version/history and published status. | Project CRUD + members + DB | Inspect current project data model; define MOM entity/version/status; build editor UI; save draft; publish/update; retain history without overwriting prior versions; enforce project access server-side. | Create/edit/save/reload; history visible; draft/published states correct; unauthorized API mutation denied. | Q03 if recipient source is unresolved or project participant semantics are ambiguous. | MOM schema/API/UI tests; screenshots/logs if useful. | No full email campaign system. | Not Started
P7-03 | D2-08 | Send MOM update to authoritative registered recipient IDs after publish/update; log result and support retry. | P7-02 + Gmail API path | Resolve recipient source from approved decision; implement server-side send boundary; create send record/status; trigger only on explicit publish/update; make operation idempotent/retryable; avoid duplicate sends on refresh. | Success/failure logged; recipient list correct; retry path works; duplicate trigger does not create unintended duplicate send. | Gmail OAuth/configuration, sender identity, recipient decision Q03, or billing issue. | Email send log; test message metadata; retry/idempotency test. | No bulk marketing/campaign features. | Not Started
P7-04 | D2-09 | Implement persistent general project notes with edit/history and permission control. | Project access | Create note model/API/UI; support create/edit/save/reload/history as appropriate; enforce project/page permissions at server boundary; prevent cross-project access. | Notes survive refresh; authorized edit works; unauthorized direct API read/write denied. | If access semantics conflict with existing ACL model. | CRUD tests; access denial tests; history evidence. | No rich collaborative editor. | Not Started
P7-05 | Remaining business workflow closure | Close only Phase-7-relevant gaps discovered during MOM/Notes implementation, without pulling later-phase work forward. | P7-02:P7-04 | Trace dependencies back to master requirements. Fix only blockers required for MOM/email/notes to integrate with existing Projects/HR/permissions/data layers. | P0 Phase 7 journeys pass without regressions. | Any new requirement not explicitly required by Phase 7. | Change list + reason for each repair. | No Phase 8 builder expansion, Phase 9 audit, Phase 10 deployment. | Not Started
P7-06 | Phase 7 verification | Run focused end-to-end verification for Phase 7 and regression checks. | P7-01:P7-05 | Execute acceptance matrix; inspect logs; test direct API boundaries; verify no secret leakage and no paid dependency introduced. | All P7 P0 tests pass; no critical Phase 7 defect remains. | Any unresolved critical failure or cost gate. | Verification matrix; failure/correction log. | Do not perform full D2-20/D2-21/D2-23:D2-25. | Not Started
P7-07 | Context + Git + Phase 8 handoff | Persist implementation state and produce exact Phase 8 starting point. | P7-06 | Update progress tracker, architecture/context where behavior changed, agents/workflow rules if needed, decision register; create Git checkpoint if configured; write Phase 8 handoff. | Another AI can resume and understand exactly what is done/pending. | Git/context unavailable or unresolved critical state. | Commit/checkpoint; updated context; handoff sheet/file. | Do not start Phase 8. | Not Started

## MOM Data Model
MOM DATA MODEL & STATE
Use the existing data layer; adapt names to actual repo conventions rather than blindly replacing the schema.
Entity/Field | Type | Purpose | Rules | Write authority | Read authority | History/audit | Validation | Sensitive? | Status
ProjectMOM | collection/document | One logical MOM stream per project | Linked to project; latest status/version visible | Project editor/admin | Project access | Versions retained | Project exists | Business | Required
momVersion | integer | Monotonic version number | Increment on published revision; draft saves may use separate revision mechanism | Server | Project access | Immutable published version preferred | Positive integer | No | Required
content | text/structured | MOM body | Preserve editor content safely; sanitize/render according to app boundary | Project editor/admin | Project access | Version snapshot | Non-empty or explicitly allowed empty | Potentially sensitive | Required
status | enum | draft/published | Only server-authorized publish transition triggers email | Project editor/admin | Project access | Transition history | draft/published | No | Required
recipientSource | enum/reference | Authoritative recipient source | Must follow approved Q03 decision; do not infer silently | Admin/config boundary | Admin/project editor as appropriate | Decision history | Valid configured source | Potentially sensitive | Gate
recipientsSnapshot | list | Exact recipients for a published version | Snapshot at send time to preserve auditability | Server | Admin/project access as appropriate | Persist with send record | Valid email IDs | Sensitive | Required
sendRecord | subcollection/entity | Email attempt status | pending/sending/sent/failed/retryable; idempotency key | Server only | Admin/project editor if permitted | All attempts retained | Unique event/version key | Sensitive | Required
createdAt/updatedAt | timestamp | Lifecycle timestamps | Server-generated | Server | Permitted users | Immutable createdAt | Server timestamp | No | Required

## MOM Email Workflow
MOM EMAIL AUTOMATION WORKFLOW
Gmail API, explicit server boundary, send logging and retryability. No third-party transactional email by default.
Step | Trigger | Server action | Data captured | Idempotency | Failure handling | Human gate | Security rule | Verification | Fallback | Status
1 | User saves draft | Persist draft only | MOM version/content | No email side effect | Show save error; do not send | None | Authorization required | Reload draft | None | Not Started
2 | User publishes/updates MOM | Validate actor + project + content + recipient source | Project ID, MOM version, recipients snapshot | Unique project+version+event key | Do not duplicate on retry | Q03 must be resolved | Server only | Publish twice/retry test | Manual send only if source says so | Not Started
3 | Server queues/manages send | Create send record before/with controlled send | send ID, status, timestamps | Unique send key | Retryable failed state | Gmail OAuth/config may gate | No client token access | Inspect send record | Manual email fallback only if explicitly approved | Not Started
4 | Gmail API send | Send to approved recipients | sender, recipients, subject, body, message metadata | Provider/message ID if available | Record provider error without leaking secrets | OAuth/sender setup gate | Least privilege | Controlled test recipient | Manual fallback | Not Started
5 | Success | Mark sent | sentAt, provider/message ID if safe | Idempotent status transition | No repeated send | None | Audit trail | Recipient receives message | None | Not Started
6 | Failure | Mark failed/retryable | error class, timestamp, attempts | Same send key | Retry only according to bounded policy | If auth/billing/config failure | Do not expose raw secrets | Failure then retry test | Manual fallback if approved | Not Started
7 | Audit | Expose send history to authorized users | status, version, recipient snapshot, timestamps | Immutable attempt record | N/A | None | Sensitive data access controlled | History matches actual behavior | None | Not Started

## Q03 Recipient Gate
Q03 — MOM RECIPIENT DECISION GATE
The master workbook marks this question OPEN. Do not silently turn the default into a final policy.
Decision ID | Question | Source default | What AI may do before decision | What requires human decision | Implementation consequence | Evidence | Status
Q03 | Who receives MOM emails? | Registered project participant emails | Build recipient abstraction and store recipient source as configurable; do not hard-code a broader audience. | Confirm authoritative recipient source if current app does not already establish it. | Recipient resolver and send audit must use the approved source. | Decision recorded in context/decision register. | OPEN
Q03-G1 | Are project participants the registered recipient list? | Default = yes | AI can inspect existing project participant/member records. | User confirms or changes source. | Resolver points to participant email records or approved alternative. | User confirmation + updated decision register. | Pending
Q03-G2 | Should every MOM update email immediately? | D2-08 says on MOM publish/update. | AI can implement explicit publish/update event boundary. | If user wants batching/digest/manual approval, that is a behavior change requiring confirmation. | Trigger policy changes. | Decision record. | Pending
STOP RULE | If Q03 cannot be resolved from existing authoritative project data and prior decisions, STOP and ask the user to confirm the recipient source. Do not guess.

## Notes Workflow
PROJECT NOTES WORKFLOW
Simple persistent notes; no rich collaborative editor. History and permissions are required.
Step | Action | Server rule | Data | Access | History | Verification | Failure handling | Status
1 | Open notes | Load notes only for project/page user can access | projectId + note records | Project/page ACL | History visible if implemented | Authorized user can load | 403/denial; no data leak | Not Started
2 | Create/edit note | Validate actor server-side | content, author, timestamps | Editor/admin as configured | Create revision/history | Save/reload | No partial write | Not Started
3 | View history | Return only history for authorized project | revision snapshots | Project access | Immutable prior revisions | Older content reloads | 404/403 appropriately | Not Started
4 | Unauthorized access | Attempt direct API read/write using another project/user | N/A | Denied | No leakage | 403/denial test | Fix boundary before proceeding | Not Started
5 | Regression | Refresh/navigation/logout/login | N/A | Same as normal ACL | History remains | Smoke test | Focused correction | Not Started

## Remaining Workflow Boundary
REMAINING BUSINESS WORKFLOW BOUNDARY
A strict fence so autonomous execution does not accidentally consume later phases.
Area | Phase 7 action | Allowed | Not allowed | Reason | If discovered | Evidence | Status
Projects | Integrate MOM and Notes with existing project access/members | Yes | Rebuild Projects CRUD/countdown/files | Dependencies already assigned to earlier phases | Repair only the specific blocker | Change list | Enforced
Email | Gmail API send path, logs, retryability | Yes | Email marketing/campaign system | D2-08 is internal MOM notification only | Defer broader request | Feature boundary note | Enforced
Notes | Simple persistent notes + history + ACL | Yes | Rich collaborative editor | D2-09 explicitly says simple persistent notes | Defer enhancement | Scope note | Enforced
Visual Builder | Use existing editor only where needed to render/host MOM/notes UI | No advanced builder work | D2-10:D2-18 | Those are Phase 8 | Defer | Deferred backlog | Enforced
Security | Focused security checks on Phase 7 boundaries | Yes | Full D2-20 audit | Full audit is Phase 9 | Record finding and defer if non-blocking | Finding log | Enforced
QA | Phase 7 acceptance + regression | Yes | Full D2-21 end-to-end suite | Full suite is later | Record targeted test | Test report | Enforced
Deployment | No production deployment | No | D2-24/D2-25 | Phase 10 owns deployment | Defer | Handoff | Enforced
Finance/HR | Preserve existing flows and recipient/employee data needed by MOM | Yes | Redesign salary/OOP logic | Phase 6 owns Finance/HR | Repair only if direct dependency breaks | Regression evidence | Enforced

## Human Gates
HUMAN INTERVENTION GATES
AI must stop exactly here when a human action is required.
Gate | Trigger | What AI must NOT do | Exact user action | After user action | Verification | Resume command | Severity | Status | Evidence
HG7-01 | Q03 recipient source unresolved | Do not guess recipients or silently email a broader/narrower audience. | Confirm the authoritative MOM recipient source, e.g. registered project participant emails, or provide the approved alternative. | AI records decision and continues from the blocked unit. | Verify recipient resolver matches decision. | DONE — RESUME PHASE 7 | High | Pending
HG7-02 | Gmail OAuth/sender configuration required | Do not ask for secrets in chat or place tokens in source. | Complete OAuth/consent/configuration in the secure environment and tell AI only that it is configured. | AI verifies configuration using a safe test; no secret values shown. | Controlled test send. | DONE — RESUME PHASE 7 | Critical | Pending
HG7-03 | Billing or paid service appears necessary | Do not enable billing or substitute a paid SaaS silently. | Decide whether to preserve ₹0 architecture or explicitly authorize a paid dependency. | If ₹0 remains, AI must redesign within allowed architecture; if paid is authorized, record exception. | Dependency/cost scan. | DONE — RESUME PHASE 7 | Critical | Pending
HG7-04 | Existing Phase 6 security/data boundary blocks MOM/Notes | Do not bypass server authorization or expose sensitive data. | Approve a focused repair if needed or resolve the predecessor issue. | AI verifies repair and resumes exact unit. | Direct API/security test. | DONE — RESUME PHASE 7 | Critical | Pending
HG7-05 | Source contradiction or missing authoritative data | Do not invent business semantics. | Provide the missing decision/source or approve a clearly documented interpretation. | AI records decision and resumes. | Decision register/context check. | DONE — RESUME PHASE 7 | High | Pending

## Verification Gate
PHASE 7 VERIFICATION & ACCEPTANCE
Every row must have evidence before the AI marks Phase 7 complete.
ID | Test | Expected result | Method | Evidence | Failure action | Related source | Priority | Status | Verified by | Date
V7-01 | Phase 6 regression | Projects/Finance/HR and access still work | Targeted smoke tests | Test output | Focused repair or gate | Phase 6 handoff | P0 | Not Started
V7-02 | MOM create/save/reload | Content persists and reloads | UI + API | MOM record/test output | Fix root boundary | D2-07 | P0 | Not Started
V7-03 | MOM history | Previous published versions remain auditable | Create 2 revisions then inspect | Version evidence | Fix versioning | D2-07 | P0 | Not Started
V7-04 | MOM status | Draft vs published state is correct | State transition test | State evidence | Fix transition rules | D2-07 | P0 | Not Started
V7-05 | Recipient source | Exactly approved recipients are resolved | Inspect resolver + controlled test | Recipient snapshot | Stop at Q03 gate | Q03/D2-08 | P0 | Not Started
V7-06 | MOM email send | Approved recipients receive the published MOM | Controlled send | Provider/send log + test receipt | Fix send boundary | D2-08 | P0 | Not Started
V7-07 | Email idempotency | Retry/refresh does not unintentionally duplicate send | Repeat same event | Send records | Fix idempotency | D2-08 | P0 | Not Started
V7-08 | Email failure/retry | Failure is logged and retryable | Controlled failure/config test | Failure + retry record | Focused correction or gate | D2-08 | P0 | Not Started
V7-09 | Notes persistence | Notes survive refresh/navigation | UI test | Note record | Fix persistence | D2-09 | P0 | Not Started
V7-10 | Notes history | Prior revisions/history are available if implemented | Edit twice; inspect | History evidence | Fix revision logic | D2-09 | P0 | Not Started
V7-11 | Cross-project denial | User cannot access another project’s notes/MOM | Direct API test | 403/denial evidence | Fix server ACL | Permissions matrix | P0 | Not Started
V7-12 | Role boundary | Sensitive Finance/HR remains protected | Direct API test | Denial evidence | Do not weaken ACL | Permissions matrix | P0 | Not Started
V7-13 | Secret hygiene | No secret/token in client bundle, logs or repo | Static search + config inspection | Scan output | Remove exposure | AI workflow rules | P0 | Not Started
V7-14 | Cost gate | No new mandatory paid dependency | Dependency/config review | Cost report | STOP at HG7-03 | Required Tools | P0 | Not Started
V7-15 | Build/type/lint | Project checks pass | Run configured checks | CI/local output | Focused correction | Playbook | P0 | Not Started
V7-16 | Context/progress | Tracker and context match implementation | Read saved files | Context evidence | Update before completion | Playbook | P0 | Not Started
V7-17 | Phase 8 handoff | Exact next starting point is documented | Review handoff | Handoff file/sheet | Complete handoff before close | Playbook | P0 | Not Started

## Dependency & Cost Gate
DEPENDENCY & COST GATE
Hard invariant: ₹0 additional cost beyond existing Google AI Pro. Existing master workbook choices are authoritative.
Dependency | Expected route | Allowed in Phase 7 | Do not introduce | Verification | Human gate if violated | Source | Status | Evidence
Authentication | Existing Firebase Auth | Yes | Paid auth SaaS | Inspect config/package | HG7-03 if cost appears | Required Tools | Not Started
Database | Existing Firestore | Yes | Paid relational DB unless concrete need | Inspect config/package | HG7-03 | Required Tools | Not Started
File storage | Existing Google Drive | Yes | Firebase Storage as mandatory dependency | Inspect upload path | HG7-03 | Required Tools | Not Started
Email | Gmail API | Yes | Resend/SendGrid/Mailgun as mandatory | Inspect dependencies + send path | HG7-02/HG7-03 | Required Tools | Not Started
Background/async | Chosen app-supported server runtime/managed async pattern | Yes | Trigger.dev as mandatory | Inspect implementation | HG7-03 if paid/unsupported | Required Tools | Not Started
Editor | Existing open-source editor integration | No Phase 7 expansion | Paid editor plugins | Inspect package/license | HG7-03 | Required Tools | Not Started
Hosting | Existing no-cost supported deployment path | Not a Phase 7 deployment task | Paid hosting | No production deployment | HG7-03 | Required Tools | Not Started
Open-source libraries | XLSX/ExcelJS/PDF if required | Yes | Paid reporting/editor libs | Package/license scan | HG7-03 | Required Tools | Not Started

## Context Updates
CONTEXT & PROGRESS UPDATES
These files make autonomous resumption reliable.
Context file | Update required | What to record | When | Verification | Do not record | Owner | Status | Evidence
project-overview.md | Yes if Phase 7 changes product behavior | MOM, Notes, email automation, recipient decision | After architecture/behavior changes | Read back for consistency | Secrets | AI | Not Started
architecture-context.md | Yes | MOM/email/notes data flow, Gmail boundary, async/send logging | Before P7-06 completion | No contradictions with actual code | Credentials | AI | Not Started
code-standards.md | Only if new patterns introduced | Email/server mutation/error handling conventions | When needed | Matches actual code | Sensitive values | AI | Not Started
ai-workflow-rules.md | Yes if new stop/resume rules discovered | Human gates and correction rules | At gate/closeout | Resume protocol still valid | Secrets | AI | Not Started
ui-context.md | Yes if UI patterns change | MOM editor, notes, send status UI conventions | After UI implementation | Matches actual UI | Private data examples | AI | Not Started
progress-tracker.md | Yes after every unit | Unit state, tests, blockers, exact resume point | Every unit | Current code matches tracker | Secrets | AI | Not Started
agents.md | Yes if repository instructions changed | Scope boundaries and agent operating rules | If needed | Instructions are executable | Credentials | AI | Not Started
Decision register | Yes | Q03 and any other material decisions | Immediately after decision | Decision is source-backed | Personal secrets | AI | Not Started
Git checkpoint | If Git configured | Phase 7 implementation checkpoint | At closeout | Working tree/commit status | Tokens | AI | Not Started

## Stop Resume Protocol
STOP / RESUME PROTOCOL
This is the core autonomous loop. The AI must follow it literally.
Step | AI behavior | Required message content | User action | AI after resume | Evidence | Forbidden | Status
1 | Execute until a real human gate is reached. | State the exact gate ID, why it blocks, what was completed, what must be done by the user, and the exact resume phrase. | Perform only the requested human action. | Wait; do not continue automatically. | Saved tracker + gate status | Guessing, repeated confirmation requests, asking for secrets in chat | Mandatory
2 | STOP completely at gate. | Example structure: BLOCKED AT HG7-02 — Gmail OAuth/configuration required. Completed P7-02. Please configure securely. Then send DONE — RESUME PHASE 7. | Complete configuration/decision. | On resume, reread saved state and verify action. | Gate verification | Assuming DONE means success without verification | Mandatory
3 | Resume exact point. | Do not restart Phase 7 from the beginning unless state is corrupted. | Send DONE — RESUME PHASE 7. | Verify gate, then continue next pending step. | Verification output | Discarding prior progress | Mandatory
4 | If verification fails after resume. | Explain the exact remaining blocker. | Provide missing action if human-owned. | Continue only after blocker is resolved. | Updated gate evidence | Silently bypassing | Mandatory
5 | After each unit. | Mark unit complete only when acceptance passes; update context/tracker. | No user action unless gate. | Continue to next unit. | Unit evidence | Marking by assumption | Mandatory
6 | At final completion. | Provide a concise completion report and exact Phase 8 starting point. | No action unless Phase 8 is requested. | Stop Phase 7; do not begin Phase 8. | Final evidence + handoff | Starting next phase automatically | Mandatory

## AI Studio Master Prompt
GOOGLE AI STUDIO — PHASE 7 MASTER EXECUTION PROMPT
This sheet is intended to be the operational prompt/context for autonomous execution.
MASTER PROMPT
You are the autonomous implementation agent for Phase 7 of the Master Website application. AUTHORITATIVE SOURCES 1. This entire Phase 7 workbook. 2. The uploaded Master_Website_2_Day_App_Build_Checklist_ZERO_ADDITIONAL_COST_Google_AI_Studio.xlsx. 3. The actual repository/codebase. 4. Existing durable context files and the Phase 6 handoff. Do not replace source requirements with assumptions. MISSION Complete Phase 7 only: - D2-07 MOM editor - D2-08 MOM email automation - D2-09 General project notes - only the explicitly necessary Phase-7 integration/closure work required to make those units function with the existing Projects, Finance/HR, permissions and data layers. DO NOT IMPLEMENT - D2-10:D2-18 advanced visual-builder expansion - D2-19:D2-20 full ACL/security phase - D2-21:D2-25 full QA/review/deployment/closeout Those belong to later phases. Perform only focused prerequisite/regression checks needed for Phase 7 safety. OPERATING LOOP Read workbook → restore context → inspect repo → verify Phase 6 predecessor → plan P7-01 → execute one unit → verify → update progress/context → continue. At any human gate: STOP. Do not guess. Tell the user exactly what to do. Wait for: DONE — RESUME PHASE 7 Then reread the saved state, verify the human action, and resume from the exact blocked point. SOURCE DECISIONS - Q03 is OPEN in the master workbook: who receives MOM emails? Source default is registered project participant emails. If existing authoritative data already establishes this, use it and record the evidence. If not, STOP at HG7-01 and ask the user to confirm. - The ₹0 additional-cost constraint is HARD. Do not enable billing or add paid SaaS. - Gmail API is the source-recommended email route. - Email sending must be server-side, logged, retryable/idempotent, and must not expose credentials/tokens. - Notes are simple persistent notes with history/access control, not a collaborative rich editor. - Preserve all existing permissions and sensitive Finance/HR boundaries. IMPLEMENTATION RULES - Plan before each unit. - Use existing architecture and naming conventions. - Do not rebuild mature infrastructure unnecessarily. - Enforce authorization at server/API mutation boundaries. - Never trust client-provided roles, project ownership, recipient lists or financial/sensitive permissions. - Never put secrets in chat, source, logs or client bundles. - Use focused root-cause corrections only. - Update progress-tracker after every completed unit and record exact blockers. - Update architecture/context files whenever actual behavior or decisions change. - If Git is configured, create a Phase 7 checkpoint before completion. MOM ACCEPTANCE - Create/update/save/reload. - Draft/published state. - Version/history. - Approved recipient source. - Publish/update triggers email. - Send status is recorded. - Failure is retryable. - Repeated trigger does not unintentionally duplicate the same event. - Unauthorized direct API mutation is denied. NOTES ACCEPTANCE - Create/edit/save/reload. - History/revision behavior. - Project/page permission enforcement. - Cross-project direct API access denied. COST ACCEPTANCE - No new paid mandatory service. - No Firebase Storage/Blaze dependency introduced solely for this phase. - No Resend/SendGrid/Mailgun/paid email service. - No paid editor plugin. - No hidden billing requirement. COMPLETION Do not declare Phase 7 complete until: 1. All P7 units are verified. 2. All human gates are resolved. 3. Verification Gate is complete. 4. Context/progress files match implementation. 5. Git checkpoint exists if configured. 6. Phase 8 handoff is written. 7. No unresolved critical Phase-7 defect remains. FINAL REPORT Report: - units completed - files/modules changed - MOM behavior - recipient decision - email configuration status - notes behavior - verification results - human gates encountered/resolved - cost/dependency result - context/progress updates - Git checkpoint - known issues - exact Phase 8 starting point Do not start Phase 8 automatically.

## Completion & Phase 8 Handoff
COMPLETION GATE & PHASE 8 HANDOFF
Phase 7 cannot self-advance. It ends with a verified handoff.
Gate | Requirement | Evidence required | Pass condition | If not passed | Owner | Status | Completed at | Notes
C7-01 | P7-01 predecessor/context restored | Context audit + smoke test | Phase 6 state verified | STOP/repair only if in scope | AI | Not Started
C7-02 | P7-02 MOM complete | MOM tests | D2-07 acceptance passes | Focused correction | AI | Not Started
C7-03 | P7-03 Email complete | Send log + controlled receipt + retry/idempotency | D2-08 acceptance passes | Human gate or correction | AI | Not Started
C7-04 | P7-04 Notes complete | CRUD/history/access tests | D2-09 acceptance passes | Focused correction | AI | Not Started
C7-05 | P7-06 verification complete | Verification Gate | All P0 rows pass | Continue/fix | AI | Not Started
C7-06 | Context/progress synchronized | Context files | No contradiction with code | Update before close | AI | Not Started
C7-07 | Git checkpoint | Commit/checkpoint if configured | Recoverable Phase 7 state | Fix before close | AI | Not Started
C7-08 | Phase 8 handoff | Exact starting point | Phase 8 can resume without rediscovery | Write handoff | AI | Not Started
PHASE 8 HANDOFF TEMPLATE
Phase 7 final state
Completed units
MOM schema/API/UI state
Recipient decision Q03
Gmail API/OAuth configuration state
Email send log/retry/idempotency state
Notes schema/API/UI/history state
Permissions verified for Phase 7
Cost/dependency result
Known issues/deferred items
Git checkpoint
Exact Phase 8 starting unit | D2-10 Full layout editor
Phase 8 prerequisites | Existing editor core + persistence from Phase 5; Phase 7 must not have modified the advanced builder scope
Do not redo | Verified Phase 5/6/7 work unless regression is found

## Playbook Alignment
PLAYBOOK ALIGNMENT
How Phase 7 applies the uploaded app-building playbook.
Playbook principle | Phase 7 application | Evidence | Why it matters | Scope protection | Status | Owner
Architecture before coding | Restore context and inspect existing architecture before MOM/email/notes. | Context audit + plan | Prevents AI improvisation. | No implementation before P7-01. | Applied | AI
Six-file context + agents.md | Read and update durable context. | Context Updates sheet | Enables resumption. | No memory-only state. | Applied | AI
Feature specs | D2-07:D2-09 are explicit units with acceptance tests. | Phase 7 Units | Controls scope. | No later-phase pull-forward. | Applied | AI
One unit at a time | P7-02, P7-03, P7-04 etc. | Unit evidence | Limits regressions. | No stacked unverified work. | Applied | AI
Server-side authorization | MOM send/publish and Notes mutations protected at API boundary. | Verification Gate | Sensitive access cannot rely on UI. | No UI-only security. | Applied | AI
Focused corrections | Fix exact defect and rerun affected tests. | Failure handling | Reduces regression. | No broad refactor. | Applied | AI
Human intervention gates | Stop at Q03, Gmail config, billing or unresolved source decisions. | Human Gates | Preserves human control. | No guessing. | Applied | AI
Cost-aware architecture | Gmail API + existing Google/Open Source stack. | Cost Gate | Maintains ₹0 invariant. | No paid SaaS without approval. | Applied | AI
Review before completion | Phase-specific verification and context sync. | Completion Gate | Prevents false completion. | Full review remains Phase 9. | Applied | AI
Production verification | Deferred to Phase 10. | Handoff | Keeps sequence intact. | No deployment here. | Applied | AI

## Decision Register
PHASE 7 DECISION REGISTER
Record every material decision. Never silently convert an open question into a permanent rule.
ID | Decision/question | Source/default | Decision made | Evidence | Impact | Date | Owner | Status
Q03 | Who receives MOM emails? | Registered project participant emails | PENDING HUMAN CONFIRMATION unless existing authoritative project participant data resolves it | User decision or source-backed existing model | Recipient resolver/send audit |  | User/AI | Open
Q03-BEH | Send timing | On MOM publish/update | Use explicit publish/update event unless user changes this | D2-08 source checklist | Email trigger behavior |  | AI | Default
Q03-FALLBACK | Manual fallback | Manual email fallback listed in Required Tools | Only use if explicitly approved or email service cannot be configured | Required Tools | Operational fallback |  | User/AI | Not selected
COST | Additional cost | ₹0 hard constraint | Preserve ₹0 unless user explicitly changes constraint | Master workbook | Architecture/dependencies |  | User/AI | Resolved

## Workbook Index
WORKBOOK INDEX
Use this sheet to navigate the autonomous Phase 7 control system.
Sheet | Purpose | When AI reads it | Primary authority | Human action? | Status
START HERE | Mission, scope, cost invariant, source decisions | First | Master workbook + Phase 7 scope | No | Mandatory
Autonomous Control | Non-negotiable execution rules | First and continuously | Playbook + phase rules | No | Mandatory
Requirements Freeze | R07/R09 and relevant access requirements | Before planning | Master workbook | Only if unresolved | Mandatory
Phase 7 Units | P7-01:P7-07 implementation sequence | During execution | D2-07:D2-09 + handoff | At gates | Mandatory
MOM Data Model | MOM entity/state rules | Before P7-02 | D2-07 | Possibly | Mandatory
MOM Email Workflow | Server-side email flow | Before P7-03 | D2-08 + Required Tools | Yes if config needed | Mandatory
Q03 Recipient Gate | Open recipient decision | Before/at P7-03 | Open Questions | Yes | Mandatory if unresolved
Notes Workflow | Notes implementation | Before P7-04 | D2-09 | Possibly | Mandatory
Remaining Workflow Boundary | Prevents phase drift | Continuously | 10-phase sequence | No | Mandatory
Human Gates | Exact stop/resume behavior | At blockers | Playbook + source | Yes | Mandatory
Verification Gate | Acceptance evidence | After each unit/closeout | Source acceptance | No unless failure | Mandatory
Dependency & Cost Gate | ₹0/dependency protection | Before new dependency | Required Tools | Yes if violated | Mandatory
Context Updates | Durable context persistence | After changes | Playbook | No | Mandatory
Stop Resume Protocol | Autonomous continuation loop | At every gate | User workflow | Yes at gates | Mandatory
AI Studio Master Prompt | Operational master instruction | At start and when context needs reset | Entire workbook | No | Mandatory
Completion & Phase 8 Handoff | Closeout + next phase | End | 10-phase sequence | No | Mandatory
Playbook Alignment | Method alignment | Audit | Uploaded playbook | No | Reference
Decision Register | Material decisions | At every decision | Open Questions | Yes where marked | Mandatory