## START HERE
PHASE 8 — FULL WEBSITE-BUILDER EXPANSION + CUSTOM PAGES/PUBLISHING
Standalone autonomous execution workbook for Google AI Studio. Upload after Phase 7. AI must implement, verify, stop at genuine human gates, and resume from the exact saved point after confirmation.
Mission | Complete D2-10 through D2-18 of the approved master checklist: full layout, responsive design, styling, animations/interactions, custom CSS, custom JavaScript, themes/templates, plugins/extensions, and pages/assets/preview/publish.
Primary architecture rule | Configure and extend the mature visual-editor engine integrated in Phase 5. Do not rebuild editor internals from zero.
Predecessor | Phase 7 must be verified as complete enough to preserve the application shell, Projects, Finance, HR, MOM, Notes, data layer and existing editor core/persistence.
Autonomous loop | Read workbook → restore Phase 7 context → inspect repo → verify predecessor → plan one unit → implement → verify → update context/progress → continue.
Human-gate loop | When a real human action is required: STOP, state the exact gate and action, wait for user, then resume only after: DONE — RESUME PHASE 8.
Hard cost invariant | ₹0 additional cost beyond existing Google AI Pro. Do not enable billing or introduce paid editor plugins/SaaS/storage/email/hosting dependencies.
Source open questions carried forward | Q01 editor engine, Q06 custom JS permission, Q07 plugin policy, Q08 published-page route/domain. Resolve only if still materially unresolved; otherwise use recorded decisions.
Security boundary | Custom JS must never execute in the main application origin. Use an isolated/sandboxed preview/published runtime as specified by the source.
Plugin boundary | Use the editor's plugin API. Admin-controlled registration/allowlist; do not execute arbitrary unreviewed third-party plugin code.
Phase boundary | D2-19 flexible access and D2-20 full security audit belong to Phase 9. Phase 8 performs only the minimum permission/script-isolation checks needed to prevent unsafe implementation.
Completion | Phase 8 is complete only after D2-10:D2-18 acceptance tests pass, context/progress/Git checkpoint are updated, all human gates are resolved, and a precise Phase 9 handoff exists.

## Autonomous Control
AUTONOMOUS CONTROL
Non-negotiable rules for Phase 8 execution.
ID | Rule | Required behavior | Stop condition | Resume trigger | Evidence | Forbidden | Priority | Status
A8-01 | Read entire source | Read every Phase 8 sheet plus master workbook/context before editing. | Source/context inaccessible or contradictory. | Resolve access/decision; then DONE — RESUME PHASE 8. | Read log/context audit | Guessing requirements | P0 | Mandatory
A8-02 | Restore Phase 7 state | Inspect Phase 7 handoff and actual repo; verify editor core/persistence. | Predecessor incomplete/broken in a way that blocks Phase 8. | Focused predecessor repair or user action. | Smoke tests + tracker | Assuming tracker is correct without code inspection | P0 | Mandatory
A8-03 | Plan before each unit | Identify engine capability, configuration, data changes, security boundary and tests. | Material ambiguity or unsupported engine capability. | Human decision or documented source-backed resolution. | Unit plan | Starting implementation while blocked | P0 | Mandatory
A8-04 | Configure provider-native engine | Use GrapesJS/equivalent mature engine APIs/plugins/configuration. | Requirement would require rebuilding engine internals. | Human gate only if engine cannot support a P0 requirement safely. | Capability evidence | Hand-building a custom editor engine | P0 | Mandatory
A8-05 | One unit at a time | Implement D2-10 → D2-18 sequentially, verifying each. | Unit acceptance fails. | Focused correction then retest. | Unit evidence | Stacking unverified features | P0 | Mandatory
A8-06 | Persist structured editor state | Keep page JSON/HTML/CSS/JS/assets/version metadata in defined persistence boundaries. | Persistence schema conflicts or corrupts existing data. | Stop and repair migration/boundary. | Load/save/version tests | Overwriting authoritative data without migration | P0 | Mandatory
A8-07 | Responsive isolation | Store breakpoint/device-specific styles without corrupting base styles. | Breakpoints leak styles unexpectedly. | Fix scope and rerun responsive matrix. | Desktop/tablet/mobile evidence | Global style mutation without scope | P0 | Mandatory
A8-08 | Custom CSS scope | Store page/component/class CSS separately from structured editor state and scope it correctly. | CSS can escape intended page/component scope. | Stop; correct CSS boundary. | Scope test | Global app CSS injection from page editor | P0 | Mandatory
A8-09 | Custom JS isolation | Never execute arbitrary page JS in app origin. | Sandbox/isolated runtime cannot be established. | STOP for human decision/architecture repair. | Sandbox test | eval in app shell, same-origin unrestricted execution, token access | P0 | Mandatory
A8-10 | Plugin boundary | Use editor plugin API with admin registration/allowlist and version metadata. | Plugin would execute unreviewed arbitrary runtime code. | STOP for Q07 decision/security boundary. | Plugin registration test | Arbitrary third-party plugin execution | P0 | Mandatory
A8-11 | Cost gate | No paid mandatory dependency. | Billing becomes necessary. | STOP; preserve ₹0 or obtain explicit decision to change constraint. | Dependency scan | Enabling billing silently | P0 | Mandatory
A8-12 | Authorization boundary | Respect existing editor/page/project permissions at load/save/publish and sensitive configuration APIs. | UI-only restriction or bypass found. | Focused repair; Phase 9 full audit later. | Direct API denial test | Trusting client roles | P0 | Mandatory
A8-13 | Progress persistence | Update tracker/context after each unit and gate. | State cannot be saved reliably. | Stop before proceeding. | Saved tracker/context | Memory-only progress | P0 | Mandatory
A8-14 | Exact resume | On DONE — RESUME PHASE 8, reread saved state and verify human action. | Human action cannot be verified. | Ask for missing verification. | Gate evidence | Assuming completion | P0 | Mandatory
A8-15 | No phase drift | Do not start Phase 9/10 work. | Later-phase task discovered. | Record/defer unless it blocks safe Phase 8 implementation. | Deferred backlog | Scope creep | P0 | Mandatory

## Requirements Freeze
PHASE 8 REQUIREMENTS FREEZE
Master workbook requirements R17–R27 and D2-10:D2-18 are authoritative.
ID | Requirement | Phase 8 implementation | Access | Acceptance | Source unit | Dependency | Out of scope | Status
R17 | Create new website sheet/page | Multi-page page manager: create/delete/duplicate/rename, draft/published state | Configurable page ACL | Create 2 pages, reload, publish/preview/unpublish | D2-18 | D2-16,D2-17 | Full ACL audit D2-19 | Not Started
R18 | Drag anything anywhere | Editor canvas supports drag/drop/reposition using engine capabilities | Editor access | Move components and persist | D2-10 | D1-19 | Custom engine internals | Not Started
R19 | Resize elements | Canvas/style manager dimensions and resize handles | Editor access | Resize desktop/mobile independently where supported | D2-10 | D1-19 | Unsupported engine internals | Not Started
R20 | Arbitrary columns/layouts | Nested containers, rows, flex/grid, free placement where engine supports | Editor access | Complex multi-column page reloads | D2-10 | D1-19 | 3D/WebGL editor | Not Started
R21 | Animations | Transition/animation controls and reusable interactions | Editor access | Animation works in preview/published page | D2-13 | D2-12 | Unrelated motion framework | Not Started
R22 | Custom CSS | Page-level + component/class-level CSS editor with scoped persistence | Configurable/admin for sensitive pages | CSS applies only intended scope | D2-14 | D2-12 | Server-side CSS compilation | Not Started
R23 | Custom JavaScript | Admin-controlled custom JS editor with isolated sandbox/published runtime | Admin/default restricted | Script works without compromising app shell | D2-15 | D2-13,D2-14 | Untrusted same-origin execution | Not Started
R24 | Themes | Reusable global styles/templates/themes | Admin/configurable | Apply theme to page and persist version | D2-16 | D2-12 | Theme marketplace | Not Started
R25 | Plugins | Plugin registration boundary + test extension | Admin | Plugin adds component/control without changing core | D2-17 | D2-10:D2-16 | Arbitrary third-party runtime | Not Started
R26 | Responsive breakpoint editor | Device manager: desktop/tablet/mobile + custom breakpoints where engine supports | Editor access | Styles persist per device | D2-11 | D2-10 | Unrelated responsive framework | Not Started
R27 | Fully customizable pages | Pages + assets + components + styles + scripts + preview + publish + versions | ACL | Nontrivial custom page end-to-end | D2-10:D2-18 | All Phase 8 units | CDN/analytics | Not Started

## Phase 8 Units
PHASE 8 EXECUTION UNITS
Execute in order. Each unit has its own plan, implementation, verification, evidence and stop/resume behavior.
Unit | Source | Objective | Dependencies | AI execution | Verification | Human gate | Evidence | Out of scope | Status | Started | Completed
P8-01 | Phase 7 handoff / D2-10 prereq | Restore Phase 7 context and inspect existing visual editor core. | Phase 7 complete; D1-19 editor core/persistence | Read all context + repo; identify editor engine/version, current configuration, persistence schema, page model and known limitations; run baseline editor smoke test. | Existing editor mounts; drag/resize/layers/history/persistence baseline still works. | Q01 engine unresolved or predecessor broken materially. | Context audit + baseline test + decision state | No advanced feature implementation yet | Not Started
P8-02 | D2-10 / R18-R20 | Enable full layout editor: nested containers, columns, rows, free placement where engine supports, alignment, sizing, margins/padding/gaps, layers/tree. | P8-01 | Configure engine canvas, component types, container rules, layer manager and dimension controls; preserve existing components; persist hierarchy and dimensions. | Build complex multi-column + nested layout, reload successfully, select from tree, move/resize. | Engine cannot safely support a P0 requirement without custom core rewrite. | Layout test evidence + persisted page JSON | No 3D/WebGL/custom engine | Not Started
P8-03 | D2-11 / R26 | Enable responsive device/breakpoint controls and responsive preview. | P8-02 | Configure device manager, desktop/tablet/mobile, optional custom breakpoints if engine supports; isolate device-specific style rules; add visibility per breakpoint if supported. | Same page renders correctly at configured breakpoints; desktop/mobile changes persist independently. | Engine capability ambiguity or unsupported required behavior. | Responsive matrix/screenshots or test logs | No separate responsive framework | Not Started
P8-04 | D2-12 / R20 | Complete visual styling system: typography, colors, backgrounds, borders, shadows, spacing, dimensions, positioning, flex/grid, reusable classes/tokens. | P8-02,P8-03 | Configure style manager and reusable style classes/tokens; expose only safe properties; verify style serialization. | Change styles on nested elements, reload, verify unrelated components are unchanged. | Style storage conflicts with existing app CSS or engine limitation. | Style persistence/scope tests | No server-side CSS compiler | Not Started
P8-05 | D2-13 / R21 | Enable animations/transitions and interaction/event hooks. | P8-04 | Use engine-native commands/plugins/CSS interactions; support click/hover actions where engine permits; isolate any custom behavior. | Preview and published runtime demonstrate animation/interaction without breaking shell. | Required interaction cannot be safely represented by engine. | Preview/published behavior test | No broad animation framework rewrite | Not Started
P8-06 | D2-14 / R22 | Add page-level and component/class-level custom CSS editor with scoped persistence. | P8-04 | Store CSS separately from structured page JSON/HTML; define scope; expose editor; validate/sanitize or isolate rendering according to architecture. | CSS affects intended page/component only; persists after reload and publish. | Safe scoping/sanitization boundary unresolved. | CSS scope test + persistence evidence | No server-side CSS compilation | Not Started
P8-07 | D2-15 / R23 / Q06 | Add admin-controlled custom JS editor with isolated preview/published runtime. | P8-05,P8-06 | Implement script storage/versioning; enforce admin/default restriction at server boundary; execute only in sandboxed/isolated iframe/published runtime; prevent access to app credentials/session. | Script executes in preview/published page; app shell remains protected; sandbox escape attempts fail. | Q06 unresolved; sandbox cannot be demonstrated; route/domain isolation Q08 affects safety. | Sandbox test + direct API permission test | Never execute arbitrary page JS in app origin | Not Started
P8-08 | D2-16 / R24 | Create reusable themes/templates, global styles, duplicate page, save as template, apply template. | P8-04 | Build theme metadata/versioning, reusable style tokens, template save/apply/duplicate behavior; create independent editable page from template. | Apply theme; create page from template; edit new page without mutating source template. | Theme/template semantics conflict with existing storage. | Template/theme version tests | No marketplace or paid templates | Not Started
P8-09 | D2-17 / R25 / Q07 | Create plugin/extension registration boundary and load at least one test extension. | P8-02:P8-08 | Use editor plugin API; create allowlist/admin registration/version metadata; load a controlled local/test extension that adds a component/control. | Test extension loads and changes editor capability without changing core; unauthorized registration denied. | Q07 unresolved; extension requires arbitrary unreviewed third-party runtime. | Plugin registration + isolation/permission evidence | No arbitrary third-party plugin execution | Not Started
P8-10 | D2-18 / R17/R27 / Q08 | Implement multi-page manager, asset manager, page settings, preview, save/load, publish/unpublish, version snapshots. | P8-08,P8-09 | Create pages per site/project; persist editor JSON/HTML/CSS/JS/assets/version metadata; integrate Drive/app-approved asset path; preview route; draft/published state; immutable version snapshots; rollback where supported. | Create 2 pages; reload; upload/reuse asset; preview; publish; unpublish; inspect version snapshot. | Q08 unresolved if published route/domain is needed for safe runtime; asset/storage boundary unavailable. | E2E page/publish/version evidence | No CDN/page analytics; no production deployment | Not Started
P8-11 | D2-10:D2-18 | Phase 8 integrated builder verification and correction loop. | P8-02:P8-10 | Run full builder matrix; reproduce failures; issue focused corrections; rerun only affected tests plus regression; inspect persistence and runtime isolation. | All P0 Phase 8 acceptance rows pass; no critical builder defect remains. | Any critical security/cost/engine limitation. | Verification matrix + correction log | No full Phase 9 audit | Not Started
P8-12 | Handoff | Update context, progress, Git checkpoint and exact Phase 9 handoff. | P8-11 | Persist decisions, engine config, page schema, CSS/JS/plugin boundaries, known issues; commit/checkpoint if configured; write Phase 9 start state. | Another AI can resume Phase 9 without rediscovery. | Context/Git unavailable or critical unresolved state. | Context diff + Git status + handoff | Do not begin Phase 9 | Not Started

## Full Builder Matrix
FULL BUILDER CAPABILITY MATRIX
Directly derived from the master workbook's Full Builder Matrix and D2-10:D2-18 scope.
Capability | Required | Engine boundary | Configuration | Persistence | Acceptance test | Source unit | Security/cost note | Status | Evidence
Resize | Yes | Canvas/style manager | Configure dimensions/handles | Width/height | Resize desktop/mobile independently | D2-10 | No paid plugin | Not Started
Arbitrary columns | Yes | Nested containers/layout system | Flex/grid/containers | Hierarchy | 3-column + nested layout | D2-10 | Provider-native | Not Started
Free-form placement where supported | Yes | Editor positioning | Absolute/relative modes | Position rules | Independent placement | D2-10 | Validate page scope | Not Started
Layers/component tree | Yes | Editor layer manager | Expose tree panel | Hierarchy | Select nested element | D2-10 | No custom engine | Not Started
Typography | Yes | Style manager | Font/size/weight/line height | Style rules | Style heading/text | D2-12 | Scoped | Not Started
Colors/backgrounds | Yes | Style manager | Controls | Style rules | Change color/background | D2-12 | Scoped | Not Started
Spacing | Yes | Style manager | Margin/padding/gap | Style rules | Change spacing | D2-12 | Scoped | Not Started
Flex/grid | Yes | Style manager | Layout properties | Style rules | Responsive layout | D2-10,D2-12 | Provider-native | Not Started
Responsive breakpoints | Yes | Device manager | Desktop/tablet/mobile + supported custom breakpoints | Device rules | Different mobile layout | D2-11 | No paid responsive SaaS | Not Started
Animations | Yes | Commands/plugins/CSS | Animation controls | Definition | Preview animation | D2-13 | Isolate scripts | Not Started
Interactions/events | Yes | Commands/components | Click/hover actions | Event config | Button interaction | D2-13 | No app-shell mutation | Not Started
Custom CSS | Yes | CSS/style system | Page + component editor | Separate CSS | CSS applies intended scope | D2-14 | Scope/sanitize | Not Started
Custom JavaScript | Yes | Script/component/plugin boundary | Admin editor + sandbox | Separate JS/version | Script works isolated | D2-15 | Critical isolation | Not Started
Themes | Yes | Global style/template system | Theme selector + tokens | Theme version | Apply theme | D2-16 | Admin/configurable | Not Started
Templates | Yes | Page/component storage | Save/duplicate/apply | Versioned | Create page from template | D2-16 | Independent copy | Not Started
Plugins/extensions | Yes | Editor plugin API | Registration + admin controls | Version/allowlist | Load test extension | D2-17 | No arbitrary runtime | Not Started
Pages | Yes | Page manager | Create/rename/delete/duplicate | DB persistence | Create 2 pages | D2-18 | ACL later in D2-19 | Not Started
Assets | Yes | Asset manager | Upload/reuse | Storage + ACL | Upload/reuse asset | D2-18 | Use approved Google Drive/app path | Not Started
Preview | Yes | Editor runtime | Preview route | No edit controls | Matches published | D2-18 | Isolated runtime | Not Started
Publish/unpublish | Yes | Page storage/runtime | Draft/published state | Versioned | Publish then unpublish | D2-18 | Q08 may gate route | Not Started
Version snapshots | Yes | Storage/version layer | Save page versions | Immutable snapshot | Restore prior version | D2-18 | No data loss | Not Started

## Editor Architecture
EDITOR ARCHITECTURE BOUNDARY
Keep the mature editor engine responsible for editing; the app owns authorization, persistence, page lifecycle and isolated runtime.
Layer | Responsibility | Source of truth | Allowed implementation | Must not do | Security boundary | Persistence | Verification | Status | Evidence
Editor engine | Canvas, components, selection, layers, drag/drop, resize, style controls, device manager, native plugins | Mature open-source editor integrated in Phase 5 | Configure APIs/plugins/components | Rebuild editor internals | Editor UI only | Serialized editor state | Mount/config smoke test | Not Started
Page model | Site/project page identity, name, slug/route, draft/published, settings | Application DB | Application API | Store only in browser | Server authorization | Page metadata | CRUD/access test | Not Started
Editor state | HTML/structured components/CSS/config | Application DB/page version | Engine serialization adapted to app schema | Overwrite unrelated data | Server validation | Versioned snapshots | Save/load/reload | Not Started
Custom CSS | Page/component/class-specific CSS | Separate page CSS record/field | Scoped editor + validation/isolation | Inject app-global unsafe CSS | Rendering boundary | Separate CSS/version | Scope test | Not Started
Custom JS | Page script | Separate script/version record | Admin-only default + sandboxed iframe/published runtime | Main-origin arbitrary execution | Sandbox/isolation | Separate JS/version | Sandbox test | Not Started
Themes | Global style tokens + theme metadata | Application DB | Versioned theme config | Mutate source pages unexpectedly | Admin/configurable | Theme versions | Apply/rollback test | Not Started
Templates | Reusable page/component structures | Application DB | Clone-on-apply | Share mutable state unintentionally | Permission checked | Template versions | Independent copy test | Not Started
Plugins | Registered extension metadata + engine plugin code | Controlled repo/config + DB registry if needed | Admin allowlist, versioned | Untrusted arbitrary plugins | Admin-only registration | Plugin metadata | Load test | Not Started
Assets | Images/files used by pages | Google Drive/app-approved storage | Asset metadata + access check | Expose private Drive URLs blindly | Server access boundary | Asset references | Upload/reuse/access test | Not Started
Preview | Read-only isolated rendering | Published/draft page state | Sandboxed/isolated route | Expose editor/admin APIs | Isolation boundary | Read page version | Preview vs publish comparison | Not Started
Publish runtime | Published page snapshot | Immutable version/page state | Safe route/runtime | Share live mutable editor state | Isolation + access | Published version | Publish/unpublish test | Not Started

## Custom JS Safety
CUSTOM JAVASCRIPT SAFETY GATE — D2-15
This is the highest-risk Phase 8 feature. The source explicitly requires an isolated runtime.
Control | Requirement | Implementation | Test | Failure response | Human gate | Forbidden | Source | Priority | Status
JS-01 | Admin/default restricted | Server-side permission check on load/save/publish APIs | Standard user direct API attempt | Fix boundary before proceeding | Q06 if unresolved | Client-only role check | D2-15/Q06 | P0 | Not Started
JS-02 | Isolated runtime | Sandboxed iframe/isolated published runtime; no arbitrary same-origin execution | Execute controlled script and inspect access | STOP; redesign boundary | If safe isolation cannot be proven | eval/script injection into app shell | D2-15 | P0 | Not Started
JS-03 | No app secrets | Published script cannot access app credentials/session tokens/admin APIs | Attempt controlled access | Remove access; rerun | If architecture exposes secrets | Embedding secrets in page | D2-15 | P0 | Not Started
JS-04 | Preview isolation | Preview uses same safe boundary as published runtime | Run script in preview | Fix preview route | If preview needs unsafe exception | Unsafe development-only bypass | D2-15 | P0 | Not Started
JS-05 | Persistence | JS stored separately/versioned from page structure | Save/reload/restore script | Fix serialization | None | Raw concatenation into app code | D2-15 | P0 | Not Started
JS-06 | Failure containment | Script errors do not crash master app shell | Throw controlled error | Fix runtime containment | None | Unhandled same-origin script crash | D2-15 | P0 | Not Started

## Plugin Extension Boundary
PLUGIN / EXTENSION BOUNDARY — D2-17
Use the editor plugin API; admin-controlled registration and no untrusted arbitrary third-party runtime.
Control | Requirement | Implementation | Verification | Human gate | Forbidden | Versioning | Source | Status
PL-01 | Registration API | Admin-only plugin registration through controlled configuration/API | Register test extension | Q07 if policy unresolved | Anonymous/arbitrary plugin upload | Plugin version recorded | D2-17/Q07 | Not Started
PL-02 | Allowlist | Only registered/approved extensions load | Attempt unregistered extension | Stop if allowlist cannot be enforced | Load every third-party package dynamically | Allowlist version | D2-17 | Not Started
PL-03 | Engine-native | Extension uses editor plugin API | Extension adds component/control | None | Modify editor internals | API version recorded | D2-17 | Not Started
PL-04 | Isolation | Plugin cannot access protected app secrets/data without permission | Controlled permission test | Stop if plugin boundary unsafe | Untrusted plugin same-origin access | Capability/version metadata | D2-17 | Not Started
PL-05 | Rollback | Disable/remove extension without corrupting editor | Disable test extension; reopen editor | Fix if state becomes unreadable | Irreversible registration | Registry state tracked | D2-17 | Not Started

## Pages Assets Publishing
D2-18 — PAGES, ASSETS, PREVIEW & PUBLISH
Complete multi-page site/project lifecycle while preserving versioned state.
Step | Capability | Data | Server action | Client behavior | Verification | Human gate | Failure handling | Source | Priority | Status
1 | Create page | siteId/projectId,name,slug,status | Authorize + create | New editable page | Create 2 pages | ACL semantics if unresolved | D2-18 | P0 | Not Started
2 | Duplicate/template page | Source page/version/template ID | Clone immutable source into new page | Independent editable copy | Edit copy; source unchanged | None | Rollback/delete clone safely | D2-16,D2-18 | P0 | Not Started
3 | Assets | Drive asset ID/reference + metadata | Authorize upload/read/link | Asset manager + reuse | Upload image and reuse on page | Storage auth if unavailable | No orphan/private leak | D2-18 | P0 | Not Started
4 | Page settings | Title, slug/route, metadata as supported | Validate and save | Settings panel | Save/reload | Q08 if route semantics unresolved | Reject invalid/conflicting route | D2-18/Q08 | P0 | Not Started
5 | Preview | Draft/version ID | Authorize read-only preview | Preview without editor chrome | Preview matches state | Isolation gate if unsafe | Fail closed | D2-18 | P0 | Not Started
6 | Publish | Page version ID | Authorize + snapshot + publish | Published route | Publish then reload | Q08 if route/domain unresolved | Keep prior published version if failure | D2-18/Q08 | P0 | Not Started
7 | Unpublish | Published page ID | Authorize + change state | Published route unavailable/disabled as designed | Unpublish test | None | Preserve version history | D2-18 | P0 | Not Started
8 | Version snapshot | Page editor state + CSS/JS/assets refs | Create immutable snapshot | Version history/restore if supported | Create 2 versions; restore prior | None | Never overwrite historical snapshot | D2-18 | P0 | Not Started

## Human Gates
HUMAN INTERVENTION GATES
Stop only when human action is actually required. Then resume with the exact command.
Gate | Trigger | AI must not do | Exact user action | After action | Verification | Resume command | Severity | Status | Evidence
HG8-01 | Q01 editor engine still unresolved or current engine cannot safely satisfy scope | Do not silently swap architecture or rebuild editor engine. | Confirm the approved mature editor engine or resolve capability decision. | AI records decision and verifies installed/configured engine. | Engine/package/license/config inspection | DONE — RESUME PHASE 8 | High | Pending
HG8-02 | Q06 custom JS permission unresolved | Do not grant broader JS execution rights. | Confirm who may run custom JS; source default is Admin only. | AI records policy and enforces server-side. | Direct API role test | DONE — RESUME PHASE 8 | Critical | Pending
HG8-03 | Sandbox/isolation cannot be demonstrated | Do not ship same-origin arbitrary JS. | Approve a safe architecture decision or resolve runtime/isolation blocker. | AI verifies sandbox test before continuing. | Sandbox test | DONE — RESUME PHASE 8 | Critical | Pending
HG8-04 | Q07 plugin policy unresolved | Do not load arbitrary third-party plugins. | Confirm admin-controlled/allowlisted policy; source default rejects untrusted third-party runtime. | AI records policy and implements boundary. | Registration/allowlist test | DONE — RESUME PHASE 8 | Critical | Pending
HG8-05 | Q08 published route/domain unresolved and materially affects runtime | Do not invent a route/domain or weaken isolation. | Confirm source default or provide approved route/domain behavior. | AI verifies preview/publish routing. | Published-route test | DONE — RESUME PHASE 8 | High | Pending
HG8-06 | Billing/paid dependency appears necessary | Do not enable billing silently. | Keep ₹0 architecture or explicitly authorize changing the cost constraint. | AI reruns dependency/cost audit. | Dependency scan | DONE — RESUME PHASE 8 | Critical | Pending
HG8-07 | Existing page/editor data migration could risk data loss | Do not perform destructive migration. | Approve migration/backup strategy or provide required action. | AI performs safe migration and verifies rollback. | Backup/schema test | DONE — RESUME PHASE 8 | Critical | Pending
HG8-08 | Predecessor Phase 7 is not actually complete | Do not fake completion or proceed through broken prerequisites. | Resolve predecessor blocker or authorize only a focused prerequisite repair. | AI reruns Phase 7 smoke tests. | Regression evidence | DONE — RESUME PHASE 8 | Critical | Pending

## Open Questions Gate
PHASE 8 OPEN QUESTIONS / DECISIONS
Carry forward only the source questions relevant to Phase 8. Do not silently resolve them.
ID | Question | Source default | AI may do before decision | Human decision required when | Implementation impact | Evidence | Status | Priority
Q01 | Which visual editor engine will be used? | GrapesJS or equivalent mature editor | Inspect actual Phase 5 integration and use it if already approved/working. | Engine is absent, materially different, or cannot satisfy P0 scope safely. | Core editor configuration and plugin API. | Decision register + package/config evidence | Open/Verify | High
Q06 | Who can run custom JavaScript? | Admin only by default | Build permission abstraction and default-restricted UI. | User wants broader access than source default or current policy is absent. | Server ACL + editor controls. | Policy + API test | Open/Verify | Critical
Q07 | Should plugins be arbitrary third-party code? | Admin-controlled plugin registration; no untrusted third-party runtime | Implement allowlist/registration boundary and controlled test extension. | Any request to permit arbitrary third-party runtime. | Plugin security and versioning. | Policy + registration test | Open/Verify | Critical
Q08 | Published custom pages same domain or separate route/subdomain? | Same app domain with isolated page runtime | Use existing route model if already explicitly established and safe. | Route/domain choice changes sandbox/security architecture. | Publish routing and JS isolation. | Decision register + route test | Open/Verify | High
COST | Must app remain ₹0 additional cost? | Yes — hard constraint | Use listed free/open-source routes. | Any mandatory paid dependency appears. | Dependency/hosting/editor choices. | Cost audit | Resolved | Critical

## Verification Gate
PHASE 8 VERIFICATION & ACCEPTANCE
P0 acceptance evidence is mandatory before completion.
ID | Test | Expected result | Method | Evidence | Failure action | Source | Priority | Status | Verified by | Date | Notes
V8-01 | Phase 7 regression | Projects/Finance/HR/MOM/Notes and editor core still work | Smoke tests | Output | Focused correction | Phase 7 handoff | P0 | Not Started
V8-02 | Complex layout | 3-column + nested containers reload correctly | Build/save/reload | Page snapshot | Fix D2-10 | D2-10/R20 | P0 | Not Started
V8-03 | Drag/reposition | Selected elements can move and persist | UI + reload | Test page | Fix D2-10 | D2-10/R18 | P0 | Not Started
V8-04 | Resize | Dimensions persist independently where supported | UI + reload | Test page | Fix D2-10 | D2-10/R19 | P0 | Not Started
V8-05 | Layers/tree | Nested component can be selected from tree | UI test | Evidence | Fix D2-10 | D2-10 | P0 | Not Started
V8-06 | Responsive | Desktop/tablet/mobile styles persist and render correctly | Breakpoint matrix | Screenshots/logs | Fix D2-11 | D2-11/R26 | P0 | Not Started
V8-07 | Styling | Typography/colors/backgrounds/borders/shadows/spacing/layout persist | Style matrix | Test page | Fix D2-12 | D2-12 | P0 | Not Started
V8-08 | Animation | Animation works in preview/published runtime | Preview/publish test | Evidence | Fix D2-13 | D2-13/R21 | P0 | Not Started
V8-09 | Interaction | Click/hover action works without shell corruption | Preview test | Evidence | Fix D2-13 | D2-13 | P0 | Not Started
V8-10 | Custom CSS scope | CSS affects intended page/component only | Scope test | Before/after evidence | Fix D2-14 | D2-14/R22 | P0 | Not Started
V8-11 | Custom JS permission | Only approved role can save/publish JS | Direct API test | 403/allow evidence | Fix or HG8-02 | D2-15/Q06 | P0 | Not Started
V8-12 | Custom JS sandbox | Script works isolated; cannot compromise app shell | Controlled script + escape attempts | Sandbox evidence | STOP + fix/gate | D2-15/R23 | P0 | Not Started
V8-13 | JS failure containment | Script errors do not crash app shell | Controlled throw | Runtime evidence | Fix isolation | D2-15 | P0 | Not Started
V8-14 | Theme | Theme applies and persists/version is retained | Apply/reload | Theme evidence | Fix D2-16 | D2-16/R24 | P0 | Not Started
V8-15 | Template | Template creates independent editable page | Create/apply/edit source+copy | Comparison evidence | Fix D2-16 | D2-16 | P0 | Not Started
V8-16 | Plugin allowlist | Registered test extension loads; unregistered extension denied | Register/load/deny | Registry evidence | Fix or HG8-04 | D2-17/Q07 | P0 | Not Started
V8-17 | Plugin rollback | Disabling extension leaves editor usable | Disable/reopen | Evidence | Fix plugin boundary | D2-17 | P0 | Not Started
V8-18 | Pages | Create 2 pages; rename/duplicate/delete as permitted | Page manager test | Page evidence | Fix D2-18 | D2-18/R17 | P0 | Not Started
V8-19 | Assets | Upload and reuse asset through approved storage path | Upload/reuse/access test | Asset evidence | Fix storage boundary | D2-18 | P0 | Not Started
V8-20 | Preview | Preview matches intended draft/published version without editor controls | Preview test | Evidence | Fix runtime | D2-18 | P0 | Not Started
V8-21 | Publish/unpublish | Publish and unpublish work with version snapshot | Lifecycle test | Publish evidence | Fix D2-18 | D2-18 | P0 | Not Started
V8-22 | Version snapshot | Two versions are retained and prior state can be restored where supported | Version test | Snapshot evidence | Fix persistence | D2-18 | P0 | Not Started
V8-23 | Direct API authorization | Page load/save/publish/config-sensitive APIs enforce server-side authorization | Direct requests | Denial/allow evidence | Focused repair; full audit Phase 9 | D2-18/permissions | P0 | Not Started
V8-24 | Secret hygiene | No secrets in page runtime, bundle, logs or repo | Static scan/config inspection | Scan output | Remove exposure | D2-15 | P0 | Not Started
V8-25 | Cost/dependency | No new paid mandatory dependency | Package/config review | Cost report | HG8-06 | Required Tools | P0 | Not Started
V8-26 | Build/type/lint | Configured checks pass | Run commands | Output | Focused correction | Playbook | P0 | Not Started
V8-27 | Context/progress | Context accurately reflects code and decisions | Review files | Context evidence | Update | Playbook | P0 | Not Started
V8-28 | Phase 9 handoff | Exact next starting point documented | Review handoff | Handoff evidence | Complete before close | Playbook | P0 | Not Started

## Dependency & Cost Gate
DEPENDENCY & COST GATE
Hard ₹0 invariant and source-approved tooling.
Dependency | Source route | Allowed | Do not introduce | Verification | Gate if violated | Reason | Source | Status | Evidence
Editor engine | GrapesJS or equivalent mature open-source editor | Yes | Paid visual editor / mandatory paid plugin | Package/license scan | HG8-01/HG8-06 | Full builder relies on mature engine | Required Tools | Not Started
Editor plugins | Open-source/editor-native plugin API | Yes | Paid plugins or arbitrary third-party runtime | Registry/license scan | HG8-04/HG8-06 | Source boundary | Required Tools/Q07 | Not Started
Database | Firestore | Yes | New DB stack without concrete need | Dependency scan | HG8-06 | Existing architecture | Required Tools | Not Started
Assets | Google Drive API | Yes | Firebase Storage as mandatory dependency | Storage inspection | HG8-06 | Avoid Blaze dependency | Required Tools | Not Started
Background | Existing supported server runtime | Yes | Trigger.dev as mandatory | Dependency scan | HG8-06 | Source says not required | Required Tools | Not Started
Hosting | Existing free/no-cost route | Phase 8 only preview/runtime; no deployment | Paid hosting/CDN | No production deployment | HG8-06 | Phase 10 owns deployment | Required Tools | Not Started
Auth | Firebase Auth | Yes | Clerk | Dependency scan | HG8-06 | Existing auth | Required Tools | Not Started
Realtime | Firestore updates if needed | Yes | Liveblocks | Dependency scan | HG8-06 | No simultaneous cursor collaboration requirement | Required Tools | Not Started

## Context Updates
CONTEXT & PROGRESS UPDATES
Durable state is mandatory for autonomous resumption.
File | Update | Record | When | Verification | Do not record | Owner | Status | Evidence
project-overview.md | Yes | Phase 8 capabilities and page publishing behavior | After requirements/behavior decisions | Read back | Secrets | AI | Not Started
architecture-context.md | Yes | Editor engine, persistence, page model, CSS/JS/plugin isolation, publish runtime | Before P8-11 | No contradictions | Credentials | AI | Not Started
code-standards.md | If needed | Editor integration, serialization, sandbox, extension conventions | When patterns introduced | Matches code | Secrets | AI | Not Started
ai-workflow-rules.md | Yes if new gates discovered | Q01/Q06/Q07/Q08 gate handling and resume rules | At gate/closeout | Resume protocol valid | Secrets | AI | Not Started
ui-context.md | Yes | Advanced editor controls, responsive/style/theme/page manager conventions | After UI work | Matches UI | Private data | AI | Not Started
progress-tracker.md | Yes after every unit | Unit state, evidence, blocker, exact resume point | Every unit | Matches repo | Secrets | AI | Not Started
agents.md | If needed | Phase boundary and editor safety instructions | If repository rules change | Executable | Credentials | AI | Not Started
Decision register | Yes | Q01/Q06/Q07/Q08 + material implementation decisions | Immediately | Source-backed | Secrets | AI | Not Started
Git checkpoint | If configured | Phase 8 checkpoint and rollback reference | Closeout | Working tree recoverable | Tokens | AI | Not Started

## Stop Resume Protocol
STOP / RESUME PROTOCOL
The autonomous loop must repeat until Phase 8 is fully complete.
Step | AI behavior | Required output | User action | AI after resume | Evidence | Forbidden | Status
1 | Execute until a genuine human gate. | State exact gate ID, blocker, completed work, exact user action, and resume phrase. | Perform the requested action only. | Wait. | Saved tracker/gate state | Continuing while blocked | Mandatory
2 | Stop fully. | Example: BLOCKED AT HG8-03 — sandbox isolation cannot yet be demonstrated. Do not continue D2-15. Resolve the isolation configuration, then send DONE — RESUME PHASE 8. | Complete human action. | Resume only after command. | Gate evidence | Guessing or bypassing | Mandatory
3 | Resume exact point. | Do not restart completed units unnecessarily. | Send DONE — RESUME PHASE 8. | Read state, verify gate, continue pending unit. | Verification output | Assuming action succeeded | Mandatory
4 | If verification fails. | Explain remaining technical/human blocker precisely. | Resolve remaining action if human-owned. | Continue after verification passes. | Updated evidence | Pretending verification passed | Mandatory
5 | After every unit. | Update progress/context and mark only verified work complete. | No action unless gate. | Continue next unit. | Unit evidence | Memory-only state | Mandatory
6 | At completion. | Provide final report and Phase 9 handoff; stop. | No automatic Phase 9 execution. | End Phase 8. | Handoff + checkpoint | Starting next phase automatically | Mandatory

## AI Studio Master Prompt
GOOGLE AI STUDIO — PHASE 8 MASTER EXECUTION PROMPT
Operational instruction. The workbook remains the specification; this prompt tells the agent how to execute it.
MASTER PROMPT
You are the autonomous implementation agent for PHASE 8 of the Master Website application. AUTHORITATIVE SOURCES 1. This entire Phase 8 workbook. 2. The uploaded Master_Website_2_Day_App_Build_Checklist_ZERO_ADDITIONAL_COST_Google_AI_Studio.xlsx. 3. The actual repository/codebase. 4. Existing durable project context and the Phase 7 handoff. MISSION Complete ONLY D2-10 through D2-18: D2-10 Full layout editor D2-11 Responsive design D2-12 Styling system D2-13 Animations/interactions D2-14 Custom CSS D2-15 Custom JavaScript D2-16 Themes/templates D2-17 Plugins/extensions D2-18 Pages/assets/preview/publish DO NOT IMPLEMENT D2-19 Flexible access as a full phase D2-20 full security audit D2-21 full E2E QA D2-23 review D2-24/D2-25 production deployment/handover Those belong to later phases. Perform only the focused authorization and isolation checks necessary to make Phase 8 safe. CORE ARCHITECTURE - Use the mature editor engine integrated in Phase 5 (GrapesJS or the source-approved equivalent). - Configure provider-native capabilities. Do not rebuild editor internals from zero. - Application owns authorization, persistence, page lifecycle, version metadata and safe runtime boundaries. - Store structured editor state separately from page-level CSS and custom JS. - Preserve version snapshots. - Use Google Drive/app-approved asset storage; do not introduce Firebase Storage as a mandatory dependency. - Keep the entire build at ₹0 additional cost. AUTONOMOUS EXECUTION LOOP 1. Read this entire workbook and master workbook. 2. Restore project-overview, architecture-context, code-standards, ai-workflow-rules, ui-context, progress-tracker, agents.md and Phase 7 handoff. 3. Inspect the actual repository. Do not trust trackers without checking code. 4. Verify Phase 7 predecessor and editor core. 5. Plan P8-01. 6. Execute exactly one unit. 7. Verify it with its acceptance criteria. 8. Update progress/context/evidence. 9. Continue to the next unit. 10. If a human gate occurs, STOP completely. STOP/RESUME When a human action is required: - State the exact gate ID. - Explain exactly why it blocks. - State what has already been completed. - State exactly what the user must do. - Never ask for passwords, private keys, OAuth secrets or tokens in chat. - Wait for: DONE — RESUME PHASE 8 After that command: - reread saved state, - verify the requested human action, - resume from the exact blocked point, - do not redo completed work unnecessarily. OPEN QUESTIONS Q01: Use the already approved/working mature editor engine if one exists. If not, stop for the engine decision. Q06: Custom JS is Admin only by default unless a documented decision says otherwise. Q07: Plugins are admin-controlled/allowlisted; no arbitrary untrusted third-party runtime. Q08: Source default is same app domain with isolated page runtime. If route/domain behavior remains materially unresolved, stop rather than inventing it. COST: ₹0 additional cost is hard. Do not enable billing. CRITICAL CUSTOM JAVASCRIPT RULE Never execute arbitrary page JS in the main application origin. Custom JS must run only inside a sandboxed/isolated preview/published runtime. The page script must not access app credentials, session tokens, admin APIs or unrelated project data. Test permission and isolation with direct API and runtime tests. If safe isolation cannot be demonstrated, STOP. CRITICAL PLUGIN RULE Use the editor's plugin API. Admin registration/allowlist is required. Record plugin name/version/API compatibility. Load one controlled test extension. Do not create a marketplace or arbitrary third-party plugin loader. PERSISTENCE RULES Persist: - page metadata, - structured editor state, - CSS separately, - JS separately, - assets references, - themes/templates, - plugin registration metadata, - draft/published state, - version snapshots. Do not overwrite immutable historical versions. RESPONSIVE RULE Desktop/tablet/mobile styles must not accidentally mutate each other. Use the editor device manager and style rules. Test independent breakpoint changes. PUBLISHING RULE Preview and published pages must render from a safe, versioned runtime representation, not from the live editor UI state. Support publish and unpublish. Create version snapshots. Do not deploy production infrastructure in Phase 8. VERIFICATION At minimum verify: - complex nested multi-column layout, - drag/reposition, - resize, - layers/tree, - desktop/tablet/mobile, - typography/colors/backgrounds/borders/shadows/spacing/flex/grid, - animations, - interactions, - scoped custom CSS, - custom JS permissions, - custom JS sandbox, - JS failure containment, - themes, - templates, - plugin registration/allowlist/rollback, - two pages, - assets, - preview, - publish/unpublish, - version snapshots, - direct API authorization for relevant editor endpoints, - secret hygiene, - no paid mandatory dependency, - build/type/lint, - context/progress, - Phase 9 handoff. CORRECTION LOOP If a verification fails: 1. identify the smallest root cause, 2. make the smallest safe correction, 3. rerun the affected test, 4. rerun related regression tests, 5. update the correction log, 6. continue only after acceptance passes. COMPLETION Do not declare Phase 8 complete until all P0 D2-10:D2-18 acceptance criteria pass, all required human gates are resolved, context/progress are synchronized, cost remains ₹0, and the Phase 9 handoff is written. FINAL REPORT Include: - units completed, - editor engine/version/configuration, - builder capabilities enabled, - page/CSS/JS/theme/template/plugin architecture, - custom JS isolation result, - plugin boundary result, - publishing/asset/version result, - human gates and decisions, - verification results, - dependency/cost audit, - context/Git checkpoint, - known deferred issues, - exact Phase 9 starting point. STOP AFTER PHASE 8. Do not automatically execute Phase 9.

## Completion & Phase 9 Handoff
PHASE 8 COMPLETION GATE & PHASE 9 HANDOFF
Phase 8 ends here. No automatic Phase 9 execution.
Gate | Requirement | Evidence | Pass condition | If not passed | Owner | Status | Completed | Phase 9 relevance | Notes
C8-01 | D2-10 complete | Layout matrix | Complex layout/reposition/resize/tree passes | Focused correction | AI | Not Started |  | Foundation for integration/security
C8-02 | D2-11 complete | Responsive matrix | Breakpoints/device styles pass | Focused correction | AI | Not Started |  | Responsive security/QA
C8-03 | D2-12 complete | Style matrix | Styling passes without collateral mutation | Focused correction | AI | Not Started |  | Integration
C8-04 | D2-13 complete | Animation/interaction tests | Preview/publish behavior passes | Focused correction | AI | Not Started |  | QA
C8-05 | D2-14 complete | CSS scope tests | Scoped CSS persists/renders safely | Focused correction | AI | Not Started |  | Security audit
C8-06 | D2-15 complete | Sandbox + permission tests | JS isolated and permissioned | HG8-03 or correction | AI | Not Started |  | Critical security input
C8-07 | D2-16 complete | Theme/template tests | Independent reusable assets work | Focused correction | AI | Not Started |  | Integration
C8-08 | D2-17 complete | Plugin tests | Allowlist + test extension + rollback pass | HG8-04 or correction | AI | Not Started |  | Security audit
C8-09 | D2-18 complete | Page/publish tests | Pages/assets/preview/publish/version pass | HG8-05 or correction | AI | Not Started |  | Integration/security
C8-10 | Verification complete | Verification Gate | All P0 rows pass | Continue/fix | AI | Not Started |  | Phase 9 baseline
C8-11 | Context/Git complete | Context + checkpoint | Recoverable state | Update before close | AI | Not Started |  | Phase 9 resume
C8-12 | Phase 9 handoff complete | Handoff below | Exact next starting point recorded | Write before close | AI | Not Started |  | D2-19 onward
PHASE 9 HANDOFF TEMPLATE
Phase 8 final state
Editor engine/version/configuration
D2-10 layout state
D2-11 responsive state
D2-12 styling state
D2-13 animation/interaction state
D2-14 custom CSS boundary
D2-15 custom JS permission + sandbox boundary
D2-16 themes/templates state
D2-17 plugin registration/allowlist state
D2-18 pages/assets/preview/publish/version state
Q01/Q06/Q07/Q08 decisions
Cost/dependency audit
Known issues/deferred items
Git checkpoint
Exact Phase 9 starting point | D2-19 Flexible access → D2-20 Security audit → later Phase 9 integration/QA
Do not redo | Verified Phase 5/6/7/8 work unless regression is found

## Decision Register
PHASE 8 DECISION REGISTER
Never silently turn an open source question into a permanent implementation rule.
ID | Question | Source/default | Decision | Evidence | Implementation impact | Date | Owner | Status
Q01 | Visual editor engine | GrapesJS or equivalent mature editor | Use existing Phase 5 approved engine if present; otherwise gate. | Repo/package/config evidence | Editor API/configuration |  | AI/User | Open
Q06 | Custom JavaScript permission | Admin only by default | Pending if not already decided. | User/source decision | Server ACL/editor controls |  | AI/User | Open
Q07 | Plugin policy | Admin-controlled; no untrusted third-party runtime | Pending if not already decided. | User/source decision | Registry/allowlist/isolation |  | AI/User | Open
Q08 | Published page route/domain | Same app domain with isolated runtime | Use recorded Phase 1 decision if present; otherwise gate if material. | Context/decision evidence | Preview/publish routing |  | AI/User | Open
COST | Additional cost | ₹0 hard constraint | Preserve. | Master workbook | No billing/paid dependency |  | AI | Resolved

## Playbook Alignment
PLAYBOOK ALIGNMENT
Phase 8 maps the source playbook methodology to executable controls.
Principle | Phase 8 implementation | Evidence | Scope protection | Human gate | Status | Owner | Notes
Architecture before coding | Restore Phase 7 context, inspect editor architecture, decide engine capability before feature changes. | P8-01 context/baseline | No feature coding before baseline | Q01 if needed | Applied | AI
Provider-native capabilities | Configure mature editor rather than hand-building canvas engine. | P8-02:P8-10 | No custom editor internals | Engine capability gate | Applied | AI
Feature specs | D2-10:D2-18 each has a dedicated execution unit. | Phase 8 Units | No D2-19+ implementation | Per unit | Applied | AI
One unit at a time | Implement → verify → persist state → continue. | Unit evidence | No stacked unverified work | At blockers | Applied | AI
Security at boundaries | Custom JS/plugin/page mutation boundaries protected server-side/isolated. | JS/plugin tests | Full audit deferred to Phase 9 | HG8-02/HG8-03/HG8-04 | Applied | AI
Focused correction loop | Small root-cause fix and targeted regression. | Correction log | No broad refactor | If unsafe fix required | Applied | AI
Human intervention | Explicit gates for open decisions, unsafe isolation, billing and data migration. | Human Gates | No guessing | DONE — RESUME PHASE 8 | Applied | AI
Context persistence | Update durable context and progress after every unit. | Context Updates | No memory-only progress | None | Applied | AI
Review before handoff | P0 verification and exact Phase 9 handoff. | Completion Gate | No automatic next phase | None | Applied | AI

## Workbook Index
WORKBOOK INDEX
Navigation map for autonomous Phase 8 execution.
Sheet | Purpose | When read | Authority | Human action | Status
START HERE | Mission, scope, boundaries, cost and source decisions | First | Master workbook | Only if gate | Mandatory
Autonomous Control | Execution rules | First/continuous | Playbook | At gates | Mandatory
Requirements Freeze | R17-R27 | Planning | Master workbook | If unresolved | Mandatory
Phase 8 Units | P8-01:P8-12 sequence | Execution | D2-10:D2-18 | At gates | Mandatory
Full Builder Matrix | Capability-level specification | During builder work | Full Builder Matrix | If unsupported | Mandatory
Editor Architecture | Layer boundaries | Before/through implementation | Feature specs + architecture | If architecture conflict | Mandatory
Custom JS Safety | D2-15 safety controls | Before JS and verification | D2-15/Q06 | Yes if unresolved | Mandatory
Plugin Extension Boundary | D2-17 controls | Before plugin work | D2-17/Q07 | Yes if unresolved | Mandatory
Pages Assets Publishing | D2-18 lifecycle | Before page/publish work | D2-18/Q08 | Yes if unresolved | Mandatory
Human Gates | Stop/resume gates | At blockers | Source + playbook | Yes | Mandatory
Open Questions Gate | Q01/Q06/Q07/Q08/COST | Decision points | Open Questions | Yes where open | Mandatory
Verification Gate | P0 acceptance evidence | After each unit/closeout | Master checklist | No unless failure | Mandatory
Dependency & Cost Gate | No-cost protection | Before dependencies | Required Tools | Yes if violated | Mandatory
Context Updates | Durable state | After changes | Playbook | No | Mandatory
Stop Resume Protocol | Exact autonomous loop | At every gate | User workflow | Yes | Mandatory
AI Studio Master Prompt | Operational execution instructions | Start/reset | Entire workbook | No | Mandatory
Completion & Phase 9 Handoff | Closeout and next phase | End | 10-phase sequence | No | Mandatory
Decision Register | Material decisions | At each decision | Open Questions | Yes | Mandatory
Playbook Alignment | Method audit | Review | Playbook | No | Reference