## START HERE
PHASE 9 — INTEGRATION, SECURITY, PERMISSIONS, QA & CORRECTION LOOP
Standalone autonomous execution workbook for Google AI Studio. Grounded in the master workbook's D2-19 through D2-23. Phase 10 deployment remains explicitly out of scope.
Mission | Integrate all completed modules, enforce access controls, perform the full security audit, execute end-to-end QA and financial testing, then review AI-generated code and resolve findings.
Source scope | D2-19 Flexible access; D2-20 Security audit; D2-21 End-to-end QA; D2-22 Financial test suite; D2-23 Code review.
Explicitly deferred | D2-24 Production deployment and D2-25 production smoke/handover remain Phase 10.
Autonomous loop | Read workbook/spec → restore Phase 8 context → inspect actual repo → plan → implement/test one unit → verify → persist evidence → continue.
Human-gate loop | When human action is required: STOP. Explain exact gate/action. Wait for: DONE — RESUME PHASE 9. Verify the action before continuing.
Cost invariant | ₹0 additional cost beyond existing Google AI Pro. D2-20 includes explicit zero-cost verification; do not silently enable billing.
Security standard | Server-side authorization at API/mutation boundaries; protect sensitive Finance/HR; isolate custom JS; protect Drive assets; audit admin endpoints, XSS, CSRF, injection, secrets and published-page boundaries.
QA scope | Full critical journey: login → project → countdown → Excel upload → expense → OOP → salary → report → MOM email → custom page → publish → responsive preview.
Financial QA | Allowance threshold, excess reimbursement, carry-forward, partial payment, duplicate claim prevention and report reconciliation.
Review rule | Review AI-generated code, dependencies, editor integration, authorization and business calculations. Fix findings only; no unrelated refactor.
Completion | Only complete Phase 9 when all P0 tests pass, critical security findings are resolved/documented, financial totals reconcile, review findings are resolved/documented, context/Git state is updated, and Phase 10 handoff is complete.

## Autonomous Control
AUTONOMOUS CONTROL
Non-negotiable execution rules for Phase 9.
ID | Rule | Required behavior | Stop condition | Resume trigger | Evidence | Forbidden | Priority | Status
A9-01 | Read entire source | Read every sheet in this workbook, master workbook, Phase 8 handoff and durable context. | Source/context inaccessible or contradictory. | Resolve issue; DONE — RESUME PHASE 9. | Source-read/context audit | Guessing missing requirements | P0 | Mandatory
A9-02 | Restore predecessor state | Inspect actual repo and verify Phase 8 builder/page/publish state. | Phase 8 incomplete/broken in a blocking way. | Focused repair or user action. | Regression output | Trusting tracker without code inspection | P0 | Mandatory
A9-03 | Plan each unit | Define test scope, expected behavior, evidence and correction path before changes. | Material ambiguity. | Human gate or source-backed resolution. | Unit plan | Blind patching | P0 | Mandatory
A9-04 | Server-side authorization | Test and enforce access at API/load/save/publish/mutation boundaries. | UI-only protection or direct API bypass. | Fix before proceeding. | Direct API tests | Client-trusted roles | P0 | Mandatory
A9-05 | Sensitive-data isolation | Salary, investments, other-user OOP and protected files must not leak. | Cross-user access succeeds. | Stop and correct boundary. | 403/denial evidence | Broadening access for convenience | P0 | Mandatory
A9-06 | Security audit | Audit auth, authz, files, JS, XSS, CSRF, injection, storage, admin endpoints, secrets, published runtime. | Critical finding remains unexplained. | Focused correction; human gate if architecture decision needed. | Finding register | Marking unresolved critical issue as acceptable | P0 | Mandatory
A9-07 | Full critical journey | Run exact master checklist journey end to end. | Critical journey fails. | Focused correction and rerun. | Journey evidence | Skipping failing stages | P0 | Mandatory
A9-08 | Financial reconciliation | Use exact Phase 6 policy/config and verify totals; do not invent Q05 semantics. | Totals disagree or policy ambiguous. | Human decision if Q05 still unresolved. | Calculation evidence | Changing accounting semantics silently | P0 | Mandatory
A9-09 | Correction loop | For each finding: reproduce → root cause → smallest fix → targeted regression → update finding. | Fix causes regression or cannot be safely made. | Human gate or defer with evidence. | Correction log | Unrelated refactor | P0 | Mandatory
A9-10 | Zero-cost verification | Inspect dependencies/config/environment for billing requirements. | Paid service is mandatory or unexpectedly enabled. | STOP; user decides or architecture changes to preserve ₹0. | Cost audit | Enabling billing silently | P0 | Mandatory
A9-11 | Secrets hygiene | No secrets in repo/client bundle/logs/chat; production secrets remain Phase 10. | Secret exposure found. | Remove/reconfigure before proceeding. | Secret scan | Printing tokens | P0 | Mandatory
A9-12 | Progress persistence | Update tracker/context after each unit and after each gate. | State cannot be saved. | Stop before proceeding. | Tracker/context | Memory-only progress | P0 | Mandatory
A9-13 | Exact resume | After DONE — RESUME PHASE 9, verify human action before continuing. | Verification fails. | Ask for only remaining action. | Gate evidence | Assuming user action succeeded | P0 | Mandatory
A9-14 | No deployment | Do not perform production deployment or final production smoke. | Deployment task appears necessary. | Record for Phase 10 handoff. | Handoff | Deploying early | P0 | Mandatory

## Requirements Freeze
PHASE 9 REQUIREMENTS FREEZE
Master workbook R01-R27, Permissions Matrix, and D2-19:D2-23 are authoritative.
ID | Requirement | Phase 9 treatment | Access/security | Acceptance | Source checklist | Dependency | Out of scope | Status
R01 | Master shell Projects/Finance/HR | Regression across all modules | Existing ACL | All modules open according to role | D2-21 | Phases 1-8 | Deployment | Not Started
R05 | Expense file + structured ledger | Regression + financial QA | Project access | File/records/totals reconcile | D2-21,D2-22 | Phase 6 | Feature redesign | Not Started
R07 | MOM email | Regression + security/privacy test | Project/editor recipient rules | MOM send works and logs | D2-21 | Phase 7 | Campaign system | Not Started
R08 | OOP reimbursement | Financial QA | Employee own/admin | Claim-to-payout flow reconciles | D2-22 | Phase 6 | Bank integration | Not Started
R10 | Admin salary | Direct API denial for non-admin | Admin only | Unauthorized read/write blocked | D2-19,D2-20 | Phase 6 | Payroll bank transfer | Not Started
R11 | Salary carry-forward | Financial QA | Admin | No data loss | D2-22 | Phase 6 | Payroll integration | Not Started
R13 | ₹5000 OOP rule | Financial QA using configured policy | Admin config/employee claims | Threshold cases pass | D2-22 | Q05/Phase 6 | Policy redesign | Not Started
R14 | Admin investments | Direct API denial for standard users | Admin only | Unauthorized access blocked | D2-19,D2-20 | Phase 6 | Recommendations | Not Started
R15 | Anyone with access can edit permitted pages | ACL load/save/publish tests | Server enforced | Allowed edit succeeds; disallowed direct API fails | D2-19 | Phase 3/8 | Enterprise SSO | Not Started
R16 | Admin-controlled protected pages | Protected Finance/salary/investments/pages | Server enforced | Non-admin blocked | D2-19,D2-20 | Permissions Matrix | Deployment | Not Started
R17-R27 | Full builder capabilities | Integrated QA + security review | Page/editor/plugin/JS boundaries | All critical builder flows pass | D2-19:D2-23 | Phase 8 | New builder features | Not Started

## ACL Verification Matrix
D2-19 — FLEXIBLE ACCESS & SERVER-SIDE ACL
Verify the Permissions Matrix against real API behavior. This is not a UI-only test.
Capability | Admin | Standard user with access | Employee self | Expected server enforcement | Direct API test | Expected denial/allow | Sensitive | Source | Priority | Status
Dashboard | RW | RW permitted | Own/read permitted | Yes | Call route as each role | Allowed per module ACL | No | Permissions Matrix | P0 | Not Started
Create project | Yes | Configurable | No | Yes | POST as each role | Allow only configured roles | No | Permissions Matrix | P0 | Not Started
Edit project | Yes | Member/editor | No | Yes | PUT/PATCH as member/nonmember | Member allowed; nonmember denied | No | Permissions Matrix | P0 | Not Started
Delete project | Yes | Configurable | No | Yes | DELETE as each role | Only authorized role | No | Permissions Matrix | P0 | Not Started
Checklist Excel | Yes | Editor | No | Yes | Read/write file route | Authorized only | Potential | Permissions Matrix | P0 | Not Started
Expense Excel | Yes | Editor | No | Yes | Read/write route | Authorized only | Financial | Permissions Matrix | P0 | Not Started
Budget allocations | Yes | Permitted | No | Yes | Read/write API | Unauthorized denied | Financial | Permissions Matrix | P0 | Not Started
Own OOP claim | Yes | Yes | Yes | Yes | Create/read own | Own allowed | Financial | Permissions Matrix | P0 | Not Started
Other employee OOP | Yes | Configurable/no by default | No | Yes | Read/write another employee | Denied unless explicit permission | Financial | Permissions Matrix | P0 | Not Started
Salary | Yes | No | No | Yes | Direct GET/POST/PATCH | Non-admin denied | Highly sensitive | Permissions Matrix | P0 | Not Started
Salary report | Yes | No | No | Yes | Direct API | Non-admin denied | Highly sensitive | Permissions Matrix | P0 | Not Started
Investments | Yes | No | No | Yes | Direct API | Non-admin denied | Sensitive | Permissions Matrix | P0 | Not Started
MOM | Yes | Editor if permitted | No | Yes | Read/write/publish | ACL respected | Business | Permissions Matrix | P0 | Not Started
Custom page create | Yes | Configurable | No | Yes | Direct create | Configured role only | No | Permissions Matrix | P0 | Not Started
Custom page edit | Yes | Page ACL | No | Yes | Direct save | Page ACL respected | No | Permissions Matrix | P0 | Not Started
Custom CSS | Yes | Configurable/admin sensitive | No | Yes | Direct save | Role policy respected | Potential | Permissions Matrix | P0 | Not Started
Custom JS | Yes | Admin/default restricted | No | Yes | Direct save/publish | Non-admin denied by default | Critical | Permissions Matrix | P0 | Not Started
Themes/templates | Yes | Configurable | No | Yes | Apply/edit | ACL respected | No | Permissions Matrix | P0 | Not Started
Plugins | Yes | Admin | No | Yes | Register/load | Non-admin denied | Critical | Permissions Matrix | P0 | Not Started
Publish | Yes | Configurable | No | Yes | Publish API | Only authorized role | Critical | Permissions Matrix | P0 | Not Started
Drive assets | Yes | Permitted | Own/assigned | Yes | Direct asset read/write | Unauthorized denied | Potential | Permissions Matrix | P0 | Not Started

## Security Audit
D2-20 — SECURITY AUDIT
Audit the actual application, not only source code. Every finding must be reproduced, classified and resolved or documented.
ID | Area | Audit question | Test method | Expected secure result | Finding severity | Correction rule | Human gate if | Source | Priority | Status | Evidence
S9-01 | Authentication | Can unauthenticated users reach protected APIs/pages? | Unauthenticated direct requests | 401/403 and no sensitive data | Critical/High | Fix boundary | Auth architecture issue | D2-20 | P0 | Not Started
S9-02 | Authorization | Can role/member restrictions be bypassed by direct API? | Cross-role API requests | Server denial | Critical | Fix before completion | Unresolvable ACL semantics | D2-19 | P0 | Not Started
S9-03 | Salary/investments | Can standard user read sensitive records? | Direct API + alternate IDs | Denied | Critical | Fix before completion | Data model flaw | D2-20 | P0 | Not Started
S9-04 | OOP | Can employee read/write another employee's claims? | ID substitution | Denied unless explicitly permitted | High | Fix boundary | Policy ambiguity | D2-20 | P0 | Not Started
S9-05 | Drive/files | Can unauthorized user access project assets by guessed/reference ID? | Direct file/API access | Denied | Critical/High | Fix access boundary | Storage architecture issue | D2-20 | P0 | Not Started
S9-06 | Custom JS | Can page JS access app session, secrets or admin APIs? | Sandbox runtime tests | No access | Critical | Fix isolation | Sandbox architecture decision | D2-15,D2-20 | P0 | Not Started
S9-07 | XSS | Can user content execute unintended script in app origin? | Payload tests in notes/MOM/page content | Escaped/sanitized/isolated | Critical/High | Fix rendering boundary | Architecture ambiguity | D2-20 | P0 | Not Started
S9-08 | CSRF | Can state-changing endpoints be triggered cross-origin without authorization? | Cross-origin request tests | Rejected/validated | High | Fix CSRF strategy | Runtime limitation | D2-20 | P0 | Not Started
S9-09 | Injection | Do IDs/query/filter inputs allow injection or unsafe queries? | Malformed inputs | Validated/parameterized | High | Fix validation/query boundary | Data layer issue | D2-20 | P0 | Not Started
S9-10 | Admin endpoints | Can non-admin invoke admin-only functions? | Direct endpoint calls | Denied | Critical | Fix server authorization | Role architecture issue | D2-20 | P0 | Not Started
S9-11 | Secrets | Are tokens/keys/secrets in repo/client bundle/logs? | Static scan + bundle inspect | None | Critical | Remove/rotate/configure | Credential rotation may require user | D2-20 | P0 | Not Started
S9-12 | Published runtime | Can published page access master app internals? | Runtime/browser tests | Isolated | Critical | Fix route/sandbox | Q08 architecture decision | D2-20 | P0 | Not Started
S9-13 | Plugin boundary | Can unregistered plugin execute? | Registry bypass test | Denied | Critical | Fix allowlist | Q07 decision | D2-20 | P0 | Not Started
S9-14 | Storage rules | Can client write arbitrary sensitive records? | Tampered payload tests | Server validates owner/role | Critical | Fix mutation rules | Data architecture issue | D2-20 | P0 | Not Started
S9-15 | Error leakage | Do errors reveal secrets/internal paths? | Trigger controlled errors | Safe user-facing errors | Medium/High | Sanitize logs/errors | If provider behavior blocks | D2-20 | P1 | Not Started
S9-16 | Dependency audit | Any vulnerable/unapproved/paid dependency introduced? | Package/license/config scan | Approved + cost compliant | High/Critical | Remove/replace | Billing/engine decision | D2-20 | P0 | Not Started

## End-to-End QA
D2-21 — END-TO-END QA
Run the exact critical user journey from the master checklist and capture exact failures.
Step | Journey | Expected result | Test data | Evidence | Failure severity | Correction | Regression | Source | Priority | Status | Notes
1 | Login | Authorized user logs in; unauthorized user cannot enter protected app | Admin + standard + employee test users | Auth logs/output | Critical | Fix auth | Repeat login tests | D2-21 | P0 | Not Started
2 | Project | Project opens and permissions apply | Existing test project | Screenshot/log | High | Fix project ACL | Project smoke | D2-21 | P0 | Not Started
3 | Countdown | Event countdown is accurate and handles expiry | Known event date/time | UI evidence | Medium | Fix time logic | Countdown smoke | D2-21 | P1 | Not Started
4 | Checklist Excel | Upload/reload/access works | Known workbook | File evidence | High | Fix storage | Upload regression | D2-21 | P0 | Not Started
5 | Expense | Expense file + structured ledger calculate correctly | Known allocation/expense data | Totals evidence | Critical | Fix ledger | Expense regression | D2-21 | P0 | Not Started
6 | OOP | Employee claim flows through approval/payout | Known claims | Ledger evidence | Critical | Fix workflow | OOP regression | D2-21 | P0 | Not Started
7 | Salary | Admin sees salary; non-admin blocked | Known salary period | API/UI evidence | Critical | Fix ACL | Salary regression | D2-21 | P0 | Not Started
8 | Report | Salary report matches ledger | Known ledger | Report evidence | Critical | Fix report | Report regression | D2-21 | P0 | Not Started
9 | MOM email | MOM publish/update sends to approved recipients and logs | Controlled recipients | Send log + receipt | Critical | Fix email | MOM regression | D2-21 | P0 | Not Started
10 | Custom page | Create/edit custom page using full builder | Nontrivial test page | Page evidence | Critical | Fix builder | Builder regression | D2-21 | P0 | Not Started
11 | Publish | Publish custom page and load it | Test page/version | Runtime evidence | Critical | Fix publish | Publish regression | D2-21 | P0 | Not Started
12 | Responsive preview | Desktop/tablet/mobile render correctly | Responsive test page | Screenshots/log | High | Fix responsive | Builder regression | D2-21 | P0 | Not Started
13 | Notes | Project notes save/reload with ACL | Test note | Evidence | High | Fix notes | Notes regression | D2-21 | P0 | Not Started
14 | Cross-module regression | Navigation and permissions remain intact after full journey | All modules | Regression report | Critical | Focused fix | Repeat affected journey | D2-21 | P0 | Not Started

## Financial Test Suite
D2-22 — FINANCIAL TEST SUITE
Use the exact Phase 6 policy/configuration. Do not reinterpret the ₹5,000 rule during QA.
ID | Scenario | Expected result | Test data | Calculation/evidence | Failure severity | Correction | Source | Priority | Status | Notes
F9-01 | Below ₹5,000 threshold | Configured policy result is correct | Claim below threshold | Payout/reimbursement calculation | Critical | Fix engine/config | D2-22/Q05 | P0 | Not Started
F9-02 | Exactly ₹5,000 | Configured policy result is correct | Claim exactly threshold | Calculation evidence | Critical | Fix boundary | D2-22/Q05 | P0 | Not Started
F9-03 | Above ₹5,000 | Configured threshold + extra line-item semantics are applied exactly as configured | Claim above threshold | Calculation evidence | Critical | Fix engine/config | D2-22/Q05 | P0 | Not Started
F9-04 | Carry-forward | Pending salary carries without loss/double count | Prior pending period | Ledger reconciliation | Critical | Fix ledger | D2-22 | P0 | Not Started
F9-05 | Partial salary payment | Remaining due is correct | Partial payment | Ledger reconciliation | Critical | Fix ledger | D2-22 | P0 | Not Started
F9-06 | Duplicate claim | Duplicate submission does not create duplicate payout | Same claim twice | Claim IDs + payout records | Critical | Fix idempotency | D2-22 | P0 | Not Started
F9-07 | Approved claim | Only approved claim enters payout | Approved/rejected pair | Payout reconciliation | Critical | Fix approval boundary | D2-22 | P0 | Not Started
F9-08 | Rejected claim | Rejected claim never enters payout | Rejected claim | Payout evidence | Critical | Fix workflow | D2-22 | P0 | Not Started
F9-09 | Salary report | Report totals match ledger | Known month | Report vs ledger | Critical | Fix report | D2-22 | P0 | Not Started
F9-10 | Month close/reopen | Historical period remains consistent | Two periods | Before/after comparison | High | Fix period logic | D2-22 | P1 | Not Started
F9-11 | Allocation vs spend | Budget allocations and spend reconcile | Known project budget | Totals | Critical | Fix expense ledger | D2-22 | P0 | Not Started

## Correction Loop
FOCUSED CORRECTION LOOP
Every failure becomes a bounded correction, not a broad re-prompt or unrelated refactor.
Finding ID | Reproduction | Root cause | Smallest safe fix | Targeted retest | Regression tests | Severity | Human gate if | Status | Evidence
Not Started
REQUIRED CORRECTION RECORD FORMAT | Finding → reproduction → expected/actual → root cause → smallest fix → affected tests → regression result → final disposition. Never mark a finding closed without evidence.

## Code Review
D2-23 — CODE REVIEW
Review AI-generated code, dependency changes, editor integration, authorization and business calculations. Fix findings only; no unrelated refactor.
ID | Review area | Questions | Evidence | Expected result | Finding severity | Correction rule | Source | Priority | Status | Notes
CR-01 | Requirements | Does implementation match Phase 1-8 specs and R01-R27? | Diff/spec review | No material mismatch | High/Critical | Fix only mismatch | D2-23 | P0 | Not Started
CR-02 | Architecture | Does code respect existing data/storage/editor boundaries? | Architecture/code review | No unnecessary stack change | High | Focused fix | D2-23 | P0 | Not Started
CR-03 | Dependencies | Were unapproved libraries/services added? | Package/license/config scan | Only approved/free dependencies | High/Critical | Remove/replace | D2-23 | P0 | Not Started
CR-04 | Editor integration | Are engine APIs used rather than custom engine internals? | Editor integration review | Provider-native implementation | Medium/High | Refactor only affected area | D2-23 | P1 | Not Started
CR-05 | Authorization | Are sensitive mutations server-enforced? | API route review + tests | Server-side enforcement | Critical | Fix before completion | D2-23 | P0 | Not Started
CR-06 | Custom JS | Is JS isolated and admin-restricted by default? | Runtime + code review | No app-origin arbitrary execution | Critical | Fix before completion | D2-23 | P0 | Not Started
CR-07 | Plugin system | Is plugin registration controlled and versioned? | Registry/API review | Admin allowlist | Critical | Fix before completion | D2-23 | P0 | Not Started
CR-08 | Financial calculations | Are allowance/reimbursement/carry-forward calculations unchanged and test-backed? | Code + test review | Matches Phase 6 policy | Critical | Fix + rerun financial suite | D2-23 | P0 | Not Started
CR-09 | Error handling | Are failures logged safely without leaking secrets? | Error path review | Safe errors | High | Focused fix | D2-23 | P1 | Not Started
CR-10 | Maintainability | Is code consistent with project standards? | Standards review | No avoidable duplication/dead code | Medium | Focused cleanup only | D2-23 | P1 | Not Started
CR-11 | Tests | Are P0 acceptance tests reproducible? | Test suite review | Critical flows covered | High | Add/fix targeted tests | D2-23 | P0 | Not Started
CR-12 | Scope | Did AI implement later-phase deployment work? | Diff review | No D2-24/D2-25 changes | High | Revert/defer | D2-23 | P0 | Not Started

## Human Gates
HUMAN INTERVENTION GATES
Stop exactly when human action is required; never request secrets in chat.
Gate | Trigger | AI must not do | Exact user action | After action | Verification | Resume command | Severity | Status | Evidence
HG9-01 | Phase 8 predecessor materially incomplete | Do not hide regression or assume it is complete. | Resolve predecessor issue or approve focused repair. | AI reruns predecessor smoke tests. | Test evidence | DONE — RESUME PHASE 9 | Critical | Pending
HG9-02 | Authorization semantics materially conflict with source/open decisions | Do not invent access rules. | Confirm required permission behavior where source is genuinely unresolved. | Record decision and test server boundary. | ACL test | DONE — RESUME PHASE 9 | High | Pending
HG9-03 | Critical security architecture issue cannot be safely fixed in-scope | Do not bypass, disable or downgrade the security boundary. | Provide required architectural decision/configuration. | AI verifies safe correction. | Security retest | DONE — RESUME PHASE 9 | Critical | Pending
HG9-04 | Credential rotation/configuration is required | Do not ask for credentials in chat. | Perform secure credential/configuration action outside chat and confirm completion. | AI verifies without reading secret value. | Secret hygiene/config test | DONE — RESUME PHASE 9 | Critical | Pending
HG9-05 | Paid/billing dependency detected | Do not enable billing silently. | Keep ₹0 architecture or explicitly change cost constraint. | AI reruns cost audit. | Dependency scan | DONE — RESUME PHASE 9 | Critical | Pending
HG9-06 | Q05 accounting semantics remain unresolved and block financial reconciliation | Do not invent accounting outcome. | Confirm policy interpretation or configure approved policy. | AI reruns affected financial suite. | Financial matrix | DONE — RESUME PHASE 9 | High | Pending
HG9-07 | Production deployment requested during Phase 9 | Do not deploy. | Defer to Phase 10. | AI records handoff only. | Handoff review | DONE — RESUME PHASE 9 | High | Pending

## Dependency & Cost Gate
DEPENDENCY & COST GATE
Phase 9 must verify the architecture remains within the approved ₹0 additional-cost constraint.
Area | Expected | Allowed | Forbidden | Verification | Gate | Source | Status | Evidence
Auth | Firebase Auth | Existing stack | New paid auth | Dependency/config review | HG9-05 | Required Tools | Not Started
DB | Firestore | Existing stack | New paid DB without need | Dependency/config review | HG9-05 | Required Tools | Not Started
Files | Google Drive | Existing storage | Mandatory Firebase Storage/Blaze | Storage/config review | HG9-05 | Required Tools | Not Started
Email | Gmail API | Existing MOM path | Paid transactional email | Dependency/config review | HG9-05 | Required Tools | Not Started
Editor | Open-source mature editor | Existing integration | Paid mandatory editor plugins | Package/license scan | HG9-05 | Required Tools | Not Started
Realtime | Firestore updates if needed | Existing stack | Liveblocks mandatory | Dependency scan | HG9-05 | Required Tools | Not Started
Jobs | Existing server/runtime | Existing capabilities | Trigger.dev mandatory | Dependency scan | HG9-05 | Required Tools | Not Started
Hosting | No-cost planned deployment route | No production deployment in Phase 9 | Paid hosting requirement | Record only for Phase 10 | HG9-05 | Required Tools | Not Started

## Context Updates
CONTEXT, PROGRESS & EVIDENCE UPDATES
Required for autonomous resumption and Phase 10 handoff.
File | Required update | Record | When | Verification | Do not record | Owner | Status | Evidence
project-overview.md | Yes | Integrated production-readiness state and remaining deployment boundary | Closeout | Consistent with code | Secrets | AI | Not Started
architecture-context.md | Yes | ACL, security findings, QA architecture, correction decisions | During/closeout | Matches implementation | Credentials | AI | Not Started
code-standards.md | If needed | Testing/review/security patterns | When introduced | Matches code | Secrets | AI | Not Started
ai-workflow-rules.md | Yes if new gate behavior | Correction loop and human gates | At gates/closeout | Resume protocol intact | Secrets | AI | Not Started
ui-context.md | If needed | QA-discovered UI behavior/constraints | Closeout | Matches actual UI | Private data | AI | Not Started
progress-tracker.md | Yes after every unit/finding | Unit state, findings, tests, exact resume point | Continuously | Matches repo | Secrets | AI | Not Started
agents.md | If needed | Phase 9/10 boundary rules | If changed | Executable | Credentials | AI | Not Started
Decision register | Yes | Material ACL/security/cost/Q05 decisions | Immediately | Source-backed | Secrets | AI | Not Started
Correction log | Yes | Every finding and disposition | Every correction | Reproducible | Secrets | AI | Not Started
Git checkpoint | If configured | Review-ready Phase 9 state | Closeout | Recoverable | Tokens | AI | Not Started

## Stop Resume Protocol
STOP / RESUME PROTOCOL
This loop must repeat until all Phase 9 P0 work is complete.
Step | AI behavior | Required output | User action | AI after resume | Evidence | Forbidden | Status
1 | Run until genuine human gate. | Gate ID + blocker + completed work + exact action + resume command. | Perform exact requested action. | Wait. | Saved gate/tracker state | Continuing while blocked | Mandatory
2 | Stop completely. | Example: BLOCKED AT HG9-03 — critical auth boundary cannot be safely corrected within current architecture. Do not continue. Provide/approve required decision, then DONE — RESUME PHASE 9. | Resolve/decide. | Reread state and verify. | Gate evidence | Guessing/bypassing | Mandatory
3 | Resume exact point. | Do not restart unrelated work. | Send DONE — RESUME PHASE 9. | Verify then continue pending unit/finding. | Verification output | Assuming action succeeded | Mandatory
4 | Failure after resume. | Explain exactly what remains. | Resolve remaining human action if applicable. | Retest. | Updated evidence | Marking pass without evidence | Mandatory
5 | Every correction. | Update finding, test and context. | None unless gate. | Continue after targeted regression. | Correction record | Broad refactor | Mandatory
6 | Completion. | Final report + Phase 10 handoff; stop. | No automatic deployment. | End Phase 9. | Handoff/checkpoint | Starting Phase 10 automatically | Mandatory

## AI Studio Master Prompt
GOOGLE AI STUDIO — PHASE 9 MASTER EXECUTION PROMPT
Operational instruction; this workbook remains the detailed specification.
MASTER PROMPT
You are the autonomous implementation, security, QA and review agent for PHASE 9 of the Master Website application. AUTHORITATIVE SOURCES 1. This entire Phase 9 workbook. 2. The uploaded Master_Website_2_Day_App_Build_Checklist_ZERO_ADDITIONAL_COST_Google_AI_Studio.xlsx. 3. The actual repository/codebase. 4. Phase 8 handoff and all durable project context. MISSION Complete ONLY: D2-19 Flexible access D2-20 Security audit D2-21 End-to-end QA D2-22 Financial test suite D2-23 Code review DO NOT PERFORM D2-24 production deployment D2-25 production smoke test/final handover Do not deploy, publish production infrastructure, or move production secrets in Phase 9. AUTONOMOUS LOOP Read everything → restore Phase 8 context → inspect actual repo → verify predecessor → plan P9-01 → execute/test → verify → persist evidence → continue. At any human gate: STOP completely. Tell the user: - exact gate ID, - why it blocks, - what has been completed, - exactly what the user must do, - then wait for: DONE — RESUME PHASE 9 After resume: - reread saved progress, - verify the human action, - resume at the exact blocked point, - do not redo unrelated completed work. D2-19 — FLEXIBLE ACCESS Use the source Permissions Matrix as the acceptance contract. Test both UI and direct API behavior. Server-side enforcement is mandatory. Verify: - dashboard/module access, - project create/edit/delete, - project membership, - checklist/expense files, - budget allocations, - own OOP, - other employee OOP, - salary, - salary report, - investments, - MOM, - custom page create/edit, - CSS, - JS, - themes/templates, - plugins, - publish, - Drive assets. D2-20 — SECURITY AUDIT Audit actual behavior: - authentication, - authorization, - sensitive-data isolation, - file access, - custom JS isolation, - XSS, - CSRF, - injection, - storage rules, - admin endpoints, - secrets, - published-page boundaries, - plugin boundaries, - dependency/license/cost compliance, - safe error handling. Every finding must be reproduced, severity-classified, corrected or explicitly documented with reason and owner. Critical findings cannot be left unresolved. D2-21 — END-TO-END QA Run the master journey exactly: login → project → countdown → Excel upload → expense → OOP → salary → report → MOM email → custom page → publish → responsive preview. Also verify Notes and cross-module navigation/permissions. Capture exact failures. D2-22 — FINANCIAL TEST SUITE Use the already configured Phase 6 policy. Do not invent a new ₹5,000 interpretation. Test: - below threshold, - exactly threshold, - above threshold, - carry-forward, - partial salary payment, - duplicate claim prevention, - approved/rejected claims, - salary report reconciliation, - period consistency, - budget vs spend. All expected totals must reconcile. D2-23 — CODE REVIEW Review: - spec compliance, - architecture, - dependencies/licenses, - editor integration, - authorization, - custom JS isolation, - plugin boundary, - financial calculations, - error handling, - maintainability, - tests, - phase scope. Fix findings only. Do not perform unrelated refactors. CORRECTION LOOP For each failure: 1. reproduce, 2. identify root cause, 3. make smallest safe fix, 4. rerun affected test, 5. rerun relevant regression, 6. record evidence, 7. continue. Do not mark a finding resolved without evidence. COST ₹0 additional cost is a hard invariant. If any service/configuration requires billing or a paid dependency appears: STOP at HG9-05. Do not enable billing silently. SECRETS Never request, print or commit passwords, private keys, OAuth refresh tokens or other secrets in chat. If credential rotation/configuration is needed: STOP and tell the user to perform the secure action. PHASE BOUNDARY Do not deploy. Do not perform D2-24/D2-25. Record all production requirements for Phase 10. COMPLETION Phase 9 is complete only when: - D2-19 passes, - D2-20 has no unresolved critical finding, - D2-21 critical journeys pass, - D2-22 financial totals reconcile, - D2-23 review findings are resolved/documented, - cost remains compliant, - context/progress are synchronized, - Git checkpoint exists if configured, - Phase 10 handoff is complete. FINAL REPORT Report: - units completed, - ACL matrix result, - security findings and dispositions, - E2E results, - financial test results, - code review findings, - corrections made, - cost/dependency result, - human gates, - context/Git state, - known deferred items, - exact Phase 10 starting point. STOP AFTER PHASE 9.

## Completion & Phase 10 Handoff
PHASE 9 COMPLETION GATE & PHASE 10 HANDOFF
Phase 9 ends with a verified, review-ready build. Production deployment belongs to Phase 10.
Gate | Requirement | Evidence | Pass condition | If not passed | Owner | Status | Completed | Phase 10 relevance | Notes
C9-01 | D2-19 ACL complete | ACL matrix | All P0 access tests pass | Correct/gate | AI | Not Started |  | Critical
C9-02 | D2-20 security audit complete | Security audit + finding log | No unresolved critical issue; high issues dispositioned | Correct/gate | AI | Not Started |  | Critical
C9-03 | D2-21 E2E complete | Journey evidence | All critical flows pass | Correct/gate | AI | Not Started |  | Critical
C9-04 | D2-22 financial suite complete | Financial matrix | All expected totals reconcile | Correct/gate | AI | Not Started |  | Critical
C9-05 | D2-23 review complete | Review log | Findings resolved/documented | Correct/gate | AI | Not Started |  | Critical
C9-06 | Cost verification | Dependency audit | No unexpected paid dependency | HG9-05 | AI | Not Started |  | Critical
C9-07 | Context/progress | Context files + tracker | Matches actual repo | Update | AI | Not Started |  | Critical
C9-08 | Git checkpoint | Commit/checkpoint | Recoverable state | Create before close | AI | Not Started |  | Critical
C9-09 | Phase 10 handoff | Handoff below | Deployment can begin without rediscovery | Write before close | AI | Not Started |  | Critical
PHASE 10 HANDOFF TEMPLATE
Build state
ACL state
Security findings/dispositions
E2E QA result
Financial test result
Code review result
Known deferred non-critical issues
Cost/dependency verification
Environment variables required for production | Names only; never paste secret values here
Production auth configuration needed
Production DB/storage/email configuration needed
Published-page runtime/route configuration
Hosting/deployment route selected
Production smoke checklist to execute
Git checkpoint
Exact Phase 10 starting point | D2-24 Deploy → D2-25 Production smoke + final handover
Do not redo | Verified D2-19:D2-23 unless a production deployment regression requires investigation

## Decision Register
PHASE 9 DECISION REGISTER
Record only material decisions. Do not silently change accounting, permissions, security or deployment semantics.
ID | Question | Source/default | Decision | Evidence | Impact | Date | Owner | Status
Q02 | Standard users create projects? | Configurable; admin can enable | Use existing Phase 3/4/5 decision. If unresolved and affects tests, gate. | Context/permissions evidence | Project ACL tests |  | AI/User | Open/Verify
Q05 | Exact ₹5,000 interpretation? | Configurable threshold + requested extra ₹5,000 line item | Use Phase 6 recorded configuration; do not reinterpret. | Phase 6 decision/config | Financial tests |  | AI/User | Open/Verify
COST | Additional cost? | ₹0 hard constraint | Preserve. | Master workbook | All architecture |  | AI | Resolved
SECURITY | Critical finding disposition | No critical finding may remain unresolved | Record correction or explicit human gate; no silent risk acceptance. | Security finding log | Phase 10 readiness |  | AI/User | Open

## Workbook Index
WORKBOOK INDEX
Navigation for autonomous Phase 9 execution.
Sheet | Purpose | When read | Authority | Human action | Status
START HERE | Mission/scope/cost/phase boundary | First | Master workbook | Only at gates | Mandatory
Autonomous Control | Execution rules | First/continuous | Playbook | At gates | Mandatory
Requirements Freeze | R01-R27 treatment | Planning | Master workbook | If unresolved | Mandatory
ACL Verification Matrix | D2-19 permission tests | D2-19 | Permissions Matrix | Only if ambiguity | Mandatory
Security Audit | D2-20 security audit | D2-20 | Master workbook | At critical gates | Mandatory
End-to-End QA | D2-21 critical journey | D2-21 | Master checklist | No unless failure | Mandatory
Financial Test Suite | D2-22 calculations | D2-22 | Master checklist + Phase 6 | Q05 if unresolved | Mandatory
Correction Loop | Root-cause/focused fix records | Every finding | Playbook | At gates | Mandatory
Code Review | D2-23 review | D2-23 | Master checklist | At critical finding | Mandatory
Human Gates | Stop/resume gates | At blockers | Playbook | Yes | Mandatory
Dependency & Cost Gate | ₹0 verification | Before/closeout | Required Tools | Yes if violated | Mandatory
Context Updates | Durable state | Continuously | Playbook | No | Mandatory
Stop Resume Protocol | Exact resume behavior | At every gate | User workflow | Yes | Mandatory
AI Studio Master Prompt | Operational prompt | Start/reset | Entire workbook | No | Mandatory
Completion & Phase 10 Handoff | Closeout and next phase | End | 10-phase sequence | No | Mandatory
Decision Register | Material decisions | As needed | Open Questions | Yes where needed | Mandatory
Playbook Alignment | Method audit | Review | Playbook | No | Reference

## Playbook Alignment
PLAYBOOK ALIGNMENT
Phase 9 implementation of architecture → context → feature verification → review → handoff.
Principle | Application | Evidence | Scope protection | Human gate | Status | Owner | Notes
Architecture before coding | Restore Phase 8 state and inspect real repo before ACL/security/QA. | P9-01 | No tests based only on tracker | Predecessor gate | Applied | AI
Server-side authorization | Direct API tests for every sensitive capability. | ACL matrix | No UI-only protection | Security gate | Applied | AI
Security audit | Concrete audit categories from D2-20. | Security Audit | No full pen test beyond source scope | Critical finding gate | Applied | AI
Explicit acceptance | Exact D2-21 journey + D2-22 financial suite. | QA sheets | No vague 'looks good' | Failure loop | Applied | AI
Focused corrections | Smallest safe fix + targeted regression. | Correction Loop | No unrelated refactor | Architecture gate | Applied | AI
Review before completion | D2-23 review against specs/context. | Code Review | No deployment here | Critical finding gate | Applied | AI
Cost-aware | Verify no unexpected billing dependency. | Cost Gate | No billing enablement | HG9-05 | Applied | AI
Human agency | Stop only for decisions/configuration the AI cannot safely perform. | Human Gates | No guessing | DONE — RESUME PHASE 9 | Applied | AI
Durable progress | Update context/tracker/Git and produce Phase 10 handoff. | Context + Handoff | No memory-only state | None | Applied | AI